AUDIT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 24 September 2010 |
| Title: | Corporate Risk Management |
| Report of: | The Strategic Director and Deputy Chief Executive |
| Report reference: | CE 28/10 |

Summary:  The purpose of this report is to update Members on the Council’s Corporate Risk Register.

Recommendations:  The Committee is asked to note the contents of the report as an indication of the continuing commitment to sound governance arrangements for corporate risk management.

| Contact Officer: | Jason Gooding | Ext: | 7117 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	Audit Committee

Date:	24 September 2010

- Background

In accordance with the Council’s Risk Management Policy, the draft Corporate Risk Register is submitted to the Resources Overview and Scrutiny Panel (ROSP) for consideration on a quarterly basis.

This report contains the Risk Register (see appendix 1) that was presented to ROSP on 29 July 2010 and is the one that to which ROSP minutes from July 2010 refer to.  Subsequent amendments and scores will be discussed and agreed by the Senior Management Team and Corporate Risk Management Group.  These will be presented to ROSP in October 2010.

- Comments on the Corporate Risk Register

Following the restructure of the Senior Management Team (SMT) and introduction of new corporate priorities, a workshop was held to renew the Corporate Risk Register to reflect the new priorities and the Corporate Plan.  SMT and the Corporate Risk Management Group considered the issues and risks in delivering the Corporate Plan.  A risk management advisor from Marsh Ltd was also present to provide expert advice.

The corporate risks associated with delivering the Corporate Plan have been identified and assessed.  The current impact and likelihood of the risks have been scored according to criteria within the Council’s Risk Management policy.  Explanations of the ratings, as requested by ROSP, are shown in appendix 2.

The Action Status/ Control Strategies shown are the risk management strategies that are being adopted to reduce the impact and likelihood of the risks.  Future reports will show the changes in the score ratings resulting from the mitigating actions being taken, comparing the current with the previous risk score matrix, again as requested by ROSP.  Initiatives to reduce risk are incremental and thus changes to the risk scores over the short term are unlikely.  Target risk scores will also be identified; a certain level of risk will need to be tolerated in order to deliver the Council’s key objectives and promote change.

- Recommendations

The Committee is asked to note the Corporate Risk Register as an indication of the continuing commitment to sound governance arrangements for corporate risk management.

| Corporate Risk Register June 2010 Appendix 1 |  |
| --- | --- |

| Title | Description | Current Risk Matrix | Matrix Review Dates | Current Risk Rating | Rating Description | Current Action Status / Control Strategy | Managed By |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Limited Resources | There is a risk that scarce resources are not directed to priority areas within the Council's key objectives of local environment and local economy |  | 15 Jun 2010 | 12 | Impact Critical Likelihood Reasonably probable | To make sure that the Transformation Programme, and the Medium Term Financial Plan and the Annual Budget are coherently focussed toward the appropriate allocation of resources to deliver the organisation's key objectives. | Deputy Chief Executive |
| Strategic Housing Authority | There is a risk that the Council fails to deliver in it's role as a strategic housing authority in achieving a balanced housing market |  | 16 Jun 2010 | 12 | Impact Critical Likelihood Reasonably probable | Develop and deliver the transformation of economic development to ensure the Council can make an effective contribution to economic development objectives for Carlisle. | Strategic Director |
| Use of Resources and Assets | There is a risk that the Council fails to adequately use resources and assets to stimulate, support and sustain economic growth in the area. |  | 16 Jun 2010 | 12 | Impact Critical Likelihood Reasonably probable | To put in place fit for purpose arrangements for the management of our strategic operation and investment. These will form the subject of the asset management strategy. | Deputy Chief Executive |
| Effective and Efficient Neighbourhood services | There is a risk that the Council fails to deliver effective and efficient neighbourhood services, and improve residents' perception of Carlisle through local environment issues. |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | To develop and implement a cost efficient approach to neighbourhood management with key Council Partners. | Assistant Director (Local Environment) |
| Workforce Planning | There is a risk that the Council is unable to continue to deliver and develop services due to lack of skills/capacity within the workforce |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | Workforce Planning Group established; Organisational Devt strategy being developed to address authority-wide issues; Workforce planning tools being developed to identify and address current workforce planning issues. | Chief Executive |
| Supporting Employers | There is a risk that the Council fails to adequately support employers during the economic downturn. |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | The review of Carlisle's economic development strategy will focus the City Council and other Partners on their role in supporting city employers and encouraging new development in the area. | Strategic Director |
| Vision for the City | There is a risk that there is no clear consensus/ vision for the City’s economy and no agreed strategy with Partners. |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | The review of the work of Economic Development and Carlisle Renaissance will be integrated toward a new Strategy and Action Plan. This will be prepared for the new working group and inform the delivery board that succeeds Carlisle Renaissance. | Assistant Director (Economic Development) |
| Delivering Key Objectives | There is a risk that Members, employees and Partners do not deliver the Council's key objectives of local environment and local economy |  | 15 Jun 2010 | 8 | Impact Critical Likelihood Remote | The Transformation Programme is being explicitly designed to deliver the Council’s objectives as described in the Corporate Plan. | Chief Executive |
| Equality | There is a risk that the Council fails to meet Equality framework targets. |  | 16 Jun 2010 | 6 | Impact High Likelihood Remote | The comprehensive equality framework is currently being worked on, to be adopted by the Council in preparation for IDeA in October 2010. This will include peer assessment as part of CIEP. | Deputy Chief Executive |
| Community involvement in decision making | There is a risk that communities are not sufficiently engaged in the Transformation programme. |  | 15 Jun 2010 | 4 | Impact Marginal Likelihood Remote | Having a clear engagement strategy so that those decisions that will affect the community are timely and appropriate. | Assistant Director (Community Engagement) |

##### Impact Assessment                                                                                                Appendix 2

| Potential Impact | Critical 4 | High 3 | Marginal 2 | Negligible 1 |
| --- | --- | --- | --- | --- |
| Failure to meet a Council objective | Failure to deliver on a priority aim | Failure to deliver on a priority objective | Failure to deliver on a publicly stated performance | Failure to achieve an internally agreed objective |
| Cost, including legal and insurance costs | Council revenue or capital budget impact of 5% | Council revenue or capital budget impact of 1-5% | Council revenue or capital budget impact of less then 1% | Council revenue or capital budget impact of less than £30k |
| Death, injury, or illness of staff or a member of the public | Death or serious injury of a service user, member of staff, or member of the public due to Council actions or inaction | Injury of a service user, member of staff, or member of the public due to Council actions or inaction | Death or serious injury of a service user, member of staff, or member of the public despite appropriate Council actions | Injury of a service user, member of staff, or member of the public despite appropriate Council actions |
| Disruption to service provision | Inability to provide business critical services | Reduced ability to provide business critical services in more then one location | Reduced ability to provide business critical services in one location | Slight reduction in business critical services in one location |
| Damage to public confidence in the Council | Widespread and permanent reduction in public confidence | Limited but permanent reduction in public confidence | Very limited and temporary reduction in public confidence. |  |
| Reduced user satisfaction with services | Widespread and permanent reduction in user satisfaction | Limited but permanent reduction in user satisfaction | Temporary reduction in user satisfaction | Very limited and temporary reduction in user satisfaction |
| Damage to the Council’s reputation | National adverse media coverage Damage to reputation with the government | Countywide adverse media coverage Compulsory redundancies | Localised adverse media coverage | Isolated adverse media coverage |
| Failure to comply with legislation | Conscious failure to comply with legislation | Unconscious failure to comply with legislation |  |  |
| Failure to deliver government policy |  | Failure to deliver on stated government priority | Failure to deliver on multiple other government policies | Failure to deliver on one government policy |
| Damage to assets | Destruction of building (s) Inability to maintain information infrastructure | Damage in excess of £100k Minor reductions in information infrastructure | Damage in excess of £30k | Damage less than £30k |
| Damage to the environment | Permanent and significant environmental damage | Permanent environmental damage | Temporary environmental damage |  |

##### Likelihood Assessment

Probable – likely to occur in the short term

Reasonably probable – probably will occur at some point

Remote – may occur in time

Extremely remote – unlikely to occur

Risk Scoring

| Probable 4 | 4 | 8 | 12 | 16 |
| --- | --- | --- | --- | --- |
| Reasonably probable 3 | 3 | 6 | 9 | 12 |
| Remote 2 | 2 | 4 | 6 | 8 |
| Extremely Remote 1 | 1 | 2 | 3 | 4 |
|  | Negligible Impact 1 | Marginal Impact 2 | High Impact 3 | Critical Impact 4 |