CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 9 June 2009 |
| Title: | PAY AND WORKFORCE STRATEGY PROJECT UPDATE |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 11/09 |

Summary:

The project is in its final stage (Implementation). Although we had agreed a Final Negotiated Position with the two main trade unions in December 2008 the project was not implemented on 1 April 2009 as had been anticipated. Whilst one of the two unions, GMB, voted overwhelmingly in favour of the deal, the other Unison, is unwilling to go to ballot. As such the project has stalled.

The Senior Management Team is now putting the finishing touches to its proposal to address this hiatus which it is to bring before the Employment Panel on 12 June.

Questions for / input required from Scrutiny:

Members to monitor progress.

Recommendations:

Members to note progress and comment as appropriate.

| Contact Officer: | David Williams | Ext: | 7082 |
| --- | --- | --- | --- |

- GENERAL PROGRESS

1.1	The Pay & Workforce Strategy (PWS) project has 6 work packages, i.e.

- Job Evaluation

- Equal Pay Review

- Review of People Policies and Terms and Conditions

- Single Status

- Workforce Development Plan

- PWS Implementation.

  - The project is in accordance with Prince 2 methodology and as such is overseen by a Project Board chaired by the Deputy Chief Executive. Regular progress reports are presented to Members of the Corporate Resource Overview and Scrutiny Committee, with the last one being in April 2009.

  - The project is in its final stage (Implementation) for which an Action Plan has been agreed. This plan also embraces the remaining actions that will complete the other work packages. Job Evaluation, Single Status and Equal Pay are the key elements at this stage. Progress is reported at-a-glance in the right hand column of the action plan (see Appendix 1) with more detail provided in the body of this report. In compliance with a request from CROS, this plan has been slightly modified to show revised target dates where appropriate.

  - Agreement had been reached with the trade unions in December on all aspects of single status and all elements of a new pay policy. In early January we had also achieved a Final Negotiated Position on the key issues of a pay-line, back pay and protection. Two further steps remained before a formal agreement could be reached – a ballot of union members by the two main unions (GMB and Unison) and approval of the financial package by Members.

  - As regards Member approval, a meeting of the Employment Panel has been called for 12 June. It is intended that this will start the process whereby Council will be recommended to make a decision on implementing the project.

  - GMB conducted their ballot and the result was a resounding endorsement of the deal. Unfortunately Unison has refused to do and appear to have withdrawn from the agreement we reached in principle with them. Without the support of both unions a collective agreement to proceed is impossible.

  - There had been extensive communication of the agreed deal to employees who originally had been told that everything would change on 1 April. Employees are generally confused and unsettled now. Senior management have kept employees informed as best we can but it is hard to describe the situation as anything but unsatisfactory.

- SPECIFIC PROGRESS

  - Job Evaluation

Phase 1 Job Evaluation ended seven months ago. Phase 2 of JE is will finish during the summer. Nearly all those posts that changed during the project and those recently created new posts have now also been evaluated. There is still work to do to finish all those posts that are career graded (i.e. other steps along the career path are now being scored) and this is proving complex and time consuming. However, there are no implications for the project.

    - We are continuing with job evaluation through the current uncertainty as it is now a well-established, consistent, fair, and generally accepted method of determining the value of jobs. However, we have no new pay policy as yet which in theory could mean that our continued use of job evaluation beyond the project could be in doubt (see 2.4.1).

  - Single Status

    - Agreement was reached and implemented in April 2007 in three areas: holidays, sickness and overtime.

    - Agreement with the unions had also been reached last December in all of the remaining areas (bar one) although none can yet be implemented as explained in 1.6 above.

    - The one remaining area was car lease/car allowances. SMT agreed that this matter be considered as part of the Green Travel Plan rather than within PWS and the unions were content with this. Since when CROS itself has decided to investigate.

  - Equal Pay

    - As part of the PWS project’s equal pay work-package officers had analysed our pay structure in order to determine existing pay gaps, and during pay modelling we then examined the impact of the proposed new pay policy and structure on these gaps. We determined that our proposed new pay structure will, once it has been fully implemented, remove or significantly narrow whatever pay gaps currently exist between the sexes.

    - We have recently engaged Northgate Arinso Reward Consultants whose research and analysis is serving to validate our understanding. Their final report is not due for a few days but we have received an interim report. This finds that “There is some risk of equal pay claims within the current arrangements which are addressed through the revised pay and grading proposals”. Key findings include:

- the potential risk from equal pay claims were we to do nothing, or to reaffirm the status quo, runs to around £1million

- average female pay is significantly higher than male where jobs are now rated as equivalent through the outcome of job evaluation

- the proposed new structure will address the pay gap e.g. in Grade D male pay will be at 98% of average female pay and within two years all employees will be at the same point.

  - Pay Policy

    - We had agreed a new Pay Policy for the authority providing consistent and robust principles and procedures. All the single status areas were assimilated and job evaluation was endorsed as the basis for determining pay in future.

    - Transitional arrangements such as back-pay and protection were agreed at the same time and included within the new pay policy.

    - Because only one of the unions has endorsed the project outcome then the future of this policy could be in doubt.

- WAY FORWARD

  - For reasons which have never been fully explained Unison have refused to go to ballot and have effectively withdrawn from the Final Negotiated Position we agreed with them many months ago.

  - The status quo is not sustainable for several reasons, not least of which is because it leaves us vulnerable to legal challenge (see 2.3.2) so we are not in a position whereby we can tolerate this stalemate much longer.

  - SMT is now putting the finishing touches to its proposal to address this hiatus which it is to bring before the Employment Panel on 12 June.

4.	RECOMMENDATIONS

4.1	Members to note progress and comment as appropriate.

Appendix 1

### PWS Implementation Action Plan: Progress as at 31 May 2009

|  | Main work package | Tasks | Duration | Target date | Revised target date | Progress at 31 May 2009 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Implement PWS | Draw up a pay policy; Principles Research market Consult (SMT, Members, unions, staff) Tie in with Single Status (see 2.1) | 1 month | End of July 2008 | Unknown | A new Pay Policy was agreed with both unions in December but now Unison are in dispute |
| 1.2 |  | Devise a pay structure: JE scores (see 4.1) Research markets for pay rates Pay modelling Costs Consult (SMT, Members, unions, staff) | 1 month | End of August 2008 | Unknown | A Final Negotiated Position was agreed with both unions in January but now Unison are in dispute |
| 1.3 |  | Member approval (Executive, CROS, Employment Panel, Council?) | 1 month | End of September 2008 | Unknown | An Employment Panel has been called for 12 June |
| 1.4 |  | Assimilate staff to new pay structure | 1 month | End of October 2008 | Unknown | Awaits outcome of 1.3 |
| 1.5 |  | Issue revised Statement of Provision to staff | 1 month | End of October 2008 | Unknown | Awaits outcome of 1.3 |
| 1.6 |  | Amend Trent so as to insert new staffing structure | 3 months | End of December 2008 | Unknown | Awaits outcome of 1.3 |
| 1.7 |  | Implement outcomes of Phase 2 Job Evaluation (see 4.2) as in 1.3 – 1.6 above | 5 months | End of March 2009 | Unknown | Phase 2 JE is well underway but its outcomes can not be implemented until 1.3 is concluded |
| 1.8 |  | Consolidate implementation – documentation, correct job titles, clear reporting lines, updated job descriptions | 2 months | End of May 2009 | Unknown | Awaits outcome of previous actions |
| 2.1 | Single Status | Complete research and assessment of areas yet to be harmonised: Professional fees Extent/pay for shift work/premium payments Car allowances/leases Additional duties/Acting up Other allowances – tool, bonus, first aid, E planning, other representative roles etc Stand by/call out Flexi/flexible working Time sheet removal | 2 months | Proposals consulted on by end of August 2008 | n/a | Concluded |
| 2.2 |  | Cost and draft proposals | 1 month | End of July 2008 | n/a | Concluded |
| 2.3 |  | Consult on proposals | 1 month | End of August 2008 | n/a | Concluded |
| 2.4 |  | Draw up final proposals & link to implementation | 1 month | End of August 2008 | Unknown | Reached agreement with both unions on all areas in December but Unison position is now unclear |
| 3.1 | Equal Pay | Assess current picture | 2 weeks | End of July 2008 | n/a | Concluded |
| 3.2 |  | Carry out Equality Impact Assessments on proposed new pay structure(s) | 3 weeks | End of September 2008 | June 2009 | External consultants report is due 8 June |
| 3.3 |  | Identify and explore validity of any outstanding Equality concerns | 1 month | By December 2008 | Unknown | Awaits outcome of 1.2 and 1.3 |
| 3.4 |  | Create a draft action plan to address issues – including consultation as appropriate | 1 month | End of December 2008 | Unknown | Awaits outcome of 3.3 |
| 4.1 | Job Evaluation | Complete Phase 1 (existing scored jobs): Complete all appeals Notify staff of outcome Publish scores Pass information to Pay Modeller in a form it can be used (see 1.2) | underway | End of August 2008 | n/a | Concluded |
| 4.2 |  | Phase 2 Job Evaluation: Obtain information to allow outstanding jobs to be scored – new/amended jobs since Autumn 2007 Temp jobs anticipated to have gone but have not Casuals Career grades Arrange panels & type up/distribute the information Support and participate in Steering Panels Obtain any additional information required Support and participate in Appeal Panels Notify and publish scores Complete documentation See also 1.7 above | 5 months | End of March 2009 | End of July 2009 | Due to the complexity of existing career graded posts the end date has been put back to end of July. |
| 4.3 |  | Complete documentation to enable it to be easily retrieved when required | As in 4.2 | End of March 2009 | End of May 2009 | Underway |
| 4.4 |  | Set up an ongoing (‘mainstreamed’) Job Evaluation arrangement so as to score all new and changed jobs occurring after the end of the PWS project. Agree this with unions and Employment Panel | 1 month | 1 April 2009 | Unknown | We were going to use the arrangements agreed within the new Pay Policy but this is now in doubt. Implementation date was 1 April but now can not be predicted |
| 5 | General – all packages | Document and monitor project and highlight any issues and potential slippage Draft and produce reports, briefing notes, consultation documents, PWS Board reports, minutes CJC at intervals Inform Portfolio Holder throughout CROS at intervals Communication e.g. surgeries, road shows, presentation, newsletters etc | underway | End of March 2009 | Unknown | Date for a conclusion of project is now uncertain. |