| Indicator | Performance 2002-3 | Target 2003-4 | Interventions S = short term (within 3 months) M = medium term (3 – 6 months) L = long term (6-12 months/ongoing) | Status Green = on target Amber = in some danger Red = unlikely to be achieved | Comments |
| --- | --- | --- | --- | --- | --- |
| BV 126 Domestic Burglaries (per 1000 households) | 11.87 | 13.4 | Handy van scheme L – (crime prevention help and reassurance services to victims & vulnerable groups - launch 16th February) SHIRPA scheme in Petteril Bank and Raffles now live – 80% reduction in properties with cameras. Management issues L Persistent offenders project (P.R.O.P) – intensive support and supervision of identified offenders L | Green Green Green | 140 referrals made by British Gas, through Help the Aged. Already at capacity, and providing valuable support to Partners and the Community. CHA administrator established. Scheme in maintenance phase. Exit through commitment from Social Housing provider. Current agreement one year only. Twelve offenders engaged in the project. Additional support on Housing matters provided through Basic Command Unit budget. Scheme is supporting the Partnership meet its responsibilities under the National Drugs, and Prisoner Resettlement Strategies. Risks to success are failure of clients to engage. However, achievements outweigh risks in that, it is estimated that several hundred [a more accurate estimate is being calculated] crimes have been prevented through engaging prolific offenders on the scheme. |
| Indicator | Performance 2002-3 | Target 2003-4 | Interventions S = short term (within 3 months) M = medium term (3 – 6 months) L = long term (6-12 months/ongoing) | Status Green = on target Amber = in some danger Red = unlikely to be achieved | Comments |
| BV 127 Violent Crime (per 1000 population) | 13.65 | 11.7 | Extension of CCTV into identified hotspot for alcohol related violent crime – West Walls (partnership funded) S Continuation of door supervisor registration scheme L Progress action plan for drug and alcohol related violent crime L Progress action plan for domestic violence L | Amber Green Green Amber | Planning permission obtained and materials commissioned. Ongoing. Managed by Police and City Council Licensing (due for change) Action plan terminated. Relevant actions are mainstreamed into Partners activity [support for Pub Watch etc], or are not viable. Activity linked to that of County Group’s action plan and LPSA targets. New CDRP officers to support work of Local DV Group. |
| BV 128 Vehicle Crimes (per 1000 population) | 14.38 | 13.92 | Persistent offenders project (P.R.O.P) – intensive support and supervision of identified offenders L | Green | As above. |
| Indicator | Performance 2002-3 | Target 2003-4 | Interventions S = short term (within 3 months) M = medium term (3 – 6 months) L = long term (6-12 months/ongoing) | Status Green = on target Amber = in some danger Red = unlikely to be achieved | Comments |
| LP 134 Public Disorder (per 1000 population) | 99.00 | 88.32 | Continue to explore funding opportunities to extend CCTV L Lighting project – Currock & Upperby – M Anti-Social Behaviour Anti-Social Behaviour Co-ordinator post funded through CDRP L (previously under CV4) | Amber Green Amber | The CCTV sub group acknowledges limitations of City Council to expand systems and maintain effective monitoring. Recommend that the partnership explore utilising mobile systems to manage crime hotspots. Accepted by CDRP leadership on 16.12.03. Working party visiting Blackpool to assess existing scheme w/c 25.1.04. Work commissioned. Assessment of impact to be arranged through Hotspots task group. ASB co-ordinator will be charged with delivering the CDRP ASB action plan – Jan Gordon in post. Only twelve months remaining of strategy, ability to deliver strategy limited by time. Officer to focus on building relationships and developing strategy for 2005/8. |
| Indicator | Performance 2002-3 | Target 2003-4 | Interventions S = short term (within 3 months) M = medium term (3 – 6 months) L = long term (6-12 months/ongoing) | Status Green = on target Amber = in some danger Red = unlikely to be achieved | Comments |
| CV4 Recorded Crimes (per 1000 population) | 105.87 | 103.95 | Criminal Damage (currently 25% of all recorded crimes) detailed analysis completed - L Domestic Burglary and Vehicle Crime CDRP has appointed a Neighbourhood Watch Development Officer (18/11/02) – targeted activity in Hotspot areas, PLUS focus on farm watch L Prolific Offenders In Carlisle between April 1998 and January 2002, 13 offenders were responsible for 2.7% of recorded crimes. CDRP has applied the problem-solving model and developed the P.R.O.P scheme (as above) L | Red Amber Green | Community Intelligence Assistant [project administrator – CDRP funded] post vacant –scheme lapsed. Prior to vacancy, CDRP identified problems with project management that impacted on efficiency. The new Anti Social Behaviour Act provides Local Authorities with additional powers to tackle Graffiti, fly tipping and litter. Addressing environmental issues is a priority in the “Together Tackling Anti Social Behaviour”, National Action Plan. The Local Authority urgently needs to consider its policies and contribution to this plan. CDRP funding seminar for planning officers, developers and architects, to improve knowledge, and implementation, of SBD principles. Burglary dwelling PI’s not being met. Youth Offending Team developing ISSP (Intensive Supervision & Support programme) for 10-17 yo’s – start date 1.10.03 – already at capacity. PROP operational – as above, add JIGSAW from 1.4.04 [report next mtg] |

# Text boxes

Crime and Disorder Performance Report –  28th January 2004.