CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 3rd April 2008 |
| Title: | Corporate Risk Management |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 14/08 |

Summary: The purpose of this report is to give members of the Corporate Resources Overview and Scrutiny Committee the opportunity to consider the Corporate Risk Register.

Questions for / input required from Scrutiny:

Scrutiny and feedback on the Corporate Risk Register.

Recommendations:

That Committee consider and comment on the updated Corporate Risk Register and identify any emerging risks for consideration by the Corporate Risk Management Group.

Committee is asked to note the planned review of risk management arrangements and the proposed use of Covalent for monitoring risks.

| Contact Officer: | Carolyn Mitchell | Ext: | 7306 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	Corporate Resources Overview and Scrutiny

Date:	3rd April 2008

- Background

In accordance with the Council’s Risk Management Policy, the draft Corporate Risk Register is submitted to this Committee for consideration on a quarterly basis.

This Report contains the latest quarterly update of the Register.

The Risk Register is at Appendix 1 and the summary of changes made in the last

quarter is at Appendix 2.

2. 	Comments on the Corporate Risk Register

Members will note that any change to a risk score is shown by a symbol in the movement column.

During the last quarter, the Current Action Status / Control Strategy sections have been addressed and updated where applicable and scoring of certain risks amended accordingly.

Some new risks have been added to the Corporate Risk Register and these will be considered, and control strategies developed, prior to the next report.

In addition to scrutinising and commenting on the Risk Register, members of this committee are invited to suggest emerging risks for consideration by the Corporate Risk Management Group. If appropriate these will be incorporated into the Corporate Risk Register and members will be able to track their management at the next quarterly update.

3. 	Review of Risk Management Arrangements

Risk Management arrangements will be reviewed shortly, based on the ‘Risk Management Healthcheck’ template produced by Office of Government Commerce. The outcome of the review will be reported to a future CROS committee.

- Monitoring Risks using Covalent

Covalent, the Authority’s new performance management software, has a facility for monitoring risks. The Corporate Risk Register will be used to test/pilot this during the next quarter. It is anticipated that it will later be rolled out to service areas for maintaining their operational risk registers, and could be set to prompt managers for updates and automatically feed into the Corporate Risk Register, or provide an alert, when risk scores reach a defined level.

- Recommendations

The Committee is asked to consider and comment on the updated Corporate Risk Register and identify any emerging risks for consideration by the Corporate Risk Management Group.

The Committee is asked to note the planned review of risk management arrangements and the proposed use of Covalent for monitoring risks.

# CORPORATE RISK REGISTER Updated 14th March 2008

# Considered by Corporate Overview and Resources Committee 3rd April 2008

# Note: amendments in last quarter marked in red italics (or italics only on the printed version).

| Ref | Risk Description | Impact | Likeli-hood | Risk Score | Move-ment | Current Action Status/Control Strategy | Responsible Officer & date last updated |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Pay and Workforce Strategy Failure in the implementation of PWS  financial impact  impact on staff including Low morale/demotivation Retention difficulties Increased call on resources Impact on business/productivity Failure to implement succession planning | 4 | 3 | 12 | = | Implementation Plan and Programme determined and published Prince 2 methodology applied Regular Staff updates via Management Briefing and newsletters Continual monitoring of progress by Project Manager overseen by Project Board Project developed and delivered in partnership with Unions. Appeal panels are now scheduled to take place over the next few months. | Deputy Chief Executive 11/03/08 |
| 2 | Shared Services Consequent Shared Services risks are being assessed including:- Promised savings not realised Promised service improvements not realised Partners not engaging to an equal extent Governance arrangements not responsive enough to allow changes or amendments to | 3 | 3 | 9 | = | A shared services policy was agreed by the Council in March 2007. This clearly articulates that no shared services arrangement will be entered into by the City Council unless there are clear benefits for the authority that can be demonstrated in a full business case. This serves as a containment action that will reduce the impact of any shared services arrangements into which the City Council enters. An internal Shared Services and Efficiencies Working group has been formulated to oversee shared services and improvement/efficiencies reviews within the Council to the following terms of reference: - "To provide a forum to progress a detailed shared services strategy for delivery for the Council within the terms of the Shared Services Policy and to expand the remit of the group to cover wider efficiency and business improvement initiatives." In addition the Connected Cumbria Partnership Strategic Board (CCPSB) has initiated a large-scale service transformation programme to improve local public service delivery to deliver significant value for money. This programme has not only been shaped by the strong messages emanating from central government but also from key local drivers. The CCPSB is keen to adopt a strategic approach to service delivery across the whole of Cumbria in order to significantly improve the quality of life of their citizens. Financial savings have been built into the City Council's 2008/09 base budget in relation to improvement and efficiency reviews, and a budget has been approved to enable shared services and efficiency initiatives to be progressed. | Director of Corporate Services 11/3/08 |
| 3 | Carlisle Renaissance There is a strategic risk associated with withdrawal of the support of key partners at a sub-regional, regional and national level, loss of momentum and resultant loss of confidence within the local resident and business community. Capacity and the availability of resources are critical to this as well as effective engagement and communication mechanisms. Failure will be expressed in Reputational – failure to achieve stated objectives Financial – failure to secure and utilise funds appropriately Delivery – failure to manage a programme of growing scale and diversity. | 4 | 2 | 8 | ( | Consultants have been engaged to progress options for a Delivery Mechanism for Carlisle Renaissance to manage the delivery of development and infrastructure projects. A Detailed Application has been submitted for approval by the NWDA. This application will secure funding for additional development and project management capacity. Following discussions between Carlisle City Council and NWDA Chief Executive and Chairman, agreement has been reached on the establishment of a private sector led leadership group to drive forward Carlisle Renaissance.An interim Steering Group has been established to take forward the development of a Business and Action Plan for the delivery of the Strategy pending the formal creation of a new Board. This group includes representatives of the Carlisle City Council, Cumbria County Council, Cumbria Vision, the Northwest Development Agency, English Partnerships and the private sector led Economy & Enterprise Group of the Carlisle Partnership, responsible for the preparation of the new Carlisle Economic Strategy. The target date for the formal establishment of this new mechanism is April 2008. Progress will be monitored through the Corporate Resources Overview and Scrutiny Committee. | Director , Carlisle Re- naissance 11/03/08 |
| 4 | MediumTerm financial planning and maintaining asset values; failure leading to:- - risk of systems and procedures failing to address MTFP objectives - risk that expenditure not linked to key objectives and priorities - fails to be forward looking and programmed - lack of corporate ownership - failure to achieve balanced budget through the budgetary process - failure to match future commitments and aspirations compared to funding available - maintaining asset values | 4 | 2 | 8 | = | The MTFP and Capital Strategy were approved by Council on 17th July 2007, and an update for the next three year period is currently underway. The MTFP and Capital Strategy are reviewed regularly in the light of current pressures arising and this has been carried out throughout the 2008/09 to 2010/11 budget process. As predicted the RSG settlement, whilst not being zero in cash terms for this Council, was well below inflation. The increase was 1% in 2008/09, 0.5% 2009/10 and 0.5%2010/11, against general inflation of 2.8% being included in the 2008/09 estimates. The PWS implications, shortfalls in income projections and budget pressures in a number of areas are set out in the 2008/09 three year Budget. There is a specific risk in failing to achieve the identified savings to offset the spending pressure identified and SMT are monitoring this aspect prior to reporting back to members. Clear strategy for linking resources to corporate priorities is to be developed. The work of the Capital Projects Group and Corporate Programme Boards will support the improvements to financial and performance improvements regarding the capital programme. | Director of Corporate Services 11/3/08 |
| 5 | Carlisle Northern Development Route | 4 | 2 | 8 | = | The County Council selected a preferred bidder, Connect CNDR (a brand name for Balfour Beatty), on the 22 November. Final negotiations are expected to be completed by end March 2008 with a view to awarding the contract in early June 2008. Construction, which is expected to take 2 years would commence in September 2008. In addition to the construction of the CNDR the 30 year concession includes the management and maintenance of:- A7 (Junction 44 to Scottish Border) A689 (Junction 44 to Brampton Bypass) A595 from Newby West, south A6071 (Brampton Bypass to Scottish Border. The completion of the CNDR would reduce pollution on Scotland Road to below the threshold level. | Director of Community Services 11/03/08 No change |
| 6 | Financial Management Information provided must be accurate, robust & timely to enable Budget Holders to manage, failure leading to:- - poor management decisions - loss of credibility in information provided -Service Heads fail to focus on key objectives - Not linked to performance management - failure to adopt best practice and achieve value for money - specific risks identified associated with Contractor Plus system | 3 | 2 | 6 | = | The Council’s Financial Management arrangements have been assessed as adequate in the Audit Commission’s Use of Resources judgement, and also by the independent review of financial management conducted by IPF. Action has been taken on all areas of improvements required. The updated Use of Resources judgement in 2007 maintained the assessment at adequate. An action plan is being developed to tackle the areas which need improving to raise the score. Work is ongoing with the Policy and Performance and Finance Teams to further improve linkages between use of resources and performance, and this is set out in the Direction of Travel Action Plan. All of the posts in the new financial services structure approved by the Executive at the end of September last year have now been appointed to. This will increase capacity in the service and deliver further improvements. A specific risk remains to the Council from the existing system utilised by the Community Services Directorate for ex DSO work and the ability to easily reconcile the system to the Councils core financial management system. A budget has been allocated and work is progressing to replace the Community Services system. A significant financial training programme has now been launched to improve the financial management standards throughout the authority. | Director of Corporate Services 11/3/08 |
| 7 | Failure to focus clear Corporate Priorities leading to:- - resources wasted on lesser priorities - key objectives not achieved | 3 | 2 | 6 | = | New Corporate Priorities now determined :- Greener , Cleaner and Safer The Learning City Carlisle Renaissance Further work is in place to ensure that these are the drivers for focussing activity and expenditure. Refresh of Corporate Plan scheduled for April 2008. | Town Clerk & Chief Executive 11/03/08 |
| 8 | Protection of IT E-records and data and hard copy information:- - failure will have business/financial impact - inability to meet legal/other obligation - impact on resources / cost of re-establishment | 3 | 2 | 6 | = | As part of the IT Unit’s contribution to the Council’s BCM programme, the scale and profile of the ICT Disaster Recovery arrangements will be tailored to fit the corporate need. As part of the Business Continuity planning arrangements, the issue of hard copy storage and recovery will be considered. | Director of Corporate Services 11/03/08 |
| 9 | Failure to implement an effective IT Strategy:- - failure to maximise benefits of e-business and e-procurement - increased security risks | 3 | 2 | 6 | = | The Information Systems Group (ISG) is currently working upon revised strategy for 2008/2011 which will be considered by Corporate Resources Overview and Scrutiny Committee in due course. A new security policy is in development to deal with increased security risks. | Director of Corporate Services 11/03/08 |
| 10 | Performance Management challenges Failure to embed performance management in the culture of the Council at all levels - inefficient and ineffective management - misdirected/wasted resources - failure to meet target/continuous improvement | 3 | 2 | 6 | = | Quarterly Performance conferences now commenced to monitor and address performance corporately Performance Management included in Directorate’s Service Plans Performance Management Framework was published March 2007. New Performance Management IT system will go live by April 2008. | Deputy Chief Executive 12/03/08 |
| 11 | Health & Safety management and systems failure could lead to:- - exposure to legal action - financial impact of failing to ensure recovery of all - reputational impact on Council - increased exposure of staff to H&S risks - creation of image of non-proactive employer - lack of understanding of Health and Safety Manager’s role | 3 | 2 | 6 | = | Council’ Health and Safety Policy fully adopted Qualified H&S Manager employed in a corporate role Clear H&S management systems installed across the Council Health and Safety action plan regularly updated and ongoing auditing of current practices Developing local Performance Indicators which will be reported on in the Council’s performance management reports to Corporate Resources Overview & Scrutiny Committee Continuing training of staff as appropriate including mandatory training for newly appointed employees Role of Health and safety to be included in Service plans H&S strategy under development. | Deputy Chief Executive 12/03/08 – no change |
| 12 | Financial Reporting following comments of audit Commission on standard of financial reporting- Failure will lead -reputational damage -have an impact on overall CPA assessment -poor relationship with District Audit | 3 | 2 | 6 | = | The Audit Commission judged the Council’s financial reporting standard for 2006/07 as part of the Use of Resources judgement to be inadequate, albeit improvements were recognised. The 2007/08 Accounts will be submitted to Council on 26th June following consideration by the Audit Committee and Executive on 23rd June. The area of greatest risk for improving the financial reporting standards is in the increasing complexity of the accounts under the move to International Financial Reporting Standards, which increases the risk of error in the accounts. | Director of Corporate Services 11/03/08 |
| 13 | Partnerships (including framework agreement & collaborative working arrangements) Existing partnerships and New and proposed partnerships , failure to ensure compliance with existing arrangements leading to:- - failure to meet stated objectives - reputational and financial impact - onerous terms and conditions, and inadequate exit strategy - increased exposure to risk - major review of compliance with partnership agreements or evidence of agreements not undertaken on a regular or structured basis | 3 | 2 | 6 | = | The revised draft Partnership policy has been considered by the Executive and Corporate Resources Overview and Scrutiny Committee and will be submitted for approval to the next Council meeting. The Use of Resources judgement has highlighted that the Council needs to improve its financial performance of partnerships including a link to outputs and ensure the results are shared with partners and acted upon. It has also highlighted that appropriate governance arrangements should be in place for all significant partnerships. The new policy sets out responsibilities in this respect. Corporate Services Efficiency and Procurement team is responsible for the monitoring arrangements, this includes the update of the central register, completion of annual reviews of all significant partnerships, annual reports to members and quarterly progress reports to SMT. One to one assistance is given to officers when setting up new partnerships. Senior Management Team will ensure that their individual risks from partnership working arrangements should be included in Operational Risk Registers. | Director of Corporate Services 11/03/08 |
| 14 | Failure to implement Code of Corporate Governance failure to meet legal duty failure to adopt sound, consistent, transparent and auditable processes | 4 | 1 | 4 | = | The Code of Corporate Governance Action Plan is updated and reported to the Audit Committee quarterly. The Code itself has recently been fundamentally altered and guidance has now been received from CIPFA / SOLACE on the new arrangements. This has required a fundamental review of our current arrangements and this will be implemented in time for the 2007/8 accounts, and will be submitted for consideration by the Audit Committee on 23rd June. | Director Corporate Services 11/03/08 |
| 15 | Flooding | 3 | 2 | 6 | = | The flood defence project on the Eden is now substantially completed and will provide increased protection for properties in the Warwick Road area from river flooding. The flood defence project for the river Caldew has achieved all the approvals and is scheduled to commence on site in March 2008. United Utilities start work in March 2008 on major sewerage improvements in the Warwick Road and Willowholme areas. The "Making Space for Water Group" meet on a regular basis and flood response arrangements are reviewed regularly to provide an integrated response to incidents. | Director of Community Services 19/12/07 |
|  | Vacancy Management |  |  |  |  | Risks associated with this activity will be considered and included in next update of this Risk Register |  |
|  | Efficiency Savings |  |  |  |  | Risks associated with this activity will be considered and included in next update of this Risk Register |  |

# Risks to be removed

| Ref | Risk Description | Impact | Likeli-hood | Risk Score | Move-ment | Current Action Status/Control Strategy | Responsible Officer & date last updated |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Failure to have robust Business Continuity Planning arrangements - severe impact on business/provision of services - financial impact - reputational impact - legal liability These may include the risk of Flu Pandemic leading to:- inability to maintain services due to impact on staff and suppliers failure to contribute to emergency response due to extent of above | 3 | 1 | 3 | ↓ | Marsh Limited have facilitated the development of a new Business Continuity Plan. Initial testing has been carried out and training delivered to managers and staff with identified roles in the Corporate Business Continuity Management Plan. The Plan and Strategy are being presented to Corporate Resources Overview and Scrutiny Committee on 3rd April 2008. | Deputy Chief Executive 12/03/08 |
|  | Potential loss of VAT reclaimed Potential loss of VAT Partial Exemption Status resulting in the potential for a significant amount of VAT to become irrecoverable and a potential cost to the Council of approx £200k. If the VAT the Council reclaims from Revenues & Customs (HMRC) on its exempt activities (mainly Industrial Estates, Miscellaneous Properties and Crematorium) exceeds 5% of the total amount of VAT recovered, then the whole amount of the VAT on the exempt activities can no longer be recovered. | 2 | 1 | 2 | ↓ | Following a full consideration of the options and issues, the Executive, on 30th July, decided to charge VAT on its commercial rents. This took effect from 1st September 2007. A transitional hardship relief scheme has been introduced for non VAT registered businesses who can prove hardship. It is currently envisaged that the 5% limit will not be breached for 2007/8. However, this is dependent on the total amount of input tax for 2007/8 reaching the predicted £2.9m. Recent notification from HMRC has advised that the calculation for 2007/08 has been suspended due to a number of authorities experiencing difficulties in remaining within the limit. It is not yet known what the longer term implications of this suspension will be however as far as the Council is concerned this risk has been negated and so the recommendation is to remove it from the risk register, albeit the monitoring will continue on a monthly basis. | Director of Corporate Services 11/3/08 |

Appendix 2 - Corporate Risk Register 14th March 2008

# Quality Control Document (changes since December 2007)

For consideration by Corporate Overview and Resources Committee 3rd April 2008

| REF NO | BRIEF DESCRIPTION | SCORE | COMMENTS |
| --- | --- | --- | --- |
| 1 | Pay and Workforce Strategy | 12 | Control strategy/action status updated |
| 2 | Shared Services | 9 | Control strategy/action status updated |
| 3 | Carlisle Renaissance | 8 | Control strategy/action status updated |
| 4 | Medium term financial planning | 8 | Control strategy/action status updated |
| 5 | Carlisle Northern Development Route | 8 | No change |
| 6 | Financial Management Information | 6 | Control strategy/action status updated |
| 7 | Corporate Priorities | 6 | Control strategy/action status updated |
| 8 | Protecting IT records | 6 | Control strategy/action status updated |
| 9 | Implement Effective IT Strategy | 6 | Control strategy/action status updated |
| 10 | Performance Management | 6 | Control strategy/action status updated |
| 11 | Health and Safety | 6 | No change |
| 12 | Financial Reporting | 6 | Control strategy/action status updated |
| 13 | Partnerships | 6 | Control strategy/action status updated |
| 14 | Corporate Governance | 4 | Control strategy/action status updated |
| 15 | Flooding | 6 | No change. |
|  | Vacancy management |  | New – for further consideration |
|  | Efficiency savings |  | New – for further consideration |
|  | Risks for Deletion |  |  |
|  | Business Continuity Plan | 3 | Impact and likelihood reduced. BCM plan and strategy developed. |
|  | Potential loss of VAT reclaimed | 2 | Likelihood reduced. Delete from Corporate Risk Register. Monitor within Corporate Services. |