OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 4 October 2007 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.84/07 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 August 2007 to 30 November 2007, 1 September 2007 to 31 December 2007 and 1 October 2007 to 31 January 2008.

Recommendations:	To note the modifications, deferrals and departures from the previous Forward Plans.

| Contact Officer: | Rachel Rooney | Ext: | 7039 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

2.1	Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the periods  1 August 2007 to 30 November 2007, 1 September 2007 to 31 December 2007 and 1 October 2007 to 31 January 2008 are outlined in Appendix A of this report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the previous Forward Plans be noted.

Contact Officer:		Rachel Rooney						Ext: 7039

1st August 2007 to 30 November 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |

| KD.017/07 | Air Quality Action Plan Community O&S | The matter was included in the Forward Plan to be considered by the Executive on 28 August 2007 but has been deferred until 22 October 2007. | Director of Community Services |
| --- | --- | --- | --- |
|  | Reason: CThe Consultants report will not be completed until early/mid September and as this is required to complete the action plan this has caused a minor but not critical slippage. |
| KD.014/07 | Section 106 Agreements in relation to Public Open Space and Play Areas | The item was not included in the Forward Plan. It was considered by the Executive on 28 August 2007 under General Exception rules. | Director of Community Services |
|  | Infrastructure O&S |  |  |
|  | Reason: Executive at its meeting on 30 July 2007 requested a further report to the August meeting, this was after the publication of the August Forward Plan. |
| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
|  | Castle Street Public Realm Improvements | The item was not included in the Forward Plan. It was considered by the Executive on 28 August 2007 under General Exception rules. | Director of Carlisle Renaissance |
|  | Infrastructure O&S |  |  |
|  | Reason: Council referred the matter back to Executive and the matter would then go back to Council on 11 September. The tight timescale meant the item was not included in the Forward Plan |
|  | NWDA Detailed Funding Application | The item was not included in the Forward Plan. It was considered by the Executive on 28 August 2007 under General Exception rules. | Director of Carlisle Renaissance |
|  | Reason: Notification of pre-approval funding and the associated funding agreement for this aspect of the Concept Proposal was received after the publication of the Forward Plan |

1 September 2007 to 31 December 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.056/07 KD.058/07 | Consultation Draft Economic Strategy for Carlisle North West Development Agency Funding | These items have been added to the existing Forward Plan item for Carlisle Renaissance (KD.68/06). |  |
|  | Reason: To ensure all Carlisle Renaissance items are kept together in a central place for monitoring purposes |
|  | Joint Municipal Waste Management Strategy | The item was not included in the Forward Plan. It was considered by the Executive on 24 September 2007 under General Exception rules. | Director of Community Services |
|  | Infrastructure O&S |  |  |
|  | Reason: recently been agreed through the Cumbria Strategic Partnership and being brought to Executive to provide an opportunity to comment on the preliminary draft prior to consultation. |
| KD.055/07 | Performance Management System | The matter was included in the Forward Plan to be considered by the Executive on 24 September 2007 but is no longer a key decision. | Head of Policy and Performance Services |
|  | Corporate Resources O&S |  |  |
|  | Reason: Further investigation was required into the options available prior to asking for release of capital monies. The amount is less than £60,000 so does not need to go into the Forward Plan. |
| KD.059/07 | Electronic Documents Record Management System (EDRMS) | The matter was included in the Forward Plan to be considered by the Executive on 24 September 2007 but has been deferred until a future meeting. | Head of Policy and Performance Services |
|  | Corporate Resources O&S |  |  |
|  | Reason: A more detailed business case will be developed prior to requesting release of capital funding. It will go into a Forward Plan at a future date when a business case is developed. |
| KD.052/07 | Statutory/Temporary Allotments | The matter was included in the Forward Plan to be considered by the Executive on 24 September 2007 but has been deferred. | Director of Community Services |
|  | Community O&S |  |  |
|  | Reason: Deferred pending the resolution of outstanding issues. |
|  | Council Tax Income from Second Homes | The item was not included in the Forward Plan. It was considered by the Executive on 24 September 2007 under General Exception rules. | Director of Community Services |
|  | Reason: A further report on the Council Tax Income from Second Homes was requested at the meeting of the Executive on 28 August. This was not in enough time to include the item in the Forward Plan. |
|  | Belah Community Centre | The item was not included in the Forward Plan. It was considered by the Executive on 24 September 2007 under General Exception rules. | Director of Community Services |
|  | Reason: Confirmation of part funding had only recently been received. The report was brought to Executive to enable preparation of the project to commence in details. |
|  | Concept Bid to North West Development Agency | The item was not included in the Forward Plan. It was considered by the Executive on 24 September 2007 under General Exception rules | Director of Development Services and Director of Carlisle Renaissance |
|  | Reason: The NWDA had only recently offered the prospect of funding for the current financial year for the issue of site assembly in Carlisle Renaissance transformational areas. As the funding may be available for the current financial year, it needed to be considered by Executive as quickly as possible. |

1 October 2007 to 31 January 2008

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.068/07 | Carlisle Renaissance: North West Development Agency Funding Bid | The matter was included in the Forward Plan to be considered by a Special Executive on 8 October 2007 but has been deferred. | Director of Carlisle Renaissance |
|  | Reason: The detailed application is not ready to be taken to Executive. |