###### EXCERPT FROM THE MINUTES OF THE

EXECUTIVE

###### HELD ON 30 AUGUST 2005

EX.167/05	CARLISLE RENAISSANCE IMPLEMENTATION TEAM

(Non Key Decision)

(In accordance with Rule 15(i) of the Overview and Scrutiny Procedure Rules, the Mayor agreed that the call-in procedures should not be applied to this decision.)

Portfolio	Promoting Carlisle

Subject Matter

The Head of Economic and Community Development submitted Report ECD.12/05 setting out the costs of the Carlisle Renaissance Implementation Team, the implications for the City Council and the contributions secured and still to be sought from Partner Agencies.

The ideas emerging from the initial work on Carlisle Renaissance are based on an analysis of the strengths, weaknesses, opportunities and threats facing Carlisle.  The proposed team is being set up to reflect the key work areas identified as a response to this analysis.  A proposed structure was attached to the report for a team based on three year fixed term appointments.

An individual to oversee, manage and give leadership to the programme is clearly required, with appropriate administrative, communication and project management support. The details of the team are still being developed and negotiated with partner agencies who may be able to provide specialist technical advice.

An interim team was now being established to maintain the current pace of activity, in particular:

- 	the momentum with Government needs to be kept up;

- 	a large scale programme of public consultation and involvement is now starting on the Prospectus;

- 	detailed consultation will be required on the strategies and proposals as they develop;

- 	sources of external funding need to be explored and negotiated;

- 	conditions need to be established to attract private sector investment.

The City Council would need to progress, as a priority, the Asset Management and Local Planning frameworks to set the context for Renaissance.  It must also establish appropriate governance arrangements with the County Council and with key local stakeholders.  Without all these factors being in place, there is a risk that Carlisle Renaissance will not succeed and the opportunity to make Carlisle a key driver of the local and sub regional economy and enable more sustainable local communities will be lost.

Although there is a degree of risk in embarking on the process, in terms of work that may not lead to a proposal and upfront costs to create the conditions for investment, the likely benefits far outweigh these initial risks.  The greater risk is that the opportunities are not explored and seized.

On 1 August 2005, the Executive agreed to continue with David Taylor Partnerships (DTP) co-ordinating the developing programme, in the role of Interim Director.

At the Task Group meeting on 27 July 2005, further clarification was sought from partner agencies on the details of their initial commitments to the Team.

The proposals to date are as follows:

- Carlisle City Council

The City Council will cover the cost of extending the contract for David Taylor Partnerships (DTP) to act as Interim Director until the end of December 2005;

It was recommended that the City Council also considers providing the resources to support the following posts at an annual cost of £250,000 with £40,000 required before the end of March 2006:-

The Programme Director;

Communications and Marketing;

Administrative Support;

Project Management;

Learning City Manager;

Urban Designer;

- English Partnerships

They have agreed to cover the Development Manager role using one of their vacant posts, with recruitment starting shortly.  Depending on the response, the salary and job description may need to be reviewed and additional funding may be required, some falling in this financial year.

- Government Office North West (GONW)

GONW has offered part time support, most likely in the form of consultancy advice, for strategic planning advice.

- Cumbria County Council

The County Council has agreed to support work on a Movement Strategy.  The detail of the work and the necessary resources are subject to a formal decision, yet to be made, by the County Council.

- Other Support

Other support from Partner agencies is the subject of discussion and negotiation, including:

(a)  Cumbria Vision has the responsibility for overseeing and driving an Economic Strategy for Cumbria and their Chief Executive is keen to pursue an Economic Strategy specifically for Carlisle.  Cumbria Vision and NWDA will make a proposal in due course as to how this might be resourced.

(b) The Economic Renewal Action Plan bid to NWDA included a Programme Manager post.  It is hoped, in negotiation with NWDA, to broaden this post out to support the Sustainable Communities element of the Carlisle Renaissance work.

(c) Further discussions are needed with Cumbria Tourist Board, English Heritage and other agencies involved in promotion of tourism and the historic environment on how the tourism marketing, promotional and product development elements of Carlisle Renaissance and the high quality historic core can be enhanced. English Heritage has also offered, in principle, part funding for a Historic Environment Project Manager.  Match funding would be required to make this into a full time post.

- Operational Costs

Operational as well as staffing costs have been estimated.  There is a considerable amount of start up work to be done before the end of the current financial year.  From then on, there will be an ongoing need over the three years for professional and technical advice, marketing, communication and consultation.

- Development Framework

The most urgent requirement is for a Development Framework or Masterplan to be produced for the urban core.  With the Carlisle Local Plan Inquiry scheduled for February 2006, work must be done well in advance to set out in more detail the aspirations for new development in the urban area.  The Council must have in place a cogent argument for Carlisle Renaissance and some proposals for key development sites to enable decisions to be taken in the context of a Local Plan that represents accurately the vision for Carlisle.

The Framework would, therefore, set the context for the growth and development of the City Centre and particularly the transformational projects.  It would be developed very closely alongside and be linked with the Movement Strategy.  It would set out potential public realm and environmental improvements.  Expert professional and technical advice would be sought as part of the process.  The Council does not have enough capacity or all of the required skills to produce the Development Framework in the necessary timescale.  It is estimated that externally commissioned work would cost in the region of £120,000 and it is recommended that the Council contributes to one third of the cost, seeking support from other agencies for the rest.

- Other operational costs

Other costs in this first year to March 2006 include recruitment and setting up costs for the Implementation Team, consultation and communication and general administrative costs.  These costs could be up to £40,000.  The costs likely to continue into the following three years include further professional and technical advice, consultation, marketing and general administration and are estimated in the order of £80,000 a year.

Total costs for the Implementation Team required to the end of March 2006 are estimated at £200,000.  From April 2006 until the end of March 2009, costs are estimated at £340,000 per year.  This includes the production of a Development Framework but excludes the costs, financial and in kind, already offered by Partner Agencies.  The Executive is therefore recommended to agree to a contribution of £340,000 per year from 1 April 2006 to end March 2009, with up to a further £80,000 being committed before the end of March 2006.  This £80,000 can be covered by the amount already set aside for Carlisle Renaissance.

These costs do not include the building and site development of the Transformational Projects or other sites.  Each site will subject to detailed analysis and options appraisal.  The Council will be asked to consider its role at the appropriate time, depending on which of its land holdings may be used, the use of land in other ownership and the amount of private investment secured.

The Carlisle Renaissance Prospectus had been launched on Friday 26 August 2005 when the Deputy Prime Minister had paid a visit to Carlisle.  Members of the Executive wished to thank Officers for the excellent organisation of the launch of the Prospectus and for the visit of the Deputy Prime Minister.  The Interim Implementation Team Programme Director was present at the meeting and was welcomed by the Executive.

The Leader reported that, since the launch of the Carlisle Renaissance Prospectus, there had been enthusiasm across the City for the initiative, which was a once in a lifetime opportunity to improve Carlisle.  He considered it important for the City Council to take a lead role and for the implementation team to begin their work as soon as possible.

Summary of options rejected

None

DECISION

That the Executive recommends the City Council to grant a supplementary estimate of £1,020,000 to cover the period to 31 March 2009 towards the cost of the Carlisle Renaissance Implementation Team.

Reasons for Decision

To enable the City Council, in partnership, to maintain the momentum of the Carlisle Renaissance work and achieve the delivery of the Renaissance vision.