AUDIT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 12th June 2006 |
| Title: | STATEMENT OF ACCOUNTS 2004/05 and 2005/06 – PROGRESS AND ACTION PLAN |
| Report of: | Director of Corporate Services |
| Report reference: | FS17/06 |

Summary:

This report provides Members with further information on the issues raised by the Audit Commission and provides an update on progress with the 2004/05 Statement of Accounts, and the Action Plan approved by the Accounts Committee on 7th March and full Council on 27th April.

The revised final Statement of Accounts for 2004/05 is elsewhere on the agenda for consideration and recommendation for approval to the Council meeting on 29th June.

An update on the progress on the 2005/06 Statement of Accounts is also provided.

Recommendations:

Members are asked to:

- Note and comment on progress on the Action Plan.

- Note the potential issues remaining on the 2004/05 accounts which subject to clarification and member agreement will be adjusted in the 2005/06 Accounts where necessary.

- Note the progress on the 2005/06 Statement of Accounts.

| Contact Officer: | Angela Brown | Ext: | 7299 |
| --- | --- | --- | --- |

Note: in compliance with section 100d of the Local Government (Access to Information) Act 1985 the report has been prepared in part from the following papers: Audit Commission reports – SAS610 2004/05 May 2006, Annual Audit and Inspection Letter March 2006. Revised Statement of Accounts 2004/05.

CITY OF CARLISLE

To:	Audit Committee							FS17/06

12th June 2006

STATEMENT OF ACCOUNTS 2004/05 and 2005/06

– PROGRESS AND ACTION PLAN

- INTRODUCTION

  - The purpose of this report is to update members of the Audit Committee on the progress being made on the Statement of Accounts Action Plan to enable them to monitor and propose further action where appropriate. The Action Plan was approved by the Accounts Committee on 7th March, and by full Council on 27th April. The Action Plan is a key document for the Senior Management Team to monitor at their weekly meetings and this has been happening since it was approved in March. It is also a document that the Portfolio Holder for Finance and Resources will use on a regular basis with the Head of Financial Services. The updated Action Plan is attached at Appendix A.

  - This Plan is a significant part of the Council’s response to the S11 recommendation of the Audit Commission and the update has been drawn up in collaboration with the Audit Commission and reflects their views as to how the Council needs to address the concerns they have raised.

  - The shorter-term actions set out in the Action Plan address the immediate concerns raised by the Audit Commission but it is acknowledged that there are longer-term improvements that will also need to be addressed. This will be in the Improvement Plan that will be presented to the Audit Committee in due course. This Plan will be drawn together following the recommendations of the formal review being undertaken by IPF and which will report in late June.

  - In addition to the Action Plan, this report addresses the issues raised by the report of the Audit Commission, ‘Report on the 2004/05 Financial Statements to the Accounts Committee – June 2006 Update’ which is considered elsewhere on the agenda. The full amended Statement of Accounts for 2004/05 incorporating the adjustments required are attached in full elsewhere on the agenda for Members consideration prior to formal recommendation to Council on 29th June.

  - Finally the report provides an update on progress of the 2005/06 Statement of Accounts. A further meeting of the Audit Committee has been arranged for 21st June to consider the 2005/06 Statements, which will also need to be formally approved by Council on 29th June in order to meet the statutory deadline for the approval of the Accounts.

- PROGRESS AGAINST ACTION PLAN

2.1	The Action Plan draws together recommendations made by the Audit Commission to improve the Council’s final accounts process and was approved by the Accounts Committee at their meeting on 7th March and by full Council at the special meeting held on 27th April. The updated Action Plan is attached in full at Appendix A.

  - The purpose of the Action Plan is to advise both Members and the Senior Management Team of progress being made against the improvements identified, and is an important part of the Council’s response to the Audit Commission’s S11 recommendation considered by full Council on 27th April. The action plan is monitored weekly by the Senior Management Team. Specific issues to draw to Members attention from the Action plan (with the relevant reference from the Action Plan in brackets) are given in the paragraphs below.

  - Draft Unadjusted misstatements (Item 1) – the non-material misstatements identified in the original Audit Commission report on 15th February were adjusted and re-submitted to the Auditors on 27th February. Further queries were received on 27th March and a final set of adjusted statements was agreed with the Audit Commission and submitted on 13th April. Subsequently, the Audit Commission reported on 19th May that there are potentially some further non-material adjustments required (as set out in their report elsewhere on the agenda and detailed in paragraph 3.3 below). It is intended that these will be clarified at a meeting with the Audit Commission in early June and the adjustments reflected in the 2005/06 Statements where appropriate.

  - Draft Adjusted material misstatements  (item 2) – the material misstatements have now been adjusted and accepted by the Audit Commission to the same timescale as set out in 2.3 above. There are no material adjustments outstanding.

  - Flooding (Item 3) – The issues relating to the accounting treatment of the 2004/05 flood expenditure have largely been resolved. However the scale of the insurance flood claim which was settled with the insurers earlier this month at a value of c. £6.6m, means that there is significant work to achieve accurate accounting for the claim and this remains a high risk area for the 2005/06 accounts.

  - Cashflow Statement (Item 4) – Discussions have taken place with our financial information system supplier, to produce system reports, to assist in the production of the Cash Flow Statement.

  - Fixed Asset Valuations (Item 5) – Property Services have undertaken a full revaluation of the whole asset portfolio as at 31st March 2006 Asset classifications have been reviewed and asset lives updated. The fixed asset database is also being developed which will facilitate the production of year-end capital accounting requirements for the balance sheet. An interim Accountant has been appointed to lead on fixed asset work and to liaise with Property Services regarding valuations, agree a revised valuation programme and to ensure that all capital accounting requirements are met. This exercise will also provide the appropriate split between land and buildings, which is necessary to ensure that depreciation is calculated correctly on the assets. A property database is also under development that will be used in future to monitor movements on assets during the course of the year and can be used to calculate the annual depreciation charge.

  - Bank Reconciliation (Item 6) – Work on resolving the systems problems continues to be given the highest priority and substantial additional support has been provided from the system supplier to attempt to resolve the problems. This continues to be given high priority. Progress to date is as follows:

- For 2004/05, additional Audit Commission testing was carried out and this work along with the Council’s bank reconciliation processes have been reviewed by the Audit Commission’s technical support unit. Although no formal feedback has been received, the Audit Commission report proposes an unqualified opinion, which suggests that the additional evidence provided gives the Audit Commission the assurance for 2004/05 they were seeking.

- For 2005/06, the reconciliation to the end of December 2005 is currently balanced as previously reported and was submitted to the Audit Commission in February. The reconciliation to March 2006 is currently not balanced by c. £120 and work is continuing to balance this fully as a matter of priority. The 2005/06 reconciliation has been produced using the same database as that used for 2004/05 and so potentially similar audit issues will arise if the system cannot be balanced and reformatted fully in time for the 2005/06 Audit.

- The 2006/07 reconciliation is now balanced and signed off by a senior finance officer on a daily basis following the ‘restarting’ of the system by the supplier on a clean database. There are however still system problems remaining and the reconciliation is achieved partly on a manual basis. This is being pursued with the supplier to finally resolve the system problems.

We are continuing discussions with the Audit Commission on the work carried out to date and the format of the information presented on the 2005/06 and 2006/07 bank reconciliation to enable them to give an early view on progress.

  - Quality of Supporting Working Papers (Item 7) – Work is continuing to ensure the quality improves for 2005/06 Statements, and the papers will be subject to independent internal review prior to being submitted.  Additional training will be provided to assist with the improvement of the standard of working papers and supporting evidence across the Council.  This training will become an integral part of the Corporate Training programme that is currently being developed in conjunction with the Head of Personnel and Development Services.  An initial training session in Treasury Management has been arranged for 29 June for key staff and members of the Strategic Financial Planning Group.

  - Priority given to preparing the financial statements by senior management (Item 8) – Both the Action Plan and progress against closure of the Final Accounts for 2005/06 are monitored weekly by the Senior Management Team, and action is taken as appropriate.

  - Late closure for four successive years (Item 9) - The reasons for the late sign off of the accounts were detailed in the previous report (FS48/05). Members will be aware that the timetable for the closure of the 2005/06 accounts is again one month earlier than the previous year (approval by 30th June 2006, with the Audit to be completed by 30th September). This earlier deadline, added to the impact of the delay in completing the 2004/05 accounts, the recently agreed flood insurance claim, the problems with the bank reconciliation system, and the ongoing impact of loss of financial records in the flood, mean that the timescale for completing the 2005/06 accounts is extremely challenging.

  - Resources allocated to Financial Reporting (Item 10) – The Financial Services Unit has been restructured as part of the management restructure approved earlier in the year.  The new Head of Financial Services (Shelagh McGregor) is responsible for the service delivery and performance management of the finance function with the Director of Corporate Services retaining the strategic direction and S151 statutory responsibility as Chief Finance Officer.  Reporting to the Head of Financial Services, the Chief Accountant (Alison Taylor) has responsibility for all of the Accounting and Budgeting functions.  Within this new structure, roles and responsibilities are continuing to be refined and work is being concentrated on priorities to ensure delivery of the Council’s objectives. Additional resources have been allocated to the process, both by overtime working, re-direction of internal resources, and by the recruitment of an additional temporary accountant. The financial information system supplier is also allocating resources to assist in resolving the bank reconciliation system problems. In addition to the above, an independent review by IPF (the commercial arm of CIPFA) has been commissioned of the Council’s financial management arrangements. Their final report is expected in late June 2006, and their recommendations will form part of an ongoing improvement plan.

  - Remaining Action Plan Items (Items 11 to 25) – Action on these are detailed in Appendix A.

  - Any actions remaining from the current action plan will be incorporated into the longer term Improvement Plan, which will be prepared following the report of the IPF.

- 2004/05 STATEMENT OF ACCOUNTS - PROGRESS

3.1	The Audit Commission updated report on the 2004/05 Financial Statements is considered elsewhere on the agenda. Members will note that the report contains a proposed unqualified audit opinion (an unqualified opinion in effect means that the Accounts present fairly the financial position of the authority for that year).

  - The Audit Commission report highlights a number of areas of further potential non-trifling errors and uncertainties in the 2004/05 accounts. The Audit Commission have stated that non of these are material and do not require adjustment for the purpose of giving an opinion on the 2004/05 Accounts, however they will require them to be adjusted urgently to prevent them leading to cumulative errors in the 2005/06 Accounts.

  - The remaining potential uncertainties have not yet been quantified and discussions are ongoing with the Audit Commission to clarify the uncertainties remaining. A further meeting has been arranged for early June to discuss each issue in detail. Members should note however that the 2005/06 Accounts need to be issued by 13th June for reporting to the Audit Committee on 21st June, and full Council on 29th June in order to meet the statutory deadline for the approval of the Accounts. This in effect means that any outstanding uncertainties that are not resolved at the meeting with the Audit Commission are unlikely to be able to be dealt with in the 2005/06 accounts. An update on progress will be given to Members at their meeting on 12th June. For Members’ information, further details on each remaining uncertainty are given below.

- Leases – this issue is contained and therefore monitored as part of the 2004/05 Statement of Accounts Action Plan attached at Appendix A (item 24). It relates to whether refuse vehicles acquired in 2003/04 are deemed to be contract hire/operational leases or finance leases (and therefore accounted for either on or off the balance sheet) which should be determined in accordance with SSAP21. Following the Auditors initial query the Council obtained specialist advice from Sector, our Treasury advisors, to provide further assurance on our approach and accounting assumptions with regard to the leasing agreement. This information has been supplied to the Audit Commission. The information provided included an estimate of the capital value, the present value (PV) discount rate implicit in the original leasing agreement, and the present value percentage (which in the case of an operating lease should be less than 90%). The average PV % for the whole agreement is less than 90% albeit some of the individual vehicles exceed this limit, however it is considered that the average  % calculation is sufficient to confirm the Council’s approach to the treatment of the assets as operating leases. However the PV % is only one element of the operating/finance lease assessment, other issues relate to residual values and whether all risks and rewards of ownership are with the lessee or lessor. Sector have concluded that as the lessor is waiting 6 years to recover their residual investment, this represents significant risk and therefore the leases should be classed as operating leases. A note setting out the Council’s position was issued to the Audit Commission in February 2006 and at this stage it is not known what further information is required to provide the further assurance.

- Depreciation – the original Audit Commission report issued to Members in February included a non-trifling but not material adjustment of £306,079 relating to overstatement of depreciation in the accounts. Members agreed to reflect this in the 2004/05 Statements and this has been done. The final figure, as agreed with the Audit Commission, was £238,157. The new Audit Commission report includes a further depreciation adjustment potentially required to the accounts. This has arisen from the Audit Commission sample taken to date, which suggests that further adjustments will be required. The resolution of this item will form part of the work undertaken as part of Action No. 5 in the Action Plan.

- Assets held by Carlisle Leisure Ltd (CLL) – this issue is contained and therefore monitored as part of the 2004/05 Statement of Accounts Action Plan attached as Appendix A (item 21). The CLL contract has been reviewed and it has been established that the property assets are correctly accounted for in the Council’s balance sheet. The Council still holds the freehold to the property, which are leased to CLL at a peppercorn rent. The assets are subject to regular revaluation by Property Services on a depreciated replacement cost basis and this is the basis that the assets are held in the balance sheet. However operational items of plant and equipment have been transferred to CLL and therefore need to be written out of the Council’s balance sheet. There are other items of plant and equipment leased by the Council but utilised by CLL. These are operational leases and as such are not shown in the balance sheet. In several instances it has not been possible to assign the leases to CLL so the Council will continue to pay the annual lease charge and recharge the cost to CLL. These costs and reimbursements are shown within the revenue account. The relevant adjustments will be reflected in the 2005/06 balance sheet as previously agreed in the Action Plan.

- Flood damaged equipment – A full review of all fixed assets in the balance sheet is being undertaken in conjunction with the work being carried out on CLL assets, asset valuation work and depreciation charges. Details of any assets damaged/destroyed by the flood have previously been supplied to the Audit Commission, the details of which were included in the Audit files provided at the commencement of the 2004/05 audit. The balance sheet value of assets lost in the flood is £10,308, which will be written out of the balance sheet in 2005/06. A further amendment may be required for 12 litterbins lost in the flood, however this amendment is still to be quantified but is expected to be minimal.

- Sheepmount assets – Further details have been requested from the Audit Commission in respect of this issue as their report suggests that this is a query on a note to the balance sheet as opposed to the balance sheet value itself. The development work carried out to the Sheepmount during 2004/05 is correctly classified as an Asset under Construction based upon actual costs incurred in the year. No impairment was carried out in relation to flood damage as this was covered by the Contractors Insurance. The balance sheet also includes an operational asset valued at £150,000 which relates to a parcel of land at the Sheepmount not being developed.  Property services have fully reviewed the valuations for the entire portfolio for the 2005/06 accounts.

- Capital/Revenue Expenditure – The Audit Commission have requested further assurance be given that expenditure is properly classified between capital and revenue and that our processes ensure that this happens systematically. This assurance will take place as part of the work on the 2005/06 accounts. The largest area of analysis relates to the classification of the flood costs which will be discussed further with the Audit Commission in June.

- Preserved Right to Buy debtor – this issue relates to a discrepancy between CHA’s 2004/05 accounts and the PRTB audit certificate supplied their auditors, KPMG. The Council has accounted for the PRTB receipt in accordance with the Audit certificate, which is required under the terms of the LSVT contract.  CHA are undertaking a reconciliation exercise to identify the discrepancy and had undertaken to advise the Council of the outcome by the end of May 2006 so that any adjustment, if required, may be reflected in the 2005/06 accounts. The discrepancy may relate to sales of other CHA assets or receipt of capital income which is outwith the PRTB agreement and therefore not due to the Council. Until the relevant information is received from CHA it is not possible to quantify whether or not an adjustment is required.

  - The full revised Statements for 2004/05 are attached elsewhere on the agenda for Members consideration prior to being formally recommended to Council for approval.

- PROGRESS ON 2005/06 ACCOUNTS

4.1	As mentioned earlier, progress on the 2005/06 Audit is monitored regularly by SMT. The Executive will consider the 2005/06 out-turn reports in 12th June with the annual Statement of Accounts being submitted to the Audit Committee on 21st June for formal approval by full Council on 29th June. Work is progressing well to meet these dates. However as previously stated the main areas of concern for the 2005/06 accounts include the following:

- Any outstanding adjustments relating to 2004/05 needs to be included in the financial system to ensure that the opening balances for 2005/06 are available. Any adjustments required in relation to the updated Audit Commission report will impact on the 2005/06 Statement of Accounts, which will need to be issued on 13th June (the day after this Audit Committee) to meet the statutory deadlines.

- Analysing the flood expenditure incurred and matching this to the final insurance settlement. This is a very time consuming task and resources have been provided to ensure that this does not delay the 2005/06 accounts.

- The 2005/06-bank reconciliation remains unbalanced by C £120. Additional support has been received from the supplier to assist in reconciling the difference.

- RECOMMENDATION

5.1	Members are asked to:

- Note and comment on progress with the Action Plan

- Note the potential issues remaining on the 2004/05 accounts which subject to clarification and member agreement will be adjusted in the 2005/06 Accounts where necessary.

- Note the progress on the 2005/06 Statement of Accounts.

ANGELA BROWN

Director of Corporate Services

| Contact Officer: | Angela Brown | Ext: | 7299 |
| --- | --- | --- | --- |

Corporate Services

Carlisle City Council

1 June 2006

STATEMENT OF ACCOUNTS – ACTION PLAN (30th May 2006)

#### Key to Audit Commission reports:

1		Report on the 2004/05 Financial Statement to the Accounts Committee (February 2006)

2.		Core Process Audit – Interim Report (July 2005)

3.		Review of Financial Statements 2003/04 (November 2004)

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 1 | Draft Unadjusted (non-trifling) misstatements (See Appendix 2 to Audit Commission Report No 1) | To request the Accounts Committee to decide as to whether the adjustments are to be made. | The non-material misstatements have been adjusted including those identified in the 2003/04 accounts as per members’ request at the Accounts Committee on 15th February 2006. The amended statements were submitted to the Audit Commission on 27th February following which further queries were received on 27th March. The revised statements following agreement with the Audit Commission were sent on 13th April 2006. Subsequently the Audit Commission reported on 19th May that there remains a number of potential uncertainties as set out in their updated report to the Audit Committee on 12th June and which are expanded on in report FS17/06. A meeting has been arranged with the Audit Commission in early June and any amendments clarified at that meeting will be included in the 2005/06 Statements, which are due to be considered by the Audit Committee on 21st June. | Low – Med | 27th February and 13th April - Complete 1st June |
| 2 | Draft Adjusted material misstatements:- (See Appendix 3 to Audit Commission Report No 1) | To make the adjustments in the 2004/05 Accounts. | The material misstatements have now been adjusted and the amended statements have been submitted to the Audit Commission to the same timescales identified above. | Low | 27th February and 13th April - Complete |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 3 | Flooding (See Report No. 1 page 6) | Flood costs to be amended to reflect the actual income due to the Authority in 2004/05 and to ensure that the accounts are prepared on an accruals basis as required by accounting standards. The amendment required is in the region of £1m. | The adjustments for 2004/05 have been made as included in 2 above. The issue is being left on the action plan as the flood work is a significant factor in the 2005/06 closedown and it will be monitored carefully to ensure the year end adjustments are accounted for correctly in 2005/06. Claim settled Flood and Insurance report to be produced for Executive on 12/06/06. | Low – 2004/05 complete High – 2005/06 | 2004/05 Complete June 2006 |
| 4 | Cashflow Statement – as set out in the Audit Commission Report No 1, adjustments of £4m have been required to the 2004/05 statement. The nature of the adjustment has been a recurring issue (see recommendation 50 of Report No 3). |  | The adjustments have been made in the 2004/05 accounts as set out in 2 above. The completion of this statement is being given increased priority for 2005/06. Discussions are taking place with Civica our financial information system supplier to produce system reports, which will reduce the considerable manual effort involved in this task. | Low High | 2004/05 Complete June 2006 |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 5 | Fixed Asset Valuations – as set out in the Audit Commission Report No 1, adjustments of £2m have been required to the 2004/05 statement. The nature of the adjustment has been a recurring issue (see recommendation 14 of Report No 3). |  | The adjustments have been made in the 2004/05 accounts. Detailed requirements incorporated to the Final Accounts Timetable. Discussions are underway to improve this area of work for the 2005/06 Accounts and in particular the maintenance of the Fixed Asset Register. A Property database is under development. A specific action plan for this area of work is being developed and led by the Head of Property Services. The Interim Accountant from IPF is leading on this aspect for 2005/06 Accounts and will work with the Principal Accountant to produce and quality check these Working Papers. | Low High | 2004/05 Complete June 2006 |
| 6 | Bank reconciliation – as set out in the Audit Commission Report No 1, para 10, No 2, para R6 & R7, and No. 3 para 26. | To complete the reconciliation on a monthly basis. Also see recommendation R6 and R7 of Report No 2. | 2004/05 - The 2004/05 reconciliation is completed and has been accepted by the Audit Commission for the purpose of signing off the Accounts. 2005/06 - The bank reconciliation to December 2005 is complete. Work has continued on the position to 31 March 2006 – the amount of £124 is currently outstanding. 2006/07 - Daily reconciliation is being carried out which is providing a balance position. This work is continuing to be given top priority within the workload of the section. Additional resources (1FTE) have been employed to focus on this. | Low High | 2004/05 Complete June 2006 |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 7 | Quality of supporting working papers – as set out in the Audit Commission Report No 1 para 12 & 13 , No. 2 para R5, R8, R14 and No. 3 page 3. Delays in receiving some information – as set out in the Audit Commission Report No 2, recommendation R14 and 16. | A senior member of the finance team, unconnected with the preparation of final accounts working papers should undertake and evidence a quality review before the information is presented for audit. This review should also be undertaken for other financial information to ensure errors such as that found in opening balances are identified and corrected. | The working papers identified during the previous year’s audit to be improved have been improved. Confirmation from the Audit Commission on the number of working papers that require improvement following the completion of the 2004/05 accounts is awaited. The temporary IPF Interim Accountant is reviewing final accounts working papers. The Head of RBS and Head of FS will also undertake a quality check of working papers. It is intended that additional training will be provided to assist with the improvement of the standard of working papers and supporting evidence across the Council. However pressure of work has meant that this has not been achieved as yet. This training will become an integral element of the Management Development Training programme which is currently being developed in conjunction with the Head of Personnel and Development Services.. A session in Treasury Management has been arranged for the 29 June 2006 for key staff and members of the Strategic Financial Planning Group. | High Med | June 2006 August 2006 |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 8 | Priority given to preparing the financial statements by senior management – as set out in Audit Commission Report No 1 para 15, 16 & 17 and No. 2 para R5 & R14. | Higher priority to final accounts work should be given. | Re-engineering of the closedown process is continuing and the time allocated to closing down the service department budgets, the carry forward requests and reporting this to Members has been reduced. This time will be used to apply the technical accounting aspects of the SORP in preparing the statutory statements. Service managers been made aware that year end timetables will be strictly adhered to – and all adjustments must be submitted on time. The 2005/06 Timetable issued on 10/03/06. The Statement of Accounts Action Plan is being monitored weekly by SMT, and will be a regular item until the improvements are delivered. | Medium | June 2006. |
| 9 | Late closure of accounts Audit Commission Report No 1 para 13, 15, 16 & 17, No. 2 R15 & R21 and 3 page 3. |  | For the 2005/06 Accounts, SMT are monitoring the progress made weekly. Members of the newly formed Audit Committee will also be updated on progress. Additional resources are in place to assist with the closure process. | High | June 2006 (approval) Sept 2006 (Audit) |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 10 | Resources allocated to financial reporting. AC Report No 1 para 17, & No 2 para R5, R14, R15, R21. |  | Additional resources have been recruited to help finance staff improve the position. In addition support from IPF has been commissioned to provide an independent inspection and assurance of the Council’s processes. Report due in June 2006. | Med | June 2006 |
| 11 | Management and update of the Financial Guide needs to be reviewed to ensure that it reflects current financial and accounting and budgetary arrangements, and the Financial Services duties and responsibilities list should be brought up to date to reflect revised/new changes brought about by the new ledger system, staff changes and team structures. AC Report No.2 R3. | Full systems documentation and procedure manuals for the new financial management system to be prepared as set out in Audit Commission Report No 2, recommendation R3. | Work on these has taken place during the year. Debtors and creditors systems are complete. Additional temp resources appointed from mid March to assist with this task. However priority is currently being given to the 2005/06 Bank Reconciliation and so the additional resources are likely to be effective only after the Bank Rec improvements have been delivered. Training on the Financial Guide will be provided as an integral part of the training programme currently being developed. | Medium | June 2006 August 2006 |
| 12 | Weakness was found with the quality of supporting documentation and review for journal entries. Reports 1 para 11-17 , No 2 R8, R14 , R16 & No. 3 page 3. | Journal authorisation, documentation and evidence of review needs to be improved. | Procedures have been reviewed and implemented April 2006. For 2005/06 the journals will be reviewed independently. | Low | April 2006 - Complete |
| 13 | System amendment controls. AC Report 2 R9. | Exception reports should be run detailing all unusual attempts to access IT systems. | Where systems permit such functionality, system administrators have been reminded of this requirement. This functionality is now a mandatory requirement for all new systems. A monitoring system will be implemented. | Medium | June 2006 |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 14 | Internal Audit recommendations concerning virements have not been implemented. AC Report 2 R11. | Internal Audit recommendations on virements to be implemented as soon as possible. | Revised procedures have been implemented April 2006. | Low | April 2006 Complete |
| 15 | Not all budget monitoring reports show gross income and expenditure they show net expenditure. AC Report 2 R12. | Budget monitoring reports to the Executive should show gross income and expenditure, as showing only the net position can mask variances. | Draft of gross figures in Best Value Accounting Code of Practice format has been circulated to FSFMT. Further work is being carried out on this and SMT, Service Heads etc will then be consulted. | Low | June 2006 |
| 16 | 2003/04 interim report recommendations relating to budgetary control have not yet been fully implemented, inc the extension of budget monitoring reports to cover all revenue and balance sheet accounts as well as forecast outturn. Report 2 R13. | Audit recommendations should be regularly reviewed to ensure that all areas are addressed. | A list of reports which are required from the Financial System is being finalised. A meeting is being arranged to agree which areas of development and which reports the supplier can help with. The evidence presented in support of the accounts will include an analysis of expenditure compared to budgets. Regular reporting of Balance Sheet accounts will require significant resources to implement. | Low | August 2006 |
| 17 | Absence in the closedown plan of a risk assessment to identify high risk tasks. Start dates, lead times or timescale requirement not set out. No provision for a review of progress by Head of Finance included. Report 2 R15. | Improvements should be made to the closedown process to include a risk assessment, time allocations for tasks, and a review of working papers by the Head of Finance. Overall responsibility for each task should be clearly allocated to one member of staff. | Closedown plan has been sent out 23/03/06 and revised to identify high risk areas. These may change as time passes and is being considered as part of the Monitoring process. Head of Financial Services, Chief Accountant and Principal Accountants are involved in monitoring actions against timetable. Key issue note sent out to DCS 09 May 2006. | Medium | June 2006. |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 18 | Delays in receiving some of the information needed for the interim visit – specifically: Most recent monitoring reports and control accounts reconcilations Notes detailing any changes to key personnel, control and systems. Closedown documentation. AC Report 1 para 11-17 , No.2 R16, & 3 page 3. | Future interim visits should begin with the receipt of the working papers detailed. | The delays last year were caused by the impact of the flood. In future the Interim report papers will be provided as required. The interim Audit visit for 2005/06 has been postponed for 2005/06 to enable concentration on the 2004/05 closedown. | Low | Not carried out- Complete. |
| 19 | The links between the quality of the final accounts and working papers and the judgements necessary for our Use of Resources work should be considered by the authority. AC Report 2 R20. | The authority should consider the links between the quality of the final accounts and working papers and our Use of Resources work later in the year. | A Use of Resources Improvement Plan is under preparation. This will be monitored by the Project Manager now in place. The Head of RBS is now taking the lead in driving forward the improvements required. HofFS will continue to manage delivering the improvements linking the Uof R with the Final Accounts process. | Med | June 2006 |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 20 | The control value for the customer advice centre is £940k. The project consists of a mix of consultancy services alongside the provision of software and IT hardware products. However, the contract documentation whilst listing in detail the key outputs of the project does not assign financial values to the various elements of the contract. In order to facilitate the subsequent capitalisation and disclosure of project costs within the financial statements and asset records, as well as the calculation of capital charges (depreciation and interest), arrangements will therefore need to be established to assign valuations/fair values to individual assets or groups of similar assets and other elements of the project in accordance with the requirements of the SORP and capital accounting guidelines. AC Reports 1 Appendix 2&3 & Report 3 14 & 22 Report 2 R18. | Establish arrangements to facilitate assignment of valuations/fair values to assets and other elements of the project in accordance with the requirements of the SORP and capital accounting guidelines. | This ties in to recommendation 5 above and was a significant issue in the 2004/05 accounts and contributed to the delay. Information has been passed to the Audit Commission in February 2006 and we are awaiting confirmation of their acceptance of the information provided. Recent events covered by item 1 above. | Low | Feb 2006 – Complete. |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 21 | Leisure services were transferred to Carlisle Leisure Limited in 2002/03 however no adjustments have been made to the carrying value of leisure assets in 2002/03 or 2003/04. This includes both property assets and equipment. AC Report 3 para 22. | Evidence compliance with FRS5 and SORP requirements regarding asset recognition and carrying value of leisure assets. | Work is underway to revise the entries to take account of this item. Working papers are being drawn up which correct this error. This issue has been raised in the amended report of the Audit Commission to the Audit Committee on 12th June. | Medium | June 2006 |
| 22 | Adjustments are required to debtors and creditor balances included in the balance sheets and supporting notes in order to address errors identified during the course of our audit. AC Reports 3 para 27 | WGA will add to the importance of disclosures made in respect of inter authority debtor and creditor balances. This is likely to include the requirement to agree invoiced and accrued balances with other relevant bodies. In the run up to implementation of WGA the Authority should therefore ensure that appropriate arrangements are in place to ensure efficient access to the information required to both meet existing disclosure the requirements and the requirements of the WGA process. | Arrangements were put in place for 2004/05 to identify Whole of Government Accounts (WGA) counter parties and year-end balances. Further work is underway as part of the 2005/06 closedown timetable to identify in year transactions as well as year-end balances with counter parties. Assistance is being sought from our financial information supplier to provide relevant reports, which will assist in the analysis, and reporting of this area of work. The ODPM consolidation pack is required to understand the detailed requirements. Once obtained a meeting will be set up to tackle this issue. | High | June 2006 |

| Ref | Issue | Audit Commission Recommendation | Action | Risk (H/M/L) | Timescale |
| --- | --- | --- | --- | --- | --- |
| 23 | PRTB receipts will be 100% useable although there is an expectation that the PRTB receipts would be spent in ways that helps deliver the Authority’s housing strategy. AC Report 3 para 26. | Confirm the existence of a clear strategy for the use of PRTB receipts consistent with the expectations of the ODPM. | The use of the PRTB receipts is applied towards the achievement of sustainable communities. Officers from Housing Policy and Finance have developed a draft strategy for clarification in the 2006/07 Capital Strategy, which will be submitted for approval by full Council in August 2006, following consideration by the Executive and CRO&S. | Medium | August 2006 |
| 24 | Annual commitment under operating leases. No working papers were included in closedown file to support the SSAP 21/SORP disclosures made in respect of annual commitments under (non-cancellable) operating leases. AC Reports 1, Appendix 3 & No 3 para 47. | Complete analysis of operating lease commitments in support of disclosures made in note 3. Complete note 3 to reflect number of asset acquired through operating leases in 2003/2004. | This was actioned in the 2003/04’s accounts. There was a further issue on the Refuse Collection vehicles, which were procured during 2003/04 raised during 2004/05. Details confirming our treatment of the leases have been passed to the Audit Commission and confirmation of acceptance of treatment is awaited. Actions will depend on AC feedback. | Low | June 2006 |
| 25 | Full systems documentation for core systems (14 in total) |  | 11 systems have been documented 2005/06 as agreed with AC, rising to 14 2006/07. 40 additional days has been built into the Internal Audit Strategic Plan for 2006/07 as agreed by CROS on 23rd February. | High | 2006/07 |