CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 3rd April 2008 |
| Title: | Pay & Workforce Strategy |
| Report of: | Jason Gooding, Deputy Chief Executive |
| Report reference: | CE 13/08 |

Summary:	This report advises Members on the progress of the Pay and Workforce Strategy project.

Recommendations:

The aim of this report is

- To provide an update to Members on the progress of the Pay and Workforce Strategy.

| Contact Officer: | Carolyn Mitchell | Ext: | 7306 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	Corporate Resources Overview and Scrutiny

Date:	3rd April 2008

Report on the Pay & Workforce Strategy

# 1.	Introduction

The Pay & Workforce Strategy project is being delivered, in partnership with the Trades Unions, through 6 work packages, i.e.

- Job Evaluation

- Equal Pay Review

- People Policies and Terms and Conditions review

- Single Status review

- Workforce Development Plan

- PWS Implementation

It was originally anticipated that the project would have been completed by the end of March 2008. This has not been achieved and this report provides a summary of where we are on each of the work packages.

2.	Progress to date

2.1	Job Evaluation

To mid-March,  526 job scores had been issued to staff and published on the Intranet and 262 appeals against these job scores received from 411 people.  240 appeals against job scores had been seen by at least 1 Steering Panel. Of those remaining, 14 were SO1/SO2 appeals against Hay scores (note that the pay for these posts will be determined by NJC scores).

Where it appears that evidence provided would be unlikely to result in an increased score, appellants are being advised in writing and given the opportunity to withdraw their appeals or pass it on to the Appeal panel for their consideration. In the majority of cases, appellants have elected for the latter.

Requests have been sent out to appellants and/or managers for additional information or sign-off as necessary. Once the information has been received, it goes back to the Steering Panel for them to reach a recommendation. Although timescales were set for the return of information many managers have not responded on time and follow-up contacts have been required. One of the effects of this has been that the first of the scheduled Hay Appeal Panels have been cancelled. Managers are being reminded of the importance of meeting the deadlines.

The project is aiming towards completion of the main tranche of appeal panels by the end of July 2008, though it is acknowledged that this is a challenging target.

To support its completion, the Job Analyst’s contract has been extended and backfill in Personnel for the PWS Administrator post will also be funded, both until the end of September.

2.2	Sustainability of Job Evaluation

Further training will be arranged for managers and Union reps who are willing to sit on JE panels in the future, when the project ends and job evaluation becomes part of the day-to-day work of the Personnel team.

However, there are a number of significant new areas for the Authority, that impact on the sustainability of Job Evaluation. Although proposals have been developed that any posts should be scored prior to approval by the Staffing Forum, it is likely that the number of regrading applications will increase due to changes to job requirements arising from

- Vacancy Management

- Business Process Architecture

- Shared Services

- Flexible Retirement

Consideration may also need to be given to the impact of amalgamating staff from Authorities who have carried out Job Evaluation, but where these have resulted in different scores/salaries for similar jobs.

These will increase the number of posts to be evaluated, but also place additional resource demands on the Personnel department, who are key to carrying out future job scoring, and on other elements of the implementation of the Pay & Workforce Strategy. These issues, though having an impact on implementation, are beyond the scope of this project and will be picked up by the Head of Personnel & Development.

  - Equal Pay

Equal Pay considerations will be taken into account as part of Job Evaluation quality checks and the development of revised pay structures, reward mechanisms and policies during the next few months.

Equality impact assessment of people policies is scheduled (see next section).

  - People Policies and Terms & Conditions

Appendix 1 provides a summary of the current position on the People Policies reviews and shows when they are likely to be reviewed. Those policies which form part of the Pay & Rewards package that the Council provides for its employees need to be reviewed prior to the revised pay package proposals being developed. As indicated in the list of policies, some of them will be amended as part of the Single Status work package.

It is likely that this work package can be closed shortly, as the rest of the policies can be reviewed within the normal cycle of policy reviews.

A schedule of work has been agreed with the Corporate Equality Group for Equality Impact Assessments to be carried out on all personnel policies.

2.5	Single Status

Single Status work is continuing with costed recommendations for harmonisation in the following areas to be completed by the end of April, for incorporation to the proposals for the future pay structures

- standby and callout arrangements and payments

- payment of professional fees

- car allowances

- premia payments (i.e. rates for working at night and at the weekend as part of the normal working week)

- phasing out timesheets

This work package can be closed once the recommended options are developed.

An update on the progress on Single Status is attached as appendix 2. The proposals contained in appendix 2 have not yet been agreed with Trades Unions.

  - Workforce Development Plan

Workforce Development Plan work package can now be closed. Having developed the Plan, its implementation is ongoing and forms part of the normal Personnel and Development and corporate activity.

2.7	PWS Implementation

Discussions with the Trades Unions on issues relating to back pay and pay protection will take place over the coming months. Their starting position is to request 3 years pay protection and 6 years back pay for staff whose salaries will change. Without costed proposals for the revised pay structures negotiation on these points cannot be entered into. These proposals cannot be fully developed until job evaluation appeals are complete.

However, initial pay modelling can start in April using recommended scores from Steering Panels as this will provide a useful estimate of the likely impact.

At the time of writing, the PWS Implementation Officer post was still within the Vacancy Management system for a decision as to whether or not it can be readvertised. This decision will have a significant effect on the pace and content of completion of the project and a verbal update on this will be provided at CROS.

- Conclusion

A number of work packages are at the point of completion.

Implementation has occurred on some elements of Single Status i.e. overtime, sick leave and holiday entitlements. Other recommendations have been produced and will be considered as part of the development of revised pay structures.

Workforce Development Plan has been developed and implementation is ongoing.

A number of People Policies have been amended and changes implemented, some are currently under review for completion in early 2008/9 and will feed into the pay proposals, others to form part of ‘normal’ Personnel & Development workload

Job Evaluation appeals are progressing slowly and a verbal update on anticipated completion dates for Appeals will be provided at the Committee meeting.

Sustainability of Job Evaluation is an issue that needs to be addressed outside of this project.

Members are requested to note progress on the project.

# Appendix 1 			PWS Work Package: Review of Policies and Terms and Conditions

List of Policies, Procedures and Guidance (working document as at 12 March 2008)

| Subject area | Date last amended | Statutory implications | Single Status implications | Comments | Proposed Review Date | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| 1 Recruitment, Retention and Workforce Planning |  |
| Recruitment & appointment policy (Equal Opportunities Policy) | 2007 | Yes | No | Some changes since last amended which need to be incorporated. Plus other issues need to be considered e.g. diversity/impact assessment likely to require changes; similarly e recruitment and Workforce Development Plan (WDP). Big changes looming necessitated by Safeguarding Children. | Current | High |
| 1.2 Job Descriptions & Person Specifications | As 1.1 | No | No | Is part of recruitment & appointment procedures. Some aspects (generic working, core values) may need to be linked to WDP. Is an issue as to whether or not to utilise Job Evaluation JDs. | current | Medium |
| 1.3 Criminal Records | 2005 | No | No | Up to date (as verified by CRB Quality Assurance checks). However, big changes looming necessitated by Safeguarding Children | current | High |
| 1.4 Recruitment and Retention Framework | 2003 | No | No | Some aspects need to be coherent with WDP therefore review needs to be done in conjunction with this work package; also links with outcome of JE/Single Status | 2008/9 | Medium |
| 1.5 Guidance on advertising | 2007 | Yes | No | Reviewed as part of Recruitment and Appointment doc. Interlinks with JD/Person Spec guidance. E-recruitment may necessitate further change | 2008/9 | Medium |
| 1.6 Types of contract | No guidance | No | No | Guidance on employment of Casuals written 2000; nothing else available at present | 2008/9 | Medium |
| 1.7 Changes to establishment (Staffing Forum) | May 2005. Since updated for vacancy management March 2008 | No | No | Guidance on forms only. Needs links to (and possible incorporated into) section 8.3; Staffing Forum process recently reviewed to accommodate introduction of vacancy management system (‘recruitment freeze’) Also needs to be amended once Job Evaluation exercise has ended and JE becomes ‘mainstreamed’. | current | High |
| 1.8 Removal allowance | Pre 1997 | No | No for majority of employees (except EDs & TCCE) | Allowances updated in line with inflation; currently a separate scheme for TCCE and E D’s; certain elements insufficient and unattractive; needs to be considered as part of 1.4 | 2008/9 | Medium |
| 1.9 Redeployment | 2004 | Yes | No | Relatively recently reviewed | 2009 | Low |
| 2 Attendance |  |
| 2.1 Sickness Absence | April 2004 | Yes | No | Due for review as indicated in policy – probably only minor changes. Single Status harmonisation achieved on Sick Pay in 2007. | 2008/9 | Medium |
| 2.2 Adoption Leave | 1995 | Yes | No | Needs to be updated to include recent legislative changes | Current review | High |
| 2.3 Carers’ Leave | 2001 | Yes | No | Needs review to ensure links with other ‘time off’ policies/arrangements are complementary | early 2008/9 | High |
| 2.4 Family Emergencies | 1999 | Yes | No | Still current – needs review after other ‘time off’ policies reviewed to ensure in line with any changes | 2008/9 | Medium |
| 2.5 Maternity Leave | 2005 | Yes | No | Information about entitlement etc recently updated; needs review to develop into a policy/guidance document with links to related policies/procedures | early 2008/9 | High |
| 2.6 Maternity Support/Paternity Leave | 1997 | Yes | No | Slight update required to incorporate recent legislative changes – review required to consider level of leave provided | 2008/9 | Medium |
| 2.7 Job Share | 1997 | Yes | No | Information still valid | 2009 | Low |
| 2.8 Annual Leave | 1981 | Yes | Yes | Statutory minimum complied with; differing levels within different groups of staff. Single Status harmonisation occurred 2007. | 2008/9 | Low within this work package |
| 2.9 Special Leave – interviews, School Governor, Reservist Forces, Special Constables | Various dates 1973 – c1997 | Yes | No | No one document outlining entitlement; would benefit from consolidation | 2008/9 | Medium |
| 2.10 Compassionate Leave | 1979/1984/1993 | No | No | Written information needs to be updated to take account equality issues (have adopted most of these in practice); link to attendance issues | 2008/9 | Medium |
| 2.11 Flexi leave | Pre 1997 | No | Yes | Some work done recently which needs to be incorporated within mainstream policy development | 2008/9 | Medium |
| 3 Diversity and Equal Opportunities |  |
| 3.1 Gender, Race, etc | 2007 | Yes | No | Recent but needs to link with work being overseen by Corporate Equality Group e.g. Race Equality Scheme and 1.1 | 2008/9 | Medium |
| 3.2 Disability | 2007 | Yes | No | Recent but needs to link with work being overseen by Corporate Equality Group e.g. Disability Equality Scheme and 1.1 | 2008/9 | Medium |
| 3.3 Age discrimination | 2007 | Yes | No | Recent but still needs to link with work being overseen by Corporate Equality Group and pensions (4.10) and 1.1 | 2008/9 | Medium |
| 4 Rewards & Benefits |  |
| 4.1 Car Lease Schemes | pre 1997 | No | Possibly | CE & CO Scheme different from PO; not available to other staff (or all POs); may form part of PWS Implementation package. Green Travel Plan likely to prompt changes | 2008/9 | Medium |
| 4.2 Car Essential Users | pre 1997 | No | Possibly | Green Travel Plan likely to prompt changes | 2008/9 | Medium |
| 4.3 Long Service Awards | 1996 | No | No | Hardly changed but not priority – unless to become linked with a Rewards Strategy | 2009 | Low |
| 4.4 Overtime | 2007 | No | Yes | Single Status harmonisation occurred 2007. More comprehensive guidance required. | 2009 | Low |
| 4.5 Progression in posts | Pre 1997 | No | Possibly | Was confined to ‘professional’ type posts but recent developments has resulted in ad hoc adoption in other areas; most manual employees on ‘spot salaries’ | 2008/9 in developing revised pay structure | Low within this work package but high for implementation of JE |
| 4.6 Grading appeals | 2000 | No | Yes | Will be incorporated within Job Evaluation Work Package | 2008 | Low (for Policies work package) package but high for JE Implementation |
| 4.7 Pay policy | Pre 1997 | No | Possibly | Based around national conditions for most part; no written pay policy at present; some principles in other documents and/or ‘custom and practice’ (not comprehensive); need to include ‘salary sacrifice’; suggest best done as part of Implementation work package | 2008/9 in developing revised pay structure and | Low within this work package package but high for JE Implementation |
| 4.8 Standby and call out | Pre 1997 | No | Yes | Differing arrangements in different part of the organisation; some disquiet around the issue. Work in progress | Current. Single Status review. | High |
| 4.9 Car Parking | 2003 | No | No | Green Travel Plan likely to prompt changes | 2009 | Medium |
| 4.10 Pensions : Early release, gratuity scheme for widows and dependent relatives, disputes procedures; Guidance on Pension Scheme obligations and discretions | 1998; Disputes procedures – 2005 | Part | No | Work in progress | Current | High |
| 4.11 Redundancy selection | 2007 | Yes | No | Recently updated | 2011 | Low |
| 4.12 Salary protection | 1991 | No | No | Policy documented within Redundancy Procedures – more appropriate if separate ‘policy’ document. | 2008/9 as part of PWS Implementation | High |
| 4.13 Sick Pay | 207 | No | Yes | Single Status harmonisation achieved in 2007. | 2011 | Low |
| 4.14 Expenses | 2000 | No | No | Level increased annually in line with inflation. No issues | 2010 | Low |
| 4.15 Working time issues | 2000 | Yes | Possibly | Premium rates (out of hours working) under review within Single Status work package. Others to be considered when developing pay proposals. | Current. | Low within the Policies work package but high for Single Status |
| 5 Health, Safety and Welfare |  |
| 5.1 Health and Safety Policy | 2004 | Yes | No | Approved by full Council. Still valid although it could benefit from updating for Corporate Manslaughter legislation | 2009 | Low |
| 5.2 Confidential Counselling | Pre 1997 | No | No | Still appropriate | 2009 | Medium |
| 5.3 Abuse of Drugs and Alcohol | 1990 | No | No | Still appropriate | 2010 | Low |
| 5.4 Violence to Staff | 1999 | No | No | Still appropriate | 2010 | Low |
| 5.5 VDU Users – eye test, personal use | Pre 1997 | Yes | No | Would benefit from incorporating the system into ‘Occupational health provision’ routines & guidance to staff; information still valid | 2009 | Medium |
| 5.6 First Aid | 1980 | Yes | No | Payment of allowances would benefit from review; best dealt with as part of Implementation work package | 2008/9 part of revised pay structure proposals | Medium |
| 5.7 Occupational Health | 2007 | No | No | New enhanced arrangement jointly procured with other Cumbrian councils | 2010 | Low |
| 5.8 Smoke free environment | 2007 | Yes | No | Still valid, in line with 2007 legislation and good practice | 2011 | Low |
| 5.9 Wellbeing strategy | No strategy | No | No | Aspirational - to better integrate other policies and to introduce planned supported health promotion. However, we have no resources for it | 2008/9 | Medium |
| 6 Officer Skills and Development |  |
| 6.1 Appraisal | 2007 | No | No | Will be reviewed as part of Equality Impact Assessment process | early 2008 | Medium |
| 6.2 Workforce Development Plan | 2007 | No | No | Still valid. New Corporate Training Programme is to be launched May 2008 (City First) | 2010 | Low |
| 6.3 Secondment | 2006 | No | No | Needs some updating (to include internal secondments) | 2010 | Low |
| 6.4 Qualification Study | 2004 | No | No | Will be reviewed as part of Equality Impact Assessment process | early 2008 | Medium |
| 6.5 Induction | 2004 | No | No | Takes 2 forms: local induction and corporate induction both under review at present. Needs guidance for on-job Induction and policy/guidance on links to probation and City First. E-learning is being introduced to deliver much of the current mandatory training provided now as part of induction process | Current | High |
| 6.6 Team Improvement Reviews | 1999 | No | No | Working ok at present tho could benefit from an update | 2010 | Low |
| 6.7 Probation | Pre 1997 | No | No | A new policy is now approved and piloted. It will be fully implemented when City First is launched | Current | High |
| 6.8 Skills for Life Strategy | 2007 | No | No | Still valid | 2010 | Low |
| 6.9 Training Policy | 2006 | No | N o | Still valid though would benefit from the addition of both a corporate strategy and by Plans at Directorate level. Will be reviewed as part of Equality Impact Assessment process | Early 2008 | Medium |
| 7 Employee Relations and Communications |  |
| 7.1 Consultation and Communications framework | 2003 | Yes | No | Framework re Trades Unions Consultation; practices established partially because of above and ‘custom and practice’. Needs comprehensive guidance | 2008 | High |
| 7.2 Trades Unions Facilities Agreement | 2007 | Yes | No | Still valid | 2011 | Low |
| 7.3 Disciplinary Procedures | 2007 | Yes | Yes | Still valid | 2011 | Low |
| 7.4 Grievance Procedures | 2002 | Yes | Yes | Procedures meet statutory requirements but need for more comprehensive guidance to include additional circumstances when grievances may be raised | 2008 | High |
| 7.5 Capability Procedure | No procedure | Yes | No | No separate procedure – currently dealt with under discipline or attendance: sickness absence management procedures. Itis good practice to have a separate procedure (which can ‘mirror’ these procedures) | Current | High |
| 7.5 Code of Conduct for Officers | Pre 1992 | Yes | No | Unnecessarily wordy – needs simplifying; a national code due shortly apparently. Include in disciplinary procedures | 2008/9 | High |
| 7.6 Dignity and Respect | 2007 | No | No | Still valid | 2010 | Low |
| 7.7 Confidential Reporting | 2004 | Yes | No | Known as ‘whistleblowing’. Needs some updating. Safeguarding Children code suggests it is updated annually tho exisitng policy still valid | 2008/9 | Medium |
| 7.8 Internet and E Mail | 2000 | No | No | Initially produced by IT department – due to potential link with disciplinary procedure and code of conduct needs now needs to be mainstreamed within people policies | 2009 | Medium |
| 8 Flexibility |  |  |  |  |
| 8.1 Cross functional working | No guidance or written policy | No | No | Possibly a ‘framework’ more appropriate? | 2009 | Medium |
| 8.2 Partnership working | No guidance or written policy | No | No | Possibly a ‘framework’ more appropriate? | 2009 | Medium |
| 8.3 Changes to Establishment | See 1.7 | No | No | Authority to amend establishment is obtained through Staffing Forum. Aspect of recruiting and appointing dealt with through ‘Assimilation Protocols’ – currently produced for each set of circumstances based on protocol used in 2002 Council wide reorganisation. Needs link to 7.1 | Current | High |
| 9 Member Learning and Development | Not part of this project or work package but included for completeness. Does link with WDP |

## Key to how  ‘Priorities’ have been assessed

High:		policies/procedures (or lack of them) do not comply with statutory requirements and/or causing difficulties for the Council

Medium:	desirable to review quickly, but Council not at risk by a delay and/or need to await further developments to carry out an effective review 		e.g. they require input from other work packages or another function within the Council

Low:		policy/procedures reviewed recently and/or no significant difficulties perceived

Jean Cross PPP

# Appendix 2:

# PWS Work Package: Single Status  – Progress Report

# General

  - Terms and conditions for sickness payment, annual leave and overtime were harmonised as part of the Single Status Agreement and were effective from 1 April 2007.

  - The remaining aspects are:

- Premia payments

- Standby and call out arrangements

- Removal of timesheets for recording attendance and pay related matters

- Bonus payments

- A number of additional allowances e.g. tool allowances, shift allowances, ‘sleep in’ payment, ‘return to work’ payments, emergency planning increments

- Attendance payments

  - It was agreed that these would form part of the Pay and Workforce implementation work package as they relate primarily to employees’ pay for their job and need to be considered in tandem with the outcome of job evaluation.

# Work done to date

  - Work has been carried out on premia payments, standby/call out arrangements and removal of timesheets.  However these are in their early stages in that they have not been costed or discussed with the trades unions.

  - Premia Payments

These relate to work carried out during times most people consider antisocial hours, such as at night, at weekends, on bank holidays.  There are several different practices operating at present:

- Some employees receive payment based on a variation on those nationally agreed conditions that existed prior to the Single Status agreement in 1997

- Some employees are paid an all inclusive rate

- Some employees receive a shift allowance and ‘sleep in’ payments.

It is proposed that the Council operate two practices in future (both based on National Conditions):

- For those services where employees work a predictable rota, a shift allowance is paid, based on the ‘normal’ unsocial hours the work rota involves.  For example, if the rota gives the employee 10% of their hours on a Saturday and 6% on a Sunday, this converted to a percentage shift allowance, payable in twelve equal instalments.  This arrangement would rely on ‘give and take’ when booking leave, changing shift etc. but provides a predictable income, is administratively less time consuming and makes budgeting easier.

- Where is not possible to predict likely hours to be worked during anti-social times, a rate for actual hours worked as follows:

- 1.5 times hourly rate for all hours worked on Saturdays

- double time for all  hours worked on Sunday for those who earn below spinal column point 11 (or equivalent if we change the pay structure) and 1.5 times hourly rate for those who earn above this sum

- 1.33 times hourly rate for weekday hours worked between 20.00 and 6.00

- for working on Public holidays, employees would receive normal pay plus plain time for hours worked plus time off with pay of half a day if the shift is less than half the normal one and a full day if the shift is half or more than a normal shift.  On occasions where Christmas Day, Boxing Day or New Years’ Day fall on a Saturday or Sunday and is therefore not a designated Public Holiday, the Council may agree to pay Public Holiday rates on actual day rather than the ‘designated’ day.  The decision to be taken by the Head of Personnel and Development Services.

## Standby and callout

  - A variety of existing arrangements at present and these have been identified in an Audit report in January 2006.

  - It is proposed to replace them with the following:

- Level 1 standby and call out.  These will be employees who are required to be on standby, available and skilled enough to respond to calls at any time during the period of ‘standby duty’.  Callout is generally frequent (4 or more times a week).  For staff above scale 6 (or equivalent if the pay scale is changed) the stand by allowance paid covers all hours spent on the call out whether it is dealt with from home or the employee is required to make a visit to deal with the issue. For those paid below scale 6, the standby allowance covers all calls that can be dealt with from home and the first X number of calls out (or Y hours spent on the task).  No additional travel costs payable.

Employees on Level 1 callout will be expected to deal with a range of issues including those outside their own area of work. Included in this arrangement would be Environmental Services.  As many types of incidents as possible should be transferred to be dealt with by those on this arrangement.

- Level 2  – those employees who are required to be available, fit and skilled to deal with issues relating to their specialist work and where this cannot be carried out by those on Level 1 call out. Call out is less frequent than level 1 (less than 4 times per week); sometimes advice can be provided from home, sometimes a visit is required.  A lower level of payment will be made to employees on this rota. ).  For staff above scale 6 (or equivalent if the pay scale is changed) the stand by allowance paid covers all hours spent on the call out whether it is dealt with from home or the employee is required to make a visit to deal with the issue. For those paid below scale 6, the standby allowance covers all calls that can be dealt with from home and the first X number of calls out (or Y hours spent on the task). No additional travel costs payable.

- Level 3 Call out – payable where there are number of people who may be called out to deal with a relatively infrequent incident and apply to employees who are not obliged to remain ‘on call, fit and able to respond’.  An example of this level of callout is where key holders are called to deal with an alarm which has been activated, or IT employees are called regarding a computer failure.  Payment for this will be the time taken to deal with the callout, with a minimum payment of 2 hours (to include travel if required) at the overtime rate applicable to the employee time off in lieu at plain time.  No travel costs payable.

- Level 4– senior people who can expect to be contacted or called out as part of their job role, and as such, no payment will be made.  If any significant amount of time is spent on the task, the employee will be entitled to time off (at plain time) or, in exceptional cases, overtime at the employee’s appropriate rate. (The latter is likely to apply to those on the Emergency Planning rota). Mileage costs reimbursed at employee’s normal rate.

# Removal of timesheets

  - Some initial exploratory work has been carried out and a number of practical difficulties identified.  These fall into three areas:

- capturing necessary employee pay related data such as recording sickness, leave and other authorised absence

- job costing

- recording attendance

The first is likely to be more easily resolved than the other two.

- Other payments and allowances.

  - It is proposed to deal with the remaining issues as follows:

- Bonus – discontinue as such and incorporate into the job rate as measured by job evaluation;  the Council has no bonus schemes which could be defended in the event of an equal pay claim

- Attendance allowance – discontinue as such and incorporate into the job rate as measured by job evaluation.  The current allowance is paid to male dominated work areas and are indefensible in the event of an equal pay claim

- ‘Return to work payments’.  These are paid to Parking Patrol Officers who work a normal shift, go home for a few hours, then return to enforce parking regulations at Kingstown Industrial estate.  The proposal for these is to amend the shift patterns to give a continuous shift and pay premia payments for those hours after 20.00

- ‘Sleep in’ payments – continue to pay these

- Tool allowances – to consider whether or not these should continue.  The decision should hinge around whether or not the employees are required to provide their own tool, or whether the Council provides them

- Emergency planning increments – it is proposed that these should be discontinued as they are currently paid to four employees whose role encompasses the work they do (as in call out level 4 above).  At present, special overtime arrangements apply for staff called out in response to an emergency in that all officer receive time and a half irrespective of the hours worked and their grade.  It is proposed to bring the payment into line with the overtime rates agreed as part of Single Status i.e. those paid above scale 6 should receive single time and those below scale 6 time and a half or double time dependent on the time the work is carried out.  This also means that part time employees work 37 hours before any enhanced rates are paid.