OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 29 May 2003 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.33/03 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 April to 31 July 2003 and 1 May to 31 August 2003 since their publication on 18 March and 17 April 2003 respectively.

Recommendations:	To note the modifications, deferrals and departures from the Forward Plans for 1 April to 31 July 2003 and 1 May to 31 August 2003.

| Contact Officer: | Elspeth MacKay | Ext: | 7034 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

  - Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the period 1 April to 31 July 2003 and 1 May to 31 August 2003 are outlined in Appendix A of the report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the Forward Plans for 1 April to 31 July 2003 and 1 May to 31 August 2003 be noted.

Contact Officer:		Elspeth MacKay						Ext:: 7034

1st April 2003 to 31 July 2003

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.021/03 | Proposed Renewal of Civic Centre Fire Alarm Corporate Resources Overview and Scrutiny | Deferred from 3 April to June 2003 | Head of Commercial and Technical Services |
|  | Reason: It needs to be considered as part of a prioritised programme of risk mitigation proposals. Corporate risk management group will be meeting to consider this programme |
| KD.012/03 | Financial Ledgers Replacement Corporate Resources Overview and Scrutiny | Deferred from 3 April to 28 April 2003 | Head of Finance |
|  | Reason: Delayed as further options are being considered |
| KD.030/03 | Longtown Market Town Initiative Community Overview and Scrutiny | Deferred from 3 April 2003 to 28 April 2003 | Head of Economic and Community Development |
|  | Reason: The formal request for the Council’s involvement as the accountable body and fund holder for the scheme had not yet been received |
| EX.078/03 | Final Accounts 2001/02 – Closure Issues Corporate Resources Overview and Scrutiny | Item was not included in the Forward Plan – considered by Executive on 3 April 2003 under General Exception Rules | Head of Finance – with approval of the Leader |
|  | Reason: A recommendation needed to be considered by the Executive prior to consideration by the Council on 29 April 2003 |
|  | Housing Benefits – Allocation of additional Grants and appointment of additional staff Corporate Resources Overview and Scrutiny Committee | Item was not included in the Forward Plan – considered by Executive on 28 April 2003 under General Exception Rules | Head of Revenue and Benefits Services – with approval of the Leader |
|  | Reason: In order that action can be taken to make the necessary staff appointments as soon as possible |
|  | Raffles Regeneration – Raffles Area Strategy – Position Statement All Overview and Scrutiny Committees | Item was not included in the Forward Plan – considered by Executive on 28 April 2003 under General Exception Rules | Head of Economic and Community Development – with approval of the Leader |
|  | Reason: In order that the Raffles regeneration can proceed without unreasonable delay |

1st May 2003 to 31 August 2003

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.034/03 | CCTV Annual Report Community Overview and Scrutiny | Deferred from 9 June to 7 July 2003 | Head of Commercial and Technical Services |
|  | Reason: Staff shortages have led to a delay |
| KD.038/03 | Transportation Issues Infrastructure Overview and Scrutiny | Deferred from 9 June to 7 July 2003 | Head of Commercial and Technical Services |
|  | Reason: The Council is liasing with other agencies and responses are awaited |
| KD.035/03 | Procurement Corporate Resources Overview and Scrutiny | Deferred from 9 June 2003 to 7 July or August 2003 | Head of Commercial and Technical Services |
|  | Reason: This is to be considered as part of the Corporate Strategy and is therefore being considered under a revised timescale |
| KD.021/03 | Proposed Renewal of Civic Centre Fire Alarm Corporate Resources Overview and Scrutiny | Deferred from 9 June to 7 July 2003 | Head of Commercial and Technical Services and Executive Director |
|  | Reason: Moved to July to tie in with consideration of the report on Civic Centre Accommodation |
| KD.047/03 | Land and Property Transactions Corporate Resources Overview and Scrutiny Infrastructure Overview and Scrutiny | Standing item removed from Plan | Corporate Management Team on 6 May 2003 |
|  | Reason: Individual transactions will be included in the Plan as and when necessary |
| KD.011/03 | Raffles Regeneration – Redevelopment Agreement Corporate Resources Overview and Scrutiny Community Overview and Scrutiny | Deferred from 9 June to 7 July 2003 | Corporate Management Team on 6 May 2003 |
|  | Reason: Delays in consultation with other agencies |
| KD.026/03 | Waste Management Infrastructure Overview and Scrutiny | Deferred from 9 June to 7 July 2003 | Corporate Management Team on 6 May 2003 |
|  | Reason: Meeting with Eden District Council needs to be held before report can be finalised |
| KD.028/03 | Hostel Accommodation Community Overview and Scrutiny | Deferred from 9 June to August 2003 | Corporate Management Team on 6 May 2003 |
|  | Reason: Change in corporate reporting arrangements and delay in consultation |
| KD.039/03 | Development Control – Changes to Delegation Infrastructure Overview and Scrutiny | Item removed from Plan | Corporate Management Team on 6 May 2003 |
|  | Reason: Matter will be considered by Development Control Committee then the full Council |
| KD.073/02 | Asset Management Plan – Review of Economic Assets Corporate Resources Overview and Scrutiny Infrastructure Overview and Scrutiny | Deferred from 9 June to August or September 2003 | Corporate Management Team on 6 May 2003 |
| KD.098/02 | Local Public Service Agreements Corporate Resources Overview and Scrutiny | Deferred from 9 June to 7 July 2003 | Corporate Management Team on 6 May 2003 |
|  | Reason: Delays in meeting with other agencies involved |
| KD.101/02 | Information Systems Strategy Corporate Resources Overview and Scrutiny | Deferred from 30 June to August 2003 | Corporate Management Team on 6 May 2003 |
|  | Reason: Customer Contact has taken priority |
| KD.021/03 | Proposed Renewal of Civic Centre Fire Alarm Corporate Resources Overview and Scrutiny | Item removed from Plan | Corporate Management Team on 6 May 2003 |
|  | Reason: Subsumed within Civic Centre Accommodation (KD.029/03) |
| KD.029/03 | Civic Centre Accommodation Corporate Resources Overview and Scrutiny | Deferred from 7 July 2003 to August 2003 | Corporate Management Team on 6 May 2003 |
|  | Reason: Delayed as it now includes renewal of Civic Centre Fire Alarm |
| KD.035/03 | Procurement Strategy Corporate Resources Overview and Scrutiny | Brought forward from July or August 2003 to 9 June 2003 | Corporate Management Team on 6 May 2003 |
| KD.072/02 | Asset Management – Surplus Land Review and Operational Property Priorities Corporate Resources Overview and Scrutiny | Item removed from Plan | Corporate Management Team on 6 May 2003 |