## 2010-11 Prog
2010/11 CAPITAL PROGRAMME | [5 empty] | APPENDIX A
Scheme | Original | Carry | Other | Proposed | Potential | Revised
| Capital | Forwards | Adjustments | Carry | Savings | Capital
| Programme | from |  | Forward |  | Programme
| 2010/11 | 2009/10 |  |  |  | 2010/11
| £ | £ | £ | £ | £ | £
Current non-recurring commitments
Customer Contact Centre | 49600 |  |  |  |  | 49600
Chances Park |  | 234000 |  |  |  | 234000
Community Resource & Training Centre | 3081000 | -23900 |  | -1493400 |  | 1563700
Environmental Enhancements | 168000 | 0 | -15000 |  |  | 153000
Sub Regional Employment Sites | 256000 | 21700 |  |  |  | 277700
RBS Shared Service | 132900 | -21500 |  |  |  | 111400
Document Image Processing |  | 45000 |  |  |  | 45000
| 3687500 | 255300 | -15000 | -1493400 | 0 | 2434400
Recurring commitments
Housing Strategy - Affordable Housing | 300000 |  | -200000 | -32600 |  | 67400
Housing Strategy - Empty Homes | 140000 | 44500 | -16000 |  |  | 168500
Housing Strategy - Decent Homes | 300000 |  | -27300 |  |  | 272700
Housing Strategy - Minor Works grants |  | 11300 |  |  |  | 11300
Housing Strategy - Housing Provision | 200000 |  | -120000 | -80000 |  | 0
Planned Enhancements to Council Property | 358700 | 14700 | 5000 | 49000 |  | 427400
Willowholme Industrial Estate | 135000 | 4000 |  | -79000 |  | 60000
Kingstown Industrial Estate |  | 499100 |  | -150000 |  | 349100
Play Area Developments | 50000 | 135000 |  |  |  | 185000
Vehicles, Plant & Equipment | 381500 | 35700 | 10200 | -62700 |  | 364700
ICT Shared Service | 380000 | 104700 |  |  |  | 484700
CCTV | 70000 |  |  |  | -70000 | 0
| 2315200 | 849000 | -348100 | -355300 | -70000 | 2390800
New non-recurring commitments
Families Accommodation Replacement | 200000 |  |  | -172000 |  | 28000
Old Town Hall | 970000 |  |  | -970000 |  | 0
Roman Frontier | 2117000 | -128500 |  | -654600 |  | 1333900
City Play Trail |  |  | 83200 |  |  | 83200
Connect 2 Cycleway |  |  | 15000 |  |  | 15000
| 3287000 | -128500 | 98200 | -1796600 | 0 | 1460100
Disabled Facilities Grants
Private Sector Grants | 1249000 | 224500 |  |  |  | 1473500
| 1249000 | 224500 | 0 | 0 | 0 | 1473500
Continuing Schemes
Gateway - General Expenses |  | 29700 |  |  | -29700 | 0
Ghyll Bank Gypsy and Travellers Site |  | 48600 | 13300 |  |  | 61900
Lowry Hill Park | 75700 | -29500 |  |  |  | 46200
Trinity Church MUGA |  | 135500 |  |  |  | 135500
Heysham Park Play Area |  | 600 |  |  |  | 600
Petteril Riverbank Protection Work |  | 1300 |  |  |  | 1300
Hammonds CCTV |  | 4000 |  |  |  | 4000
Caldew/City Centre Flood Defence |  | 12100 |  |  |  | 12100
Historic Quarter | 719800 |  |  |  |  | 719800
Carbon Trust Energy Efficiency |  | 6000 |  |  |  | 6000
Renaissance Improvements |  | 24700 | -11300 |  |  | 13400
| 795500 | 233000 | 2000 | 0 | -29700 | 1000800
Flood
ODPM Private Sector Renewal |  | 25000 |  |  |  | 25000
Sheepmount Development |  | 800 |  |  |  | 800
| 0 | 25800 | 0 | 0 | 0 | 25800
TOTAL | 11334200 | 1459100 | -262900 | -3645300 | -99700 | 8785400

## Governance
SEPTEMBER 2010 - CAPITAL BUDGET MONITORING | [8 empty] | APPENDIX B
GOVERNANCE
| Scheme | Annual Budget | Proposed Carry Forwards | Potential Savings | Revised Annual Budget | Budget to date | Expenditure to date | Variance to date | Details of major variance
| Gateway - General Expenses | 29700 | 0 | -29700 | 0 | 0 | 12188 | 12188 | Final retention payment to Oxford Archaeology under the contract. To be funded from provision at year end.
Grand Total |  | 29700 | 0 | -29700 | 0 | 0 | 12188 | 12188

## Resources
SEPTEMBER 2010 - CAPITAL BUDGET MONITORING | [8 empty] | APPENDIX C
RESOURCES
| Scheme | Annual Budget | Proposed Carry Forwards | Potential Savings | Revised Annual Budget | Budget to date | Expenditure to date | Variance to date | Details of major variance
| IT Shared Service | 484700 | 0 | 0 | 484700 | 0 | 1895 | 1895 | Part of Shared Service Business Case.
| CTS/EPS IT System | 0 | 0 | 0 | 0 | 0 | 2797 | 2797 | Expenditure relates to configuring Civica system ready for various statistical returns.
| Major Repairs | 378400 | 49000 | 0 | 427400 | 127403 | 125314 | -2089 | Report presented to Executive 26th July requesting release of 2010/11 budget. No significant variances to date.
| Vehicles & Plant | 427400 | -62700 | 0 | 364700 | 90200 | 90200 | 0 | The current replacement plan is being revisited and a revised plan is being considered as part of the 2011/12 budget process..
| Energy Efficiency-Carbon Trust Initiative | 6000 | 0 | 0 | 6000 | 6000 | 2875 | -3125 | Budget carried forward from 2009/10 to complete lighting project at Tullie House.
| Document Image Processing | 45000 | 0 | 0 | 45000 | 0 | 0 | 0 | Project on hold pending creditor/debtor efficiency review.
Grand Total |  | 1341500 | -13700 | 0 | 1327800 | 223603 | 223081 | -522

## Community Engagement
SEPTEMBER 2010 - CAPITAL BUDGET MONITORING | [8 empty] | APPENDIX D
COMMUNITY ENGAGEMENT
| Scheme | Annual Budget | Proposed Carry Forwards | Potential Savings | Revised Annual Budget | Budget to date | Expenditure to date | Variance to date | Details of major variance
| Customer Services | 49600 | 0 | 0 | 49600 | 0 | 2495 | 2495 | Project linked to corporate wide review of Customer Services. Release of budget approved 11/10/10.
| Minor Works Grants | 11300 | 0 | 0 | 11300 | 5654 | 5424 | -230 | Budget carried forward from 2009/10 to assist vulnerable people to carry out approved emergency works.
| Disabled Facilities Grants | 1473500 | 0 | 0 | 1473500 | 737046 | 736973 | -73 | Approved grant commitments of £75,000 currently. Budget expected to be fully spent by financial year end.
| Housing Strategy - Decent Homes | 272700 | 0 | 0 | 272700 | 12500 | 7050 | -5450 | Housing Strategy budget reprofiled over 5 years. Expected to be fully spent by year end.
| Housing - Investment in Empty Homes | 168500 | 0 | 0 | 168500 | 24999 | 22582 | -2417 | Current approved grant commitments of £75,000. Budget expected to be fully expended this financial year.
| Housing - Support for Affordable Housing | 100000 | -32600 | 0 | 67400 | 0 | 0 | 0 | Housing Strategy budget reprofiled over 5 years. £60,000 is committed to housing development with Riverside Housing and will be spent by year end. £40,000 required in 2011/12 for development of Community Land Trust in Brampton.
| Housing Strategy - Housing Provision | 80000 | -80000 | 0 | 0 | 0 | 7356 | 7356 | Budget earmarked to be carried forward.
| Community Resource & Training Centre | 3057100 | -1493400 | 0 | 1563700 | 63692 | 59615 | -4077 | Contract for construction awarded with start on site late August 2010.
| Ghyll Bank Gypsy & Travellers Site | 61900 | 0 | 0 | 61900 | 55253 | 50304 | -4949 | Construction works completed.
| Families Accommodation Replacement | 200000 | -172000 | 0 | 28000 | 0 | 0 | 0 | Site selection in progress.
| RBS Shared Service | 111400 | 0 | 0 | 111400 | 0 | 0 | 0 | Part of Shared Service Business Case which is currently being consolidated across the Partnership.
| Sheepmount Development | 800 | 0 | 0 | 800 | 800 | -41 | -841 | Budget carried forward from 2009/10 for planned work still to be completed which was delayed due to equipment unavailability.
| Sheepmount Drainage | 0 | 0 | 0 | 0 | 0 | 5200 | 5200 | Funded from an earmarked reserve. Transfer actioned at year end.
| Synthetic Football Pitch | 0 | 0 | 0 | 0 | 0 | 326 | 326 | Expenditure incurred on project management relating to the release of the retention.
| Tullie House Gallery Improvements | 0 | 0 | 0 | 0 | 0 | 4225 | 4225 | Expenditure in relation to retention for work completed in 2007/08 and additional equipment.
| Roman Frontier | 1988500 | -654600 | 0 | 1333900 | 129932 | 75928 | -54004 | Work is currently on-going with funding partners to revise the expenditure profiles for this scheme.
| City Play Trail | 83200 | 0 | 0 | 83200 | 0 | 700 | 700 | External grant has been received for this project.
Grand Total |  | 7658500 | -2432600 | 0 | 5225900 | 1029876 | 978137 | -51739

## Local Environment
SEPTEMBER 2010 - CAPITAL BUDGET MONITORING | [8 empty] | APPENDIX E
LOCAL ENVIRONMENT
| Scheme | Annual Budget | Proposed Carry Forwards | Potential Savings | Revised Annual Budget | Budget to date | Expenditure to date | Variance to date | Details of major variance
| CCTV Future Enhancement and Development | 70000 | 0 | -70000 | 0 | 0 | 0 | 0 | Identified as saving as Phase 1 of review.
| Hammonds CCTV | 4000 | 0 | 0 | 4000 | 2002 | 0 | -2002 | Budget carried forward from 2009/10. Awaiting completion of project.
| ODPM Private Sector Renewal | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | Budget carried forward from 2009/10.
| Petteril Riverbank Protection | 1300 | 0 | 0 | 1300 | 652 | 551 | -101 | Budget carried forward from 2009/10 to accommodate final account from contractor.
| Caldew/City Flood Defence | 12100 | 0 | 0 | 12100 | 6052 | 0 | -6052 | Budget carried forward from 2009/10. Expected completion during summer 2010.
| MUGA - Trinity Church | 135500 | 0 | 0 | 135500 | 1802 | 1100 | -702 | Budget carried forward from 2009/10. Project delayed due to outstanding queries regarding the size of the development in relation to the level of funding available.
| Lowry Hill | 46200 | 0 | 0 | 46200 | 46200 | 47902 | 1702 | Project funded through Section 106 monies carried forward from 2009/10. Project completed.
| Play Areas | 185000 | 0 | 0 | 185000 | 135000 | 136539 | 1539 | Report required to Executive to release 2010/11 budget allocation of £50,000. No significant variances to date.
| Chances Park | 234000 | 0 | 0 | 234000 | 158698 | 158700 | 2 | Final account still awaited from contractor.
| Heysham Park Play Area | 600 | 0 | 0 | 600 | 300 | -133 | -433 | Budget carried forward from 2009/10 to accommodate project management inspection at end of contract. Retention invoiced at less than expected.
| Environmental Improvements | 153000 | 0 | 0 | 153000 | 80527 | 27057 | -53470 | The 2010/11 allocation requires allocation to individual schemes which will amend the current budget profile.
| Small Scale Community Projects | 0 | 0 | 0 | 0 | 0 | -197 | -197
| Kingstown Industrial Estate Roads | 499100 | -150000 | 0 | 349100 | 174558 | -99 | -174657 | Budget carried forward from 2009/10. Project still significantly delayed.
| Willowholme Industrial Estate Roads | 139000 | -79000 | 0 | 60000 | 30024 | 0 | -30024 | Budget carried forward from 2009/10. Project currently on hold.
| Castle Street Public Realm Improvements | 719800 | 0 | 0 | 719800 | 287920 | 318907 | 30987 | Budget carried forward from 2009/10. Construction began 7th June. Expected to be fully spent by financial year end.
| Connect 2 Cycleway | 15000 | 0 | 0 | 15000 | 15000 | 16840 | 1840 | Budget relates to Lime Street section of the programmed works.
| Waste Minimisation | 0 | 0 | 0 | 0 | 0 | 34924 | 34924 | Expenditure relates to the purchase of replacement wheeled bins for those stolen or damaged. Funding options for this service are currently being investigated.
Grand Total |  | 2239600 | -229000 | -70000 | 1940600 | 938735 | 742091 | -196644

## Economic Development
SEPTEMBER 2010 - CAPITAL BUDGET MONITORING | [8 empty] | APPENDIX F
ECONOMIC DEVELOPMENT
| Scheme | Annual Budget | Proposed Carry Forwards | Potential Savings | Revised Annual Budget | Budget to date | Expenditure to date | Variance to date | Details of major variance
| Renaissance Improvements | 13400 | 0 | 0 | 13400 | 6703 | 6703 | 0 | Budget carried forward from 2009/10 as match funding for Urban Design Framework.
| Old Town Hall - Strategic TIC | 970000 | -970000 | 0 | 0 | 0 | 0 | 0 | Report required to Executive to release budget.
| Sub Regional Employment Sites | 277700 | 0 | 0 | 277700 | 277700 | 487839 | 210139 | Overspend relates to additional work relating to asbestos caused by damage to the site through vandalism. Insurance claim outstanding to potentially fund this overspend.
Grand Total |  | 1261100 | -970000 | 0 | 291100 | 284403 | 494542 | 210139