| REPORT TO EXECUTIVE |
| --- |
| PORTFOLIO AREA: FINANCE |
| Date of Meeting: | 1 September 2009 |
| Public |  |
| Key Decision: | Yes/No | Recorded in Forward Plan: | Yes/No |
| Inside/Outside Policy Framework |

| Title: | ALLERDALE/COPELAND/CARLISLE REVENUES AND BENEFITS SHARED SERVICES DRAFT BUSINESS CASE |
| --- | --- |
| Report of: | Director of Corporate Services |
| Report reference: | CORP37/09 |

Summary:

This report asks members to consider the draft Business Case agreed in principle by the Project Board on 29 July 2009 (see Appendix A).

Recommendations:

Members are asked to:

- Support  the Project Board view that the preferred option in the Business Case ‘Joint Service Delivery’ be agreed.  The results of the consultation and external verification exercises to date will be circulated as an addendum to the report before the meeting.

- Note that the proposals set out in the report will deliver estimated savings of £120,000 per annum with estimated set up costs, i.e. capital, termination and protection costs of £160,000 being paid back in 1.6 years.  This £160,000 will be subject to further analysis of the financial position and will require a supplementary estimate later in the decision-making process.

| Contact Officer: | Peter Mason | Ext: | 7270 |
| --- | --- | --- | --- |

RESOURCES OVERVIEW AND SCRUTINY PANEL

Committee Report

| Public |
| --- |
| Date of Meeting: | 25 August 2009 |
| Title: | ALLERDALE/COPELAND/CARLISLE REVENUES AND BENEFITS SHARED SERVICES DRAFT BUSINESS CASE |
| Report of: | Director of Corporate Services |
| Report reference: | CORP37/09 |

Summary:

This report asks members to scrutinise the draft business case agreed in principle by the Project Board on 29 July 2009 (Business Case attached at Appendix A) before it is considered by the Executive on 1 September 2009.

Questions for / input required from Scrutiny:

In scrutinising the draft business case the Resources Overview and Scrutiny Panel is requested to consider it against the principles set out in the Council’s shared services policy agreed by Council on 6 March 2007 (and Corporate Resources Overview and Scrutiny on 7 December 2006 and 11 January 2007).

Recommendations:

Members are asked to:

- Scrutinise the preferred option set out in the business case, i.e. ‘Joint Service Delivery’.  The results of the consultation and external verification exercises to date being subject to an addendum to the report to be circulated at the meeting.

- Note that the proposals set out in the report will deliver savings of £120,000 per annum with estimated set up costs, i.e capital, termination and protection costs of £160,000 being paid back in1.6 years.

- A supplementary estimate will be required to fund the up front cost currently estimated at £160,000.

| Contact Officer: | Peter Mason | Ext: | 7270 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	The Executive							CORP 37/09

1st September 2009

ALLERDALE/COPELAND/CARLISLE

REVENUES AND BENEFITS SHARED SERVICES

DRAFT BUSINESS CASE

- Introduction

1.1	As members will be aware from regular newsletter briefings, Carlisle, Allerdale and Copeland have been undertaking detailed investigations on whether there is a business case for a shared Revenues and Benefits Service encompassing the three authorities.

1.2	The project initiation document (PID), produced in July 2008, set out the principle drivers for merging the three councils’ Revenues and Benefits Services: -

- Increased capacity and capabilities delivering economies of scale.

- Reduced ongoing revenue costs for the three councils.

- Improve service performance for the councils’ customers.

- Taking advantage of the fact that Carlisle and Copeland councils use Capita (Academy) / Northgate’s Information@Work operating systems to administer Revenues and Benefits and Carlisle and Allerdale’s joint ICT service.

- Builds upon the management/support arrangements already successfully implemented in Carlisle providing operational management of Copeland’s Revenues and Benefits service.

- Takes full advantage of the recently implemented Carlisle/Allerdale shared ICT service in aligning hardware, software and operating systems.

- Provide a model for future shared ‘transactional’ service initiatives.

1.3	A Project Board was set up to include the relevant Directors and Service Heads from each of the 3 authorities (supported by practitioner groups) with the terms of reference to progress the actions set out in the PID in producing a Revenues and Benefits Business Case (i.e. delivering the outcomes as set out in 1.2 above) for member consideration.

1.4	This report asks members to consider the draft Business case agreed in principle by the Project Board, on the 29th July 2009 (see appendix A).

- Shared Services Policy

2.1	The draft business case adheres to the Council’s shared service policy agreed by the Council on 6 March 2007, i.e.

- it benefits the citizens of Carlisle district in that it maintains/ improves current service provision at reduced cost;

- organisational cultures and priorities and legitimate variances in local operating environments of the Council are respected, e.g. maintaining different discretionary rate relief scheme and ringfencing customer contact (front office) resources;

- costs, risks and benefits will be shared on an agreed and equitable basis (still to be finalised);

- clear governance and scrutiny arrangements will be put in place to include a process to resolve disputes etc (likely to be similar to ICT shared service governance arrangements);

- common agreement to consult and involve employees on job protection arrangements will be progressed within Phase 1 of the business case;

- the identity of Carlisle City Council will be clearly linked on all documentation etc in administering Revenues and Benefits service.

3.	Key issues supporting the business case for and Allerdale/Copeland/Carlisle shared Revenues and Benefits Service.

3.1	Delivery of required outcome

The business case evidences compelling reasons why Allerdale, Copeland and Carlisle should agree a Revenues and Benefits Shared Service i.e.

- Increased capacity in delivering economies of scale at a time when the three Councils, individually, are being required to make significant cuts in back office resources and expenditure.

- Delivering further ongoing revenues savings to the three Councils over and above what has already been taken out of base budgets in 2009/10/11

- Improves service performance for customers by ‘ring fencing’ customer-facing staff at current levels and locating all front office revenues and benefits staff within the three Councils’ customer contacts centre arrangements.

- Future proofs the service in having the capacity to deliver new benefit KLOE’s, resource the impact of the recession (earmarked Government grant may be utilised) etc.

  - Service Delivery Arrangements

3.2.1	Out of the 4 Service Delivery Options considered (see Appendix A Pages17-36) Joint Service Delivering was assessed as providing the best service delivering arrangements for the 3 Councils based on Impact Assessment, Cost/Benefit Analysis, Human Resources, Governance and Risk Criteria.

    - In summary “a joint service” envisages a joint service across the three authorities with one being the employing Council. There will be a single management structure but staff undertaking actual Council Tax, NNDR and Housing Benefits administration and assessment work will be based at each of the 3 Councils ie. the bulk of staff below management level will continue to work in their current work locations. However staff of all 3 sites will work to identical practices and procedures and work on all three Councils work throughout. Obviously further rationalisation of service delivery will increase over time as staff turnover opportunities are taken advantage of.

    - The proposed shared services organisational structure, i.e. management structure based on other successful shared services and work throughput based on top quartile benchmarking data, suggests a staffing establishment of 124 FTE staff.  This is a reduction from the current staffing establishment, across the three Councils, of 11.51 FTE: mainly in management and support posts i.e.

|  | Current | Proposed |
| --- | --- | --- |
| Functional Area | Total |  |
| Managers (Heads of Service) | *1.00 | 1.00 |
| Managers (Locations/Teams) | 8.00 | 3.00 |
| Team Leaders | 14.70 | 12.00 |
| Senior Officers | 8.48 | 10.00 |
| Officers | 80.91 | 79.00 |
| Assistants | 22.42 | 19.00 |
|  | **135.51 | 124.00 |

* Only Carlisle’s Head of Service allocates more than 50% of their time to Revenues and Benefits administration.

** Note – Allerdale reduced their establishment by 5.39 during the preparation of the business case in taking savings of £119,500 in advance of the shared service.  This has been taken into account when determining the savings apportionment.

3.3	ICT Arrangements

A measure of success for a shared Revenues and Benefits service is the requirement for all three Councils to be on the same ICT infrastructure software and operating systems.  The business case reflects all three Councils operating Capita (Academy) Revenues and Benefits software (change for Allerdale) and Civica’s (ex Comino) DIP/Workflow operating system (change for Carlisle and Copeland).  The proposed ICT solution not only meets the proposed Revenues and Benefits shared service requirements but also provides the three Councils with greater disaster recovery resilience and the networking infrastructure between the three Councils to support future shared services initiatives.

4.	Issues still to be addressed

4.1	The business case is robust enough to support the recommendation that the shared  service case should be progressed, however there are a number of issues still to be finalised.

4.2	External Verification

The assumptions set out in the business case are still subject to independent scrutiny and challenge by Meritec, expert consultants engaged by the Project Board for the purpose.  Early feedback suggests that there are no major issues.  However Meritec suggest that the implementation timescale is very ambitious and that the shared service might need to be phased over a longer time frame. Meritec’s observations will be presented via an addendum to this report when received.

4.3	Redundancy and Protection costs

These cannot be determined accurately until staff have been assimilated into the new structure. The worse case scenario suggests redundancy costs in the region of £415,000 (up to 5 staff).  Also, protection costs of £11,000 have been included for the 2010/11 financial year.

4.4	Employing Authority

The employing Authority has not yet been determined.  Selection criteria

is currently being set out based on the ICT shared service criteria but taking account of lessons learnt.  This issue will need to be addressed urgently once the draft business case has been considered by the 3 authorities.

5.	Financial Summary Carlisle

5.1	The estimated Revenue and Capital costs/savings for Carlisle City Council are summarised below and set out in detail at Appendix 1.

Capital (2009/10 & 2010/11)				£000

Cost of DIP/Workflow					 188

Funded by earmarked funds in capital programme	(155)

Balance to be funded by Benefits Grant			  (33)				Revenue (non-recurring)

Termination Costs (est)					 160

Revenue (recurring)

ICT Revenues savings					  (34) pa (see note)

Staffing savings						(150) pa

Total savings							(184)

Already taken account of as part

of the transformation restructure				  (64) pa

Net savings							(120) pa

Note – Ongoing ICT revenues costs are still being finalised and savings could reduce in this respect

  - It should be noted that the split of costs, savings and termination costs is subject to final agreement.  Currently the allocation is:

Allerdale		Carlisle		Copeland

%			%			%

Capital (ICT)		33 1/3			331/3			331/3

Revenue

- Staff Savings	35			37			28

- Staff Redundancy	35			37			28

and Protection

  - Pay Back

In delivering the shared service savings of £120K pa, the Council will incur additional capital costs of £33,000 and termination (redundancy) and protection costs of £160,000 approx giving a payback period of approx 1.6 years.

  - As indicated, costs of redundancy have been estimated in the business case.  A supplementary estimate will need to be approved to fund up-front costs (to be ‘repaid’ from ongoing revenue savings).

- Consultation

6.1	Consultation with Customers

The three Councils have consulted with their Council Tax and Benefits customers on the service currently provided.  The results suggest: -

- Council Tax and Benefit customers very satisfied with service i.e. satisfaction rates averaging 90% but unemployed residents likely to make most use of Council services did not complete questionnaire in significant numbers (only 5%).

- They like the traditional methods of contact i.e. in person, phone and by letter.

- A challenge for the shared service will be to promote ‘e’ contact as current usage is less than 3%.

- Major challenge to maintain current satisfaction levels.

  - Consultation with Staff and Unions

The project Board have kept staff and local union representatives informed on the progress of the shared service business case.  Formal staff presentations commenced, on the draft business case, on the 31st July 2009 with responses required by the 31st August 2009: on the main issues set out within the business case.  An email address has been set up for staff to provide comments.  Feedback on issues like individual staff terms and conditions etc. will be part of the initial shared services implementation work (Phase 1).

- Phase 1 Implementation – Appointment of Programme Manager

  - In following ‘Best Practice’ of other large scale shared service initiatives nationally, Phase 1 of the migration to the Carlisle/Allerdale/Copeland shared Revenues and Benefits service requires the appointment of the Programme Manager in November 2009.

  - Subject to the shared service being successfully implemented, the duties of this post will move over time to those of the RBS Partnership Manager.  In the circumstances the post may be subject to competitive recruitment.

  - During the period 1 November 2009 to 31 March 2010, the Programme Manager will be responsible for:

- delivering Phase 1 actions as set out in Business Case;

- taking the ‘Senior User’ role on the 6-9 month Revenues and Benefits software and operating system implementation;

- finalising the work being progressed on the unification of policies, practices and procedures to be followed by shared service operation (also where policies cannot be unified, e.g. Discretionary Rate Relief, payment facilities);

- finalising and initially implementing of new structure including:-

- production of job descriptions

- JE process

- assimilate terms and conditions (based on lead authorities’ current terms)

-    detailed Implementation plans for assimilating staff into new

structure

- finalising governance arrangements;

- produce shared services direct costs budget projections for 2010/11 budget cycles within 3 authorities (urgent) including identified savings;

- co-ordinate consultation with stakeholders, including staff;

- ‘draft’ reports for Project Board, Senior Management Teams and Executives on progress, issues needing strategic decisions, and final report on shared services implementation (January/ February 2009);

- make all day to day operational decisions in progressing the shared service business case;

- make recommendations to Project Board on strategic issues requiring Project Board sanction.

7.4	In summary, progress business case outcomes with the view of having the 3 councils’ Revenues and Benefits service managed as a shared service from 1 April 2010 with new ICT software and operating systems targeted for implementation by 30 June 2010.  However a phased implementation may be required due to the very tight timetable set out in business case.

  - The Programme Manager will be supported directly by a Project Officer, HR and administrative support.  The Programme Manager will be able to call on the assistance/expertise of Human Resources, Financial, Legal, ICT and Revenues and Benefits practitioners from the 3 Authorities in progressing Phase 1 of the business case.  Additional resources may need to be procured/funded from base budgets.

7.6	Cost of delivering Phase 1 November 2009 to March 2010 (including oncosts)

£

Programme Manager (5 days per week)		26,000

Project Support (2 days per week) 		  6,500

Travel and Subsistence				     500

______

Total							33,000

The Phase 1 costs amounting to £11,000 per authority will be financed by current Revenues and Benefits 2009/10 base budgets.  If Carlisle’s Head of Service is appointed to this role there will be an impact on the management of Carlisle’s current service.  However the same issue will need to be addressed under Carlisle’s own management restructure.

8.	Recommendations

  - Members are asked to:

- Support the Project Board view that the preferred option in the Business Case, ‘Joint Service Delivery’, be agreed.  The results of the consultation and external verification exercises to date will be circulated as an addendum to the report before the meeting.

- Note that the proposals set out in the report will deliver savings of £120,000 per annum with estimated set up costs, i.e capital, termination and protection costs of £160,000 being paid back in1.6 years.  This £160,000 will be subject to a supplementary estimate later in the decision-making process.

- Reasons for Recommendations

The approval of the business case will mean that the implementation phase of the development of a shared Revenues and Benefits service with Allerdale and Copeland Borough Councils can commence resulting in an improved service at a lower overall cost to all 3 councils.

- Consultation

  - Consultation to Date with customers is set out in para 6 of the report.

  - Consultation proposed.

We are now undertaking a period of consultation with staff, members and other users.  The consultation with staff and their representatives will last until Monday 31st August and the business case will be available on each Council’s intranet/website.

11.	Implications

- Staffing/Resources –  Addressed within the business case

- Financial – Addressed within the business case

- Legal – The Council has a number of powers upon which it may rely to enter into a shared service including the exclusive rights given to local authorities to undertake administrative arrangements of this nature in sections 101, 102, 112 and 113 of the Local Government Act 1972, and sections 19 and 20 of the Local Government Act 2000 and the regulations made under these Acts; together with the general power within section 2 of the Local Government Act 2000 and the supporting provisions within section 111 Local Government Act 1972.  In utilising section 2 of the Local Government Act 2000 the Council must have regard to its community strategy.

- Corporate – SMT have been consulted on the shared service initiative and any observations have been incorporated within the business case.

- Risk Management – Addressed within the business case, main issues being:

- Tight timescale may require phased implementation;

- Likely short term downturn in performance;

- ICT infrastructure delays, particularly networking, considerations may delay introduction;

- Shared service model proposed, i.e. making savings at management level and rationalisation of ICT, is untested elsewhere in local government (other shared services have made savings in processing staff rather than at management level);

- Competing initiatives may result in capacity issues, e.g. ICT shared service transformational agenda.

- Equality Issues – None.

- Environmental – The proposed joint service delivery option enables the bulk of staff to continue to work in their current work location avoiding an increase in the use of private transport to travel to new office locations.

- Crime and Disorder – None.

- Impact on Customers – Improved Service envisaged in performance requirements, albeit there may be a drop in performance whilst the new services is being set up.

ANGELA BROWN

Director of Corporate Services

| DRAFT |
| --- |
| Allerdale / Copeland / Carlisle revenues and benefits - SHARED service BUsiness case |
| Version: | V0.4k |
| Authors: | Practitioner Team |
| Date: | 4th August 2009 |

Version Control

| Version | Date | Author | Comment |
| --- | --- | --- | --- |
| 0.1a | 21/10/08 | SDC | Basic draft document structure established. |
| 0.1b | 28/10/08 | SDC | Changes following Ops Board 24/10/2008 |
| 0.2a | 06/03/09 | SDC | Version 0.2a – major revisions |
| 0.2b | 09/03/09 | SDC | Changes following Practitioner Team Meeting 6/03 |
| 0.2c | 21/04/09 | SDC | Changes following Practitioner Team Meeting 17/04 |
| 0.2d | 7/05/09 | SDC | Changes following Practitioner Team review 29/4/09 |
| 0.2e | 14/5/09 | SDC | Changes following Practitioner Team Review 8/5/09 |
| 0.2f | 1/6/09 | SDC | Changes following Practitioner Team Review 9/6/09 |
| 0.2g | 19/6/09 | SDC | Changes following Practitioner Team section drafts |
| 0.2h | 1/7/09 | SDC | Changes following Practitioner Team Review 1/7/09 |
| 0.2i | 16/7/09 | SDC | Changes following Project Board discussions and follow-up (and changes for meeting on 22nd July) |
| 0.2j | 24/07/09 | ST | Changes following Practitioner Team review |
| 0.2k | 31/07/09 | ST | Amendments and update following Project Board |
| 0.2l | 04/07/09 | MT | Finance Changes |

Table of Contents

Version Control	15

Table of Contents	16

Acknowledgements	19

1	Executive Summary	20

1.1	Conclusion and Recommendation	20

2	Introduction	21

2.1	The Wider Shared Service Context	21

2.2	Context of this business case	22

2.3	Project Objectives	23

2.4	Project Scope	23

2.5	Project Background	23

2.6	Project Approach	24

2.7	Project stages	25

2.8	Current organisational structures	27

2.9	Revenues and Benefits customer consultation	27

3	Analysis of Shared Service Options	32

3.1	Potential shared service delivery options	32

3.2	Option analysis approach	32

4	Analysis of Option 1 A revenues and benefits service hosted externally (outsourcing)	34

4.1	Impact assessment	34

4.2	Cost/benefit analysis	34

4.3	Human resources implications	35

4.4	Governance implications	35

4.5	Risk analysis	35

4.6	Overall conclusion	35

5	Analysis of Option 2 Enhanced single council service delivery	37

5.1	Overview	37

5.2	Impact assessment	37

5.3	Cost/benefit analysis	38

5.4	Human resources implications	39

5.5	Governance implications	39

5.6	Risk analysis	39

6	Analysis of Option 3 Authorities outsource all revenues and benefits service to another	41

6.1	Overview	41

6.2	Impact assessment	41

6.3	Cost/benefit analysis	42

6.4	Human resources implications	42

6.5	Governance implications	43

6.6	Risk Analysis	43

7	Analysis of Option 4 Joint service delivery	44

7.1	Overview	44

7.2	Impact assessment	44

7.3	Cost/benefit analysis	44

7.4	Human resources implications	45

7.5	Governance implications	45

7.6	Risk Analysis	45

8	Evaluation summary	46

8.1	Impact Assessment	46

8.2	Cost / Benefit Analysis	47

8.3	Human Resources Analysis	47

8.4	Governance Analysis	48

8.5	Risk Analysis	48

8.6	Assessment Summary	49

8.7	Weightings	49

8.8	Option Sensitivity Analysis	51

8.9	Recommendation	51

9	Preferred Option – Joint Service Delivery	52

9.1	Governance Arrangements for the Shared Service	52

9.2	Proposed Organisation Structure	59

9.3	Staffing Levels	60

9.4	Salaries and Terms & Conditions	61

9.5	Support Arrangements (Accountancy / HR / Legal / Project Management etc)	61

9.7	Human Resource Arrangements	68

9.8	Phased implementation of the shared service	70

9.9	Communications	73

10	Recommendations	74

11	Appendices	74

Acknowledgements

This business case has been prepared using the valued contributions of many key individuals within all three organisations.

Particular thanks must go to the work package leaders and team members who have put a great deal of effort in to considering the technical, organisational and financial aspects of their designated specialist areas. Their output has provided the crucial detail required in producing this business case.

Thanks go to the support services – Finance, HR and ICT - for their valued input and the huge amount of work and analysis completed. Special thanks to Mike Thompson for his time, effort and patience and to Stephen Cawley for his project management skills in keeping everyone on track.

1	Executive Summary

This business case is the result of an extensive exercise to examine the options for the future delivery of a shared revenues and benefits service for Allerdale Borough Council, Copeland Borough Council and Carlisle City Council.

The brief to the project team was to determine the viability of a shared service as well as defining the best vehicle for accomplishing this.  The project team was tasked with exploring whether a shared service would result in:

- Increased capacity and capabilities delivering economies of scale;

- Reduced ongoing revenue costs for the three Councils;

- Improved service performance for the Councils’ customers;

- Taking advantage of the fact that Carlisle and Copeland Councils already operate a shared management service for revenues and benefits and Carlisle and Allerdale have recently established their ICT shared service.;

- The provision of a model for future shared ‘transactional’ service initiatives.

Overall, the project team were also asked to consider whether the development of a shared service would result in a more advanced service, in a shorter time, at a reduced cost, as opposed to continuing the service as three separate functions.

The implementation phase for a revenues and benefits shared service will be addressed as a subsequent project only after any approval to proceed with the recommended option has been given by all the respective Councils.

An independent external review of the draft business case has been undertaken by Meritec Limited  Their review concluded that (being undertaken during consultation period).and their comments and recommendations have been taken into account in the production of this final version of the business case.

1.1	Conclusion and Recommendation

The recommendation made in this final business case is for the joint service delivery of revenues and benefits by the three councils. The final conclusions will be made after consultation and external verification.

.

2	Introduction

2.1	The Wider Shared Service Context

It is now clearly understood and accepted that local authorities need to become much more efficient and effective in the targeted use of their resources (including staffing and finances) in order to provide services to their customers.

The bottom line is that this ultimately means doing more, or at least the same, for less.  This can only be done by transforming the way we go about providing our services.

Reports such as Gershon and Varney highlight the clear benefits that can be gained from sharing services across the UK public sector and highlight that experience from the private sector shows that typically corporate shared services can deliver efficiencies of up to 20% dependent on how high the staff to workload ratio is.

This all said, it must be noted that local authorities should not simply be developing shared services for the sake of it on the back of such reports, but that they should carefully consider what they want to achieve and then design the most effective partnership operations to deliver those objectives.

From the Cumbrian perspective, all local authorities in Cumbria have recognised the need to, and more importantly the benefits of, working together more closely and are developing plans and strategies to exploit this potential. There have been good examples of shared working across Cumbria, however, until recently most examples have been based upon joint procurement rather than actual joint delivery of services.  For example, there was a significant initiative during 2007 to explore the potential for the creation of a shared ICT service countywide.  Many of the principles established during that exercise were sound, however the project ultimately failed to progress for several reasons, such as the uncertainty over Local Government Reorganisation at the time and fundamentally due to the difficulty of bringing such a large number of organisations, with differing objectives and starting points, together.

Nevertheless, since that time Allerdale and Carlisle have since successfully collaborated to introduce their ICT Shared Service – now branded as ictConnect – and the new service is operational and starting to deliver savings and efficiencies.  Elsewhere in the county, Cumbria Improvement and Efficiency Partnership - CIEP - have initiated projects that will develop more shared working within its partner organisations and will promulgate best practice in this area.

2.2	Context of this business case

This business case examines how any future shared revenues and benefits service of Allerdale Borough Council, Copeland Borough Council and Carlisle City Council can best address the skills, capacity, and cost needs of all three organisations. The proposed service will also be designed to address the principle drivers as identified at the project initiation stage and reiterated later in this business case.

Revenues and Benefits sections play a very important part in the delivery of service and the collection of taxes for all three authorities.  They are very much part of the front line customer service provision and yet have strong links throughout each authority to key support functions such as finance, enforcement, electoral registration and others.  External partnership working with the Department for Work and Pensions and Citizens Advice Bureaux, as well as external verification and auditing, make these services very regulatory in nature and sometimes difficult to change given the nature of the legislative framework.

The duties and activities of these sections are predominantly the same across the three authorities.  The work undertaken earlier in 2009 by this project to harmonise working procedures (referenced later in this business case) as a precursor to shared service working has helped remove unnecessary local variation.  However, significant differences in terms of core systems, customer service delivery, discretionary rebates, document management, etc, remain.  All councils provide a front line local service but this is managed in different ways.  Notably, there are currently different IT systems deployed to support the delivery of these services at each authority.  Document management for both services at Allerdale is provided by a corporate document management team using a corporate system, Comino (Civica).  Carlisle and Copeland both use Northgate’s information @Work for document management, which is for the Revenues and Benefits sections only.  Allerdale uses Northgate’s Pericles system as their core revenues and benefits system, Carlisle and Copeland both use Capita’s Academy system.  There are significant challenges for the authorities in addressing these ICT system disparities and this area is covered in detail below.

Costs of delivering the services also vary between councils, for example, the budgeted cost of service per resident in 2008/09:

Carlisle	£19.41

Copeland	£22.49

Allerdale 	£20.66

A full analysis of service cost comparisons, both between the three authorities and against other marker authorities across all country has been undertaken and this is examined in detail as part of the option analysis below.

2.3	Project Objectives

The project objective, as identified in the Project Initiation Document, was to investigate the potential options for a shared service for revenues and benefits and to develop a business case for the creating and sustaining a shared service across the three councils.  This business case is based upon this detailed consideration of the potential for the future shared delivery of the revenues and benefits service across the three councils. It is intended to be issued for consultation to all stakeholders and then to be considered by corporate management and elected members at Allerdale, Copeland and Carlisle.

The principle drivers for the consideration of the transformation of the three councils’ current revenues and benefits service into a single shared service include:

- Increased capacity and capabilities delivering economies of scale.

- Reduced ongoing revenue costs for the three councils.

- Improved service performance for the councils’ customers.

- Taking advantage of the fact that Carlisle and Copeland councils already operate a shared management service for revenues and benefits and Carlisle and Allerdale have recently established their ICT shared service.

- The provision of a model for future shared ‘transactional’ service initiatives.

2.4	Project Scope

The scope of this project included consideration of the requirements of the following services for Allerdale, Copeland and Carlisle:

- Council Tax Administration.

- Business Rates Administration (NNDR).

- Housing and Council Tax Benefits Administration including overpayment recovery and fraud.

- User technical support.

- IT support for the revenues and benefits systems and interfaces

2.5	Project Background

In recent years, both Carlisle and Copeland have successfully collaborated on revenues and benefits management and technical support initiatives. Since September 2007, the two councils have worked together, with Carlisle  providing management, technical and back office support both in situ at Copeland and by remote link. Following the approval of their joint ICT business case last summer, Carlisle and Allerdale have also introduced their shared service.

2.6	Project Approach

In 2008 a project was approved to explore the potential of creating a single shared service for revenues and benefits serving the three councils and to determine whether a business case exists for the introduction of such a shared service.

To undertake this, a joint project board was created and a project structure put in place.  A project brief was agreed in the form of a project initiation document (PID) and an initial project phase was undertaken to consider a range of topics referred to as work packages.  These work packages included both revenues and benefits functional areas as well as central services, as follows:

Functional area work packages:

- Council Tax Administration

- Business Rates Administration (NNDR)

- Recovery

- Housing and Council Tax Benefits

- Fraud Prevention, Detection and Deterrence

- Benefits Overpayments

- Appeals, Discretionary Rebates, Section 44As

- Customer Interface, Contact Centre

- IT Support/User Technical Support

Central and support services work packages:

- Communications

- Finance / Budgets

- Organisational Structure

- Human Resources

- Governance / Legal

Work packages were led and resourced by a mix of key staff from each council.  In addition, a practitioner team was formed comprising the service heads and senior revenues/benefits managers from the three authorities and has dealt with the overarching project tasks and provided functional guidance to the work packages.  This business case has been developed internally by the project practitioner team, with assistance from the project manager.

A full risk analysis has been undertaken and a risk log held.  These are shown at Appendix 3.

The draft business case has also been externally scrutinised by Meritec who have provided a critical and independent review. Their comments and recommendations will be incorporated into the final business case.

This  business case has been endorsed by the project board, which includes executive directors from each of the three authorities. It is now submitted for consultation and review by each council, prior to seeking approval to move to the project initiation stage for the implementation of the recommended revenues and benefits shared service.

2.7	Project stages

The project to create this business case has been conducted over three distinct phases, as follows:

2.7.1	Initial investigations phase.

The initial project phase ran from September to December 2008. In this initial phase, the functional work packages undertook detailed evaluation of their respective areas, current service status and costs, the potential benefits and risks of introducing a shared service, and the viability of each of the four potential shared service delivery options in their area.

In addition, the central and support services work packages gave consideration to the implications of a shared service, for example in terms of human resources implications and governance arrangements.

In December 2008, an external review of the initial phase functional work package analysis work was conducted by Meritec Ltd (experienced revenues and benefits management consultants), to introduce an element of external challenge.

A dialogue was also established with the WestWey partnership; WestWey is a partnership of Weymouth and West Dorset councils that has been operating a revenues and benefits shared service for several years.  A presentation was given by the WestWey Partnership Manager to the work packages and elected members in November 2008 that highlighted their experiences in introducing a shared service and the lessons they had learnt.

The inputs from both the Meritec review and the WestWey experiences referenced the advisability of completing certain pre-requisites before embarking on any new revenues and benefits shared service.  These were mainly in the area of harmonised procedures and practices, as well as the early introduction of a number of “quick wins” (small-scale shared service initiatives and improvements).  The recommendation was to accomplish as many of these “quick wins” as possible, and as much harmonisation of procedures across the three authorities as could be achieved, prior to putting together any detailed plans for a shared service – including the preparation of a business case.

2.7.2	Procedure harmonisation and “quick wins” phase.

In December 2008, plans were produced and subsequently approved by each council to embark upon a further phase of the project to deliver the “groundwork” as recommended in the initial phase as above.  This second phase covered the period January-March 2009, during which the functional work packages (Benefits, Overpayments, Council Tax, NNDR, Recovery and Fraud) each worked on (a) the delivery of a limited number of “quick win” improvements and (b) the harmonisation of revenues and benefits procedures across the three authorities. This information is shown at Appendix 2.  Specialist external expertise from ACS Ltd (recognised experts in revenues and benefits procedures and publishers of on-line manuals) assisted the teams in creating standardised sets of procedures for the three authorities.  These standardised procedures are being adopted at each authority and will provide a sound base should approval be given to a shared service implementation.

2.7.3	Business case production.

Following the above phases, work on the production of this business case started in April 2009.  In addition, in May 2009 a tender exercise was conducted to evaluate the core revenues and benefits software and the outcome of that exercise has been incorporated into this business case and appendices.  The draft business case was referred to Meritec for an independent external review during August 2009 and their feedback was taken into account, (this will be shown in the final business case after consultation).

During all the above stages communication with stakeholders has taken place. Regular member and staff updates have been provided in the form of project briefings and newsletters.  Consultation with all revenues and benefits staff in relation to the proposed structure has been conducted in August 2009 and all comments have been taken into account and noted for the final business case.

Whilst many of the arguments for the introduction of a shared service are economic and financial, it is vital to take into account the needs and opinions of all stakeholders and in particular the customers of the services.  To this end, an exercise was undertaken to establish the views of the customer community. A series of consultations and focus groups involving a cross section of the service’s “customers” took place to obtain their input to the proposed shared service approach.

2.8	Current organisational structures

The following table provides a summary of the current staffing levels at each Council in terms of full time equivalent (FTE) staff allocated to each of the current roles within revenues and benefits:

| Revenues and Benefits | Current FTEs – Revenues (comprising council tax and NNDR admin and recovery) Benefits (comprising council tax benefit, housing benefit, fraud and appeals) |  |
| --- | --- | --- |
| Functional Area | ABC | CBC | CCC | Total |
| Head of Service | 0.00 | 0.00 | 1.00 | 1.00 |
| Service Management/Senior Officers | 6.00 | 2.00 | 8.48 | 16.48 |
| Team Leaders | 3.70 | 5.00 | 6.00 | 14.70 |
| Officers | 21.69 | 28.52 | 30.70 | 80.91 |
| Assistants | 12.30 | 4.00 | 6.12 | 22.42 |
| Total | 43.69 | 39.52 | 52.30 | 135.51 |
| Functions included above: |  |  |  |  |
| Scanning and indexing | Yes | Yes | Yes |  |
| Corporate Customer Service centre staff | No | No | No |  |
| Debtors (raising and file maintenance) | No | No | No |  |
| Overpayments | Yes | Yes | Yes |  |

2.9	Revenues and Benefits customer consultation

2.9.1	Improved service performance for the Council’s customers

One of the main aims of the business case is to maintain/improve the service to Revenues and Benefits customers.  A major challenge whilst at the same time reducing ongoing revenue costs.

2.9.2	The Survey

As part of undertaking the necessary ground work supporting the business case, a major survey was progressed of 2,400 revenues and benefits customers selected at random (expected return rate for completed questionnaires 750 or 30%) within the 3 councils.

Actual returns (as at 27th July 2009):-

| Benefits | Number sent | Number returned | % |
| --- | --- | --- | --- |
| Carlisle | 400 | 152 | 38 |
| Allerdale | 400 | 149 | 37 |
| Copeland | 400 | 114 | 29 |
| Sub Total | 1,200 | 415 | 35 |
| Revenues |  |  |  |
| Carlisle | 400 | 99 | 25 |
| Allerdale | 400 | 37 | 9 |
| Copeland | 400 | 109 | 27 |
| Sub Total | 1,200 | 245 | 20 |
| Revs & Bens Totals | 2400 | 660 | 38 |

2.9.3	The questionnaires asked customers:

- How they contacted the Council, how often, how convenient the office is and opening hours;

- How they would prefer to contact the Council and be contacted by the Council;

- How satisfied with the service, the information provided and the way claim or account handled;

- How long they waited for a response to a change in circumstances;

- Other ad-hoc questions such as methods of payment, type of customer (benefits) and how benefit/revenues information obtained.

2.9.4	Results of, and observations on, the survey of benefits customers

2.9.4.1	The spread of responses from benefits customers suggests that unemployed and available for work claimants did not complete the questionnaires, i.e. 4% of responses compared to 33% approx of caseload.  This is disappointing as it is this group that have the most changes of circumstances and therefore the most likely to contact the Council.  The retired and permanently sick/disabled make up 90% of the responses.  This is probably why 5.5% of claimants suggest their recent benefit claim was their first ever claim.  You would expect that in the current recession this percentage would be higher.2.9.4.2	Unsurprisingly customers would rather continue to use traditional methods to contact the Council, i.e.

|  | Benefits | Revenues |
| --- | --- | --- |
| Face to Face | 35% | 26% |
| Phone | 34% | 60% |
| Post | 27% | 6% |
| Email | 2% | 8% |
| Online | 1% | - |
| Text Message | 1% | - |

Customers would still prefer the Council to contact them by post, i.e.

|  | Benefits | Revenues |
| --- | --- | --- |
| Post | 43% | 53% |
| Phone | 31% | 26% |
| Face to Face | 22% | 9% |
| Email | 2% | 10% |
| Online | 1% | 1% |
| Text Message | 1% | 1% |

The results suggest much more persuading needs to be done to get customers using electronic forms of contact (email, online or text), the most cost-effective and away from face to face and telephone contact.  The fact that post is the most popular method for the Council to contact customers would suggest that the Council should use this method more for district inspections/other visits.

2.9.4.3	Overall, benefit customers are surprisingly satisfied with every aspect of the benefits service and revenues customers reasonably satisfied.  On ‘national’ benefit surveys 80%+ satisfaction rates are well within ‘top quartile’.  On responses to particular questions (not answered discounted):

| Front Office (mainly) | Benefits | Revenues |
| --- | --- | --- |
| - Opening hours convenient | 92% | 95% |
| - Able to ask questions about claim | 86% | - |
| - Satisfied with contact with Council | 92% | 93% |
| - Local office is easy to get to | 88% | 90% |
| (despite average journey being approx 4-5 miles) |
| Back Office (mainly) | Benefits | Revenues |
| - Very satisfied/satisfied on claim handled | 98% | 94% |
| - Found claim easy to complete | 82% | 94% |
| - Did not require help in completing form | 62% | - |
| - The information provided is clear and easy to understand | 89% | - |
| - Happy with payment methods | - | 95% |
| - Average length of time to get response | - | 7–10 days |

2.9.4.4	Other observations

It is surprising to note that very few claimants found out about entitlement to benefits from the Council, i.e. less than 20%.  Perhaps Council publicity on housing and council tax benefit entitlement needs improving.

No issues from a revenues perspective.

2.9.5	Impact of shared service proposals

2.9.5.1	Clearly it is a major challenge for the 3 councils to maintain such high satisfaction rates, whilst making significant cost and resource savings.

2.9.5.2	Whilst the shared service business case is suggesting a 9% reduction in back office revenues and benefits resources it has ring fenced front office/customer contact centre resources at current levels, i.e. no savings in customer facing staff are suggested.  Therefore there should be no reduction in ‘front office’ satisfaction performance.  Indeed the shared service proposals suggest that front office staff after extensive training will eventually be able to fastrack assessment of straightforward benefit claims (in meeting new benefits KLOEs).  There may be opportunities in the longer term to rotate of assessment staff between the front and back office to maintain up to date benefit assessment skills.

2.9.5.3	Economies of scale proposed in the business case suggest that current back office performance in respect of dealing with new claims and change in circumstances can be maintained (or possibly improved further).  However with such high satisfaction rates, performance monitoring of claimant related performance indicators will need to be closely monitored.

3	Analysis of Shared Service Options

3.1	Potential shared service delivery options

The project board considered the potential shared service options available and agreed to review the following:

| No | Service Delivery Option | Overview |
| --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | Revenues and benefits services delivered by an external company (or a council joint venture/not for profit company) under a commercial contract, controlled jointly by the three authorities. |
| 2 | Enhanced single council service delivery | Provision remains largely as it is now, but tactical opportunity is taken to enhance service delivery or deliver efficiency gains by learning from other councils’ initiatives. |
| 3 | Authorities outsource all revenues and benefits service to another | With this option a single authority becomes the provider, manager and controller of revenues and benefits services to the three parties with a purchaser and provider relationship with the outsourced authorities. The authorities giving up their services would have no management responsibility for revenues and benefits (other than ‘client’ responsibilities). All staff and assets would transfer to the provider authority. |
| 4 | Joint service delivery | Revenues and benefits services delivered by a single management structure with different aspects of the service hosted within the three authorities for administrative purposes and controlled jointly by the three authorities. |

3.2	Option analysis approach

Each option as above has been considered by the project teams. This analysis has included the following range of assessment criteria:

Impact assessment - the positive impact that each service delivery option would make towards achieving the key drivers established at the project initiation stage:

- Increased capacity / capabilities delivering economies of scale;

- Improved service performance for councils’ customers;

- Taking advantage of the fact that Carlisle and Copeland councils already operate a shared management service for Revenues and Benefits and Carlisle and Allerdale have recently established their ICT shared service.

- The provision of a model for future shared transactional service initiatives.

Cost/benefit analysis - the overall implementation costs for each option together with the IT Costs and the anticipated annual revenue cost reduction and financial benefits.

Human Resources implications - an assessment of the overall level of human resources effort required, complexity or arrangements, and service disruption that would be caused by adopting the specific option.

Governance implications - in terms of the effort and complexity of setting up a new service delivery model, including appropriate legal and contractual activities.

Risk Analysis - assessment of the high level risks associated with the service delivery option, covering service risk, financial risk and reputational risk.

There follows the analysis results for each of the potential shared service options based upon the above assessment approach, followed by a summary and a recommended option for shared service.  The later sections of the business case then expand on the recommended option, in terms of its financial case and how the shared service will be implemented.

The option analysis for the potential to outsource revenues and benefits was progressed by the practitioner team rather than work package teams to avoid any conflict of interest.

A scoring methodology was applied (with 0 being least positive and 3 being most positive) to each area, and then combined with appropriate weightings to give an overall view of each preferred service delivery option.

4	Analysis of Option 1 
A revenues and benefits service hosted externally (outsourcing)

4.1	Impact assessment

This option, providing the tender specification is robust, will satisfy any capacity issues currently being experienced by the three councils, e.g. Copeland’s problem in recruiting senior revenues and benefits practitioners.

Obviously economies of scale could result for the winning tenderer.  How much of this is passed back to the three councils in efficiencies (reduced service costs) would not be known until tenders returned (plus any post tender negotiations).  However the attached paper (see Appendix 1) produced for the project board on 21 October 2008 and updated on 15 April 2009 suggests that the cost of outsourced revenues and benefits services is significantly more expensive than both in-house and shared service provision.

Scoring:

(i)	Increased capacity / capabilities delivering economies of scale – 
Score = 2

(ii)	Improved service performance for councils’ customers – 
Score = 1

(iii)	Taking advantage of the fact that Carlisle and Copeland councils already operate a shared management service for revenues and benefits and Carlisle and Allerdale have recently established their ICT shared service – 
Score = 0

(iv)	The provision of a model for future “transactional” service initiatives – 
Score = 2

4.2	Cost/benefit analysis

The direct costs associated with this option are minimal, mainly costs associated with the tender specification.

However, indirect costs are significant in that currently the 3 councils recharge well in excess of £2m to revenues and benefits in ICT, legal, finance, property costs etc.  Past experience suggests that a significant portion of such recharges cannot be extinguished and will need to be absorbed by the 3 councils.  Also client costs, i.e. those parts of the service that cannot be outsourced, including discretions, committals administration, appeals and performance monitoring etc, will also need to be factored into the cost/benefit analysis.  It is assumed that client costs are included in the benchmark data noted at Appendix 1 but recharges absorbed by other services are not.

An aspect not covered in this paper as could only be considered when tenders returned is what additional benefits (over and above Revenues and Benefits service provision) the outsourcing could bring to the Council, e.g. local jobs, site operation within vicinity etc.

Scoring:

(i)	It is likely that up-front implementation costs would be borne by the supplier – 
Score = 3

(ii)	IT costs would likewise be borne by the supplier – 
Score = 3

(iii)	However, as the supplier needs to recover the setup costs during the life of the contract as well as ongoing IT costs, the above analysis does not indicate any revenue cost reduction – 
Score = 1

4.3	Human resources implications

Likely to be similar resource implications for personnel as other options (excluding enhanced status quo).

Tenderers would require TUPE and pension information to be able to cost their tenders.

Once any outsourcing is complete, there would be little or no ongoing human resource requirements.  Although as stated above, personnel recharges would have to be absorbed by other services if savings in personnel resources could not be made.

Note possible TUPE of staff from recharged services would need to be considered in any outsourcing arrangements. Score = 1.5

4.4	Governance implications

The governance arrangements should be reasonably simple as the outsourced service is a contract and would follow normal contract procedure rules.

Obviously conditions would need to be built into the contract, i.e. indemnities (bearing in mind performance of some outsourced contracts), client arrangements in each of the 3 councils, contract arrangements, share of profits (over and above normal profits), termination arrangements, dispute resolution, assumptions and risks etc.  Obviously there are resource implications for legal and procurement teams if outsourcing is the preferred option. Score = 3

4.5	Risk analysis

The analysis of performance of outsourced Revenues and Benefits operations suggests that mitigation of the risk of high cost/poor performance needs tightly determining within contract specification, i.e. poor performance would result in service, financial and reputational risk (to the Councils).

Service risk Score = 1, Financial risk Score = 1, Reputational risk Score = 1.

4.6	Overall conclusion

Overall the service/cost benchmarking paper noted at Appendix 1 suggests that outsourcing revenues and benefits has not to date delivered cost savings or service improvements (in benchmarking terms).  In the circumstances it is suggested that this option is held in abeyance whilst other options are considered.  If a business case does not stack up for any of the other delivery options under consideration, the outsourced option could be revisited by any of the councils individually (or together).

5	Analysis of Option 2
Enhanced single council service delivery

5.1	Overview

The work package information collated at the end of 2008 appeared initially to prefer the option for enhanced single council service delivery.  Work groups commented that they had chosen this option because it was the cheapest or easiest to attain but that there were potentially other more beneficial options should they have the time to explore them.

Following on then to the quick wins phase and it has been evident, whilst there are some differences between working practices in the councils, a lot can be achieved by working together even if not as a shared service.  The work that has been conducted by ACS has provided a greater understanding of how processes and procedures could be aligned and this could be achieved without the need to bring all three departments together under a shared service.  In addition, the benefit of retaining three separate council functions would be no setting up costs, ability to retain own sovereignty and identity and retain existing staff.

However, the economic positions of each of the Councils has changed somewhat over the last year and given the budgetary constraints a status quo is not sustainable. Therefore remaining as three separate councils is still an option for discussion, but the fact is that change, certainly to reduce costs and provide a more effective and efficient service, is inevitable.

5.2	Impact assessment

(i)	Increased capacity/capabilities delivering economies of scale –  
Score = 1

Staying as 3 separate councils will not deliver economies of scale but with standardised procedures capacity and capability can be increased minimally. Scheme training delivered by a shared officer would contract training periods for new staff mitigating backlogs and the need for agency staff.

Standard procedures would also allow authorities to undertake VF checks and pre-processing where backlogs are localised, allowing the processing staff, at the individual authority to key cases quickly to the application software. Non processing officers’ procedures are less driven by application software and so, with standardised procedures, would have the flexibility to provide absence cover.

There is the opportunity to take advantage of joint training procurement, potential joint procurement of stationery etc, however this will not in itself provide for the budgetary requirements of each council or enhance delivery to the customer.

If, through the ICT shared service arrangements, Allerdale and Carlisle were to share systems and infrastructure, there could be an opportunity for some efficiencies on system administration and upkeep.  It may also allow for dealing with fluctuations in workload, backlog management and offer some enhanced customer service whilst still retaining existing council identities and resources.

This however would not assist Copeland and the majority of efficiencies required would still not be met by just sharing a system(s).

(ii) 	Improve service, performance for Council’s customer - Score = 1.5

If the quick wins around alignment of processes, procedures, procurement etc., were implemented there is the opportunity to provide a slightly enhanced service to the customer.  This would allow for customers to obtain generic advice and information from any of the three Councils and understand how their application would be dealt with.  The ability however for a customer to be able to have their application processed at any council office (e.g. Wigton customer going to Carlisle) would not be available, but EDMS links would allow forms and documents to enter the processing gateway promptly from any service access point and pre-processing checks to be conducted to same standard.

(iii)	Taking advantage of the fact that Carlisle and Copeland councils already operate a shared management service for revenues and benefits and Carlisle and Allerdale have recently established their ICT shared service. This option would add nothing new to the current situation.  Only if two or more of the councils adopted the same revenues and benefits system could more efficiencies and effective working be obtained – Score = 1

Should the Copeland and Carlisle shared management arrangement dissolve then additional resource would have to be sought by Copeland to fulfil their management and supervisory requirements.  The original reason for sharing management was the inability to find sufficiently skilled and experienced officers in the area. This would be at additional cost.

(iv)	The provision of a model for future ‘transactional’ shared service initiatives - Score = 0

The three departments would remain separate however the quick wins noted above could still be applied and the small benefits achieved.

5.3	Cost/benefit analysis

Cost benefit of retaining three separate Council departments are:
Implementation costs - Score = 3

- No TUPE issues or staff redundancy costs, retention of existing skilled staff.

- Each Council could retain and service its existing customer base thereby managing the geographic, rurality and community issues.

- Ability for each Council to determine their own levels of service and delivery according to their budgetary constraints.
IT costs - Score = 1.5

- No system alignment and set up costs (Allerdale will still need to do this and the cost borne solely by the Council)

Reduced ongoing revenue costs - Score = 0.5

There are no potential economies of scale within this option and certainly no major savings to be made.  Each council would need to determine their own service delivery levels and reduce resource or standards as required to meet budgets.

There is still the matter of all councils providing a service in different ways, to different costs and standards.  There would be the opportunity to align processes and procedures without sharing but the real benefits, economies and efficiencies will only result from common applications software.

5.4	Human resources implications

Remaining as three separate council departments would have no human resource implications unless some of the quick win elements around joint fraud or visiting teams were to be implemented – Score = 3

5.5	Governance implications

As the status quo would in effect remain, there would be no governance implications for a new service delivery model.  Any enhancements around aligning processes, procedures or policies could be completed without the need to provide a different management model – Score = 3

5.6	Risk analysis

Service Risks – Score = 2

It was considered by the work packages that this option would have the least risks in terms of service delivery, finance and reputation as in effect all three councils’ services remain independent.

Given the current shared management arrangement between Carlisle and Copeland, additional risk would be that should this dissolve, recruitment of appropriate management and supervisory officers would be required and this has been very difficult in the past

KLOEs pose an additional risk in terms of their requirements on resourcing and relationships between the front and back office services.  Each council would need to spend time and resource to meet the new requirements rather than pooling resource and performance abilities

Financial Risk - Score = 1

There would be no large initial outlay (other than a new system for Allerdale) and ongoing costs would remain the same.  However, due to budgetary constraints for all three Councils it is unlikely that the current level of spending for each service could be sustained in the future. Therefore the financial risk is more to do with the inability to make savings to meet budget needs.

Reputational Risk - Score = 2

There would be no risk to losing skilled staff out of the area which was a concern of some elected members. However due to each Council’s budgetary constraints, it is likely that each would have to take a view on not replacing staff who leave in future.  This could lead to reputational issues both in terms of reduced performance, backlogs and inflexibility.

6	Analysis of Option 3
Authorities outsource all revenues and benefits service to another

6.1	Overview

It was established that none of the authorities had the capacity to deliver a combined service from their existing accommodation and there has been no detailed investigation into the availability of alternative accommodation. In addition there is a feeling that this option might meet with some political opposition.

In addition whilst combining three authorities would deliver cost savings in the long term the high cost of relocation would outweigh the benefits, certainly in the medium term. By relocating staff there would be a liability to cover the cost of travelling for an agreed period and the amount of travelling required would not meet the green agenda.

If Carlisle vacated its current accommodation it would be very difficult to let to a third party so it would either remain empty or other services would spread out increasing overall accommodation costs met by other services.

Copeland are tied in to a PFI arrangement for their accommodation for a further 21 years.

However shared service operations of up to 300,000 population (Allerdale, Copeland and Carlisle) councils combined population approx 260,000) would appear to deliver cost savings when the volumes increase giving economies of scale.  See appendix 1.

When comparing performance in respect of collection rates, benefit turnaround times, accuracy, and customer satisfaction, shared services operations significantly outperform outsourced service delivery options.

6.2	Impact assessment

(i)	Increased capacity / capabilities delivering economies of scale – 
Score = 3

With all staff working on one site there would be an increase in capacity together with providing economies of scale. The increase would bring with it a level of resilience together with the ease of co-ordinating tasks, liaising with and management of staff. However the initial transfer would see a short term drop in service and could see a loss of trained staff who do not want to travel.

The larger organisation would be able to negotiate better costs for goods and services, for example IT systems, bailiff fees, stationery, printing etc.

(ii) 	Improved service performance for councils’ customers – 
Score = 2

Whilst working from one site would improve the consistency of the service it would also mean that the existing offices would lose expertise and support for front line services. However it could improve processes by building on best practices and streamlining procedures.

There would be a loss of local knowledge particularly important in the relationship between the Council and its debtors.

(iii) 	Taking advantage of the fact that Carlisle and Copeland councils already operate a shared management service for revenues and benefits and Carlisle and Allerdale have recently established their ICT shared service – this option would build on the existing arrangements but further extended to one shared management and IT arrangements for all three authorities, based on the new site Score = 3

(iv)	The provision of a model for future “transactional” shared service initiatives – if successful this model would provide a set of terms and conditions that could be adopted by future shared service arrangements. This could be through a venture company or a solution delivered by one authority. The costs of operating through a venture company would not include support charges but would be included in a Council led solution - Score = 3

6.3	Cost/benefit analysis

The overall implementation costs for each option together with the IT Costs and the anticipated annual revenue cost reduction and financial benefits.

Whilst no analysis has taken place, it is likely that the up-front implementation costs of securing accommodation for this option would be high and in addition to the cost of option 4.  Score = 1

The costs of IT could be slightly less than all three authorities sharing a system on three sites if less servers and licences were required but no analysis has been undertaken. Score = 3

Ongoing revenue costs would be slightly reduced but recharges for support services would still remain. Score = 2

6.4	Human resources implications

An assessment of the overall level of human resources effort required, complexity or arrangements, and service disruption that would be caused by adopting the specific option.

This option would require staff to relocate to accommodation that could be a number of miles away from their existing place of work and/or home. Not only would this incur some costs but would have a detrimental effect on the environment.

There could be potential to lose experienced staff as well as requiring a change to terms and conditions, with many issues to be resolved.

Working from home is not always an option but could be considered for some roles to alleviate some of the problems. However some travel to the office would still be required for meetings, training, etc.

Whilst this option would see a reduction in numbers of staff (and therefore cost) there would be resilience through the numbers of staff on one site. Score = 1.5

6.5	Governance implications

In terms of the effort and complexity of setting up a new service delivery model, including appropriate legal and contractual activities.

This option would require the three councils to enter into a contract with one authority becoming the service provider.  The contract would be the means whereby the shared service would be defined in terms of delivery, duration, modification and dispute resolution.  Score = 3

6.6	Risk Analysis

Assessment of the high level risks associated with the service delivery option.

Service Risk

It was considered by the work packages that this option would have a negative impact on performance, certainly in the short term through disruption and loss of experienced staff who were not willing to relocate. Score = 2

Financial Risk

This option would require a large investment in new accommodation as none of the authorities have capacity to take on the number of staff required. There would also be existing costs that could not be eliminated.  Score = 1.5

Reputational Risk

There would be minimal risk to the reputation as performance and customer satisfaction could be maintained and monitored through an SLA. Score = 3

7	Analysis of Option 4
Joint service delivery

7.1	Overview

When comparing performance in respect of collection rates, benefit turnaround times, accuracy, and customer satisfaction, shared services operations significantly outperform outsourced service delivery options.

This option would allow each authority to retain their existing accommodation but would require some negotiation of what service was to be delivered from which site.

7.2	Impact assessment

(i)   Increased capacity / capabilities delivering economies of scale –

The increase in staff numbers and streamlining of processes would bring with it a level of resilience together with the ease of co-ordinating tasks, liaising with and management of staff. However the initial transfer would be likely to see a short term drop in service.

The larger organisation would be able to negotiate better costs for goods and services, for example IT systems, bailiff fees, stationery, printing etc. Score = 3

(ii)	Improved service performance for councils’ customers –

By delivering a joint service the customer would benefit from an improved more efficient service whilst retaining expertise and support for front line services. In addition it could improve processes by building on best practices and streamlining procedures, work to align procedures has already started.

There would be no loss of local knowledge which is particularly important in the relationship between the Council and its debtors. Score = 3

(iii)	Taking advantage of the fact that Carlisle and Copeland councils already operate a shared management service for revenues and benefits and Carlisle and Allerdale have recently established their ICT shared service –

This option would build on the existing arrangements but further extended to one shared management and IT arrangements for all three authorities. Whilst the staff would remain on three sites managers would be peripatetic and IT could be centrally based on one site. Score = 3

(iv)	The provision of a model for future “transactional” shared service initiatives

If successful this model would provide a set of terms and conditions that could be adopted by future shared service arrangements. Score = 3

7.3	Cost/benefit analysis

The overall implementation costs for each option together with the IT costs and the anticipated annual revenue cost reduction and financial benefits.

The implementation costs would need to include provision for redundancy or early retirement in order to reduce the numbers of supervisors/managers and staff..  Score = 2

There would be some costs associated to IT if the servers etc remained on all three sites. However consideration should be given to hosting the systems on one site therefore savings could be generated. Score = 2.5

Ongoing revenue costs would be slightly reduced but recharges for support services could be absorbed. Score = 2

7.4	Human resources implications

An assessment of the overall level of human resources effort required, complexity or arrangements, and service disruption that would be caused by adopting the specific option.

There would be a requirement to change terms and conditions, with many issues to be resolved, but this option would allow staff to work from the most convenient office. Only the managers would be expected to travel between sites, therefore minimising the carbon footprint.

Working from home is not always an option but could be considered for some roles to alleviate some of the problems. However some travel to the office would still be required for meetings, training, etc.  Score = 2

7.5	Governance implications

In terms of the effort and complexity of setting up a new service delivery model, including appropriate legal and contractual activities.

This option would require the three councils to enter into a contract with one authority becoming the employer for the revenues and benefits service.  The contract would be the means whereby the shared service would be defined in terms of delivery, duration, modification and dispute resolution.  Each council would develop means whereby corporate governance and the involvement of elected members could take place.  Score = 1.5

7.6	Risk Analysis

Assessment of the high level risks associated with the service delivery option.

Service Delivery

The risk to service delivery is mitigated by the three councils delivering at each . Score = 2.5

Financial Risk

Financial risk is mitigated by joining up ICT solutions and resources to give flexibility and resilience  Score = 2

Reputational Risk

There would be minimal risk to the reputation as performance and customer satisfaction could be maintained. Score = 3

8	Evaluation summary

There follows a summary of each of the above assessment criteria

8.1	Impact Assessment

The following table provides a summary of the positive impact that each service delivery option would make to achieving the key drivers established at the initiation of the project initiation stage, with scoring based on the most positive impact achieving 3 points, reducing to 0 equating to no benefit:

| No | Service Delivery Option | Increased capacity / capabilities delivering economies of scale | Improve Service Performance for Councils’ customers | Take advantage of CCC/CBC using Academy & CCC/ABC IT shared services implementation | Provide a model for future “transactional;” shared services | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | 2 | 1 | 0 | 2 | 5 |
| 2 | Enhanced single council service delivery | 1 | 1.5 | 1 | 0 | 3.5 |
| 3 | Authorities outsource all revenues and benefits service to another | 3 | 2 | 3 | 3 | 11 |
| 4 | Joint service delivery | 3 | 3 | 3 | 3 | 12 |

8.2	Cost / Benefit Analysis

This assessment concentrates on the financial benefit, the overall implementation costs for each option together with the IT costs and the anticipated annual revenue cost reduction.

| No | Service Delivery Option | Implementation Costs | IT Costs | Reduced Ongoing Revenue Costs | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | 3 | 3 | 1 | 7 |
| 2 | Enhanced single council service delivery | 3 | 1.5 | 0.5 | 5 |
| 3 | Authorities outsource all revenues and benefits service to another | 1 | 3 | 2 | 6 |
| 4 | Joint service delivery | 2 | 2.5 | 2 | 6.5 |

8.3	Human Resources Analysis

This assessment concentrates on the human resources implications, the overall level of effort required, complexity or arrangements, and service disruption that would be caused by adopting a particularly delivery route.

| No | Service Delivery Option | HR Complexity |
| --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | 1.5 |
| 2 | Enhanced single council service delivery | 3 |
| 3 | Authorities outsource all revenues and benefits service to another | 1.5 |
| 4 | Joint service delivery | 2 |

8.4	Governance Analysis

This assessment concentrates on the governance implications, in terms of the effort and complexity of setting up a new service delivery model, including appropriate legal and contractual activities.

| No | Service Delivery Option | Legal/ Governance Complexity |
| --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | 3 |
| 2 | Enhanced single council service delivery | 3 |
| 3 | Authorities outsource all revenues and benefits service to another | 3 |
| 4 | Joint service delivery | 1.5 |

8.5	Risk Analysis

An assessment of the high level risks associated with each service delivery option:

| No | Service Delivery Option | Service Risk | Financial Risk | Reputational Risk | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | 1 | 1 | 1 | 3 |
| 2 | Enhanced single council service delivery | 2 | 1 | 2 | 5 |
| 3 | Authorities outsource all revenues and benefits service to another | 2 | 1.5 | 3 | 6.5 |
| 4 | Joint service delivery | 2.5 | 2 | 3 | 7.5 |

8.6	Assessment Summary

| No | Service Delivery Option | Total Score |
| --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) | 19.5 |
| 2 | Enhanced single council service delivery | 19.5 |
| 3 | Authorities outsource all revenues and benefits service to another | 28 |
| 4 | Joint service delivery | 29.5 |

8.7	Weightings

The following weightings were then applied to each of the following sections:

| Assessment Area | Weighting |
| --- | --- |
| Impact Assessment | 25 |
| Cost / Benefit Analysis | 35 |
| Human Resources | 15 |
| Governance | 10 |
| Risk Analysis | 15 |

A simple totalling exercise for all areas together with the subsequent application of the above weightings has given an overall score out of a maximum of 100 against each service delivery option:

| Option | Service Delivery Option | Score |  | Weighting Factor |  | Weighted Score |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | A revenues and benefits service hosted externally (outsourced) |  |  |  |  |  |
|  | Impact Assessment | 5 | X | 2.5 | = | 12.5 |
|  | Cost / Benefit Analysis | 7 | X | 3.5 | = | 24.5 |
|  | Human Resources | 1.5 | X | 1.5 | = | 2.25 |
|  | Governance | 3 | X | 1 | = | 3 |
|  | Risk Analysis | 3 | X | 1.5 | = | 4.5 |
|  | TOTAL |  |  |  |  | 46.75 |
| 2 | Enhanced single council service delivery |  |  |  |  |  |
|  | Impact Assessment | 3.5 | X | 2.5 | = | 8.75 |
|  | Cost / Benefit Analysis | 5 | X | 3.5 | = | 17.5 |
|  | Human Resources | 3 | X | 1.5 | = | 4.5 |
|  | Governance | 3 | X | 1 | = | 3 |
|  | Risk Analysis | 5 | X | 1.5 | = | 7.5 |
|  | TOTAL |  |  |  |  | 41.25 |
| 3 | Authorities outsource all revenues and benefits service to another |  |  |  |  |  |
|  | Impact Assessment | 11 | X | 2.5 | = | 27.5 |
|  | Cost / Benefit Analysis | 6 | X | 3.5 | = | 21 |
|  | Human Resources | 1.5 | X | 1.5 | = | 2.25 |
|  | Governance | 3 | X | 1 | = | 3 |
|  | Risk Analysis | 6.5 | X | 1.5 | = | 9.75 |
|  | TOTAL |  |  |  |  | 63.50 |
| 4 | Joint service delivery |  |  |  |  |  |
|  | Impact Assessment | 12 | X | 2.5 | = | 30 |
|  | Cost / Benefit Analysis | 6.5 | X | 3.5 | = | 22.75 |
|  | Human Resources | 2 | X | 1.5 | = | 3 |
|  | Governance | 1.5 | X | 1 | = | 1.5 |
|  | Risk Analysis | 7.5 | X | 1.5 | = | 11.25 |
|  | TOTAL |  |  |  |  | 68.50 |

8.8	Option Sensitivity Analysis

A sensitivity analysis review has identified that the scoring system used is robust and is not sensitive to significant changes.

The analysis involved manipulating the weightings across each section to reach a point where the overall rankings are affected.

8.9	Recommendation

This above evaluation, including the sensitivity analysis, confirms that Joint Service Delivery is the preferred option and this is recommended for approval.

The remainder of this business case is taken forward on the basis of joint service delivery being the recommended option.

9	Preferred Option – Joint Service Delivery

Summary

The preferred option following analysis shown previously would be to provide a joint service across the three authorities with one being the employing Council.  All services will operate from each site, e.g. both revenues and benefits staff will provide their services they will not be split into separate sites. There will be a manager at each to ensure that standards and targets are being met.  Taking into account the customer surveys, it is important that local delivery and high satisfaction ratings are maintained and this option would be the best fit for this.  In addition, joining up the three services will provide additional resilience, more effective working and potential to increase efficiencies in future by joining up systems and infrastructure.

Customer service front line delivery has not been included in this business case and will still be provided on each site.

This section of the Business Case expands on the preferred option of Joint Service Delivery under the following sections:

- Governance/Legal Arrangements & Service management

- Organisational Structure

- Finance

- IT Systems

- Human Resources

- Implementation of the Service

- Communications

9.1	Governance Arrangements for the Shared Service

Overview - The following diagram summarises the proposed governance arrangements, which are explained further below:

This structure will install a control framework to ensure effective delivery of services to all three councils in a fair and equitable manner, maintaining corporate visibility and involvement at all levels.

The approach proposed broadly follows the governance arrangements that have already recently been established for the Allerdale/Carlisle ICT Shared Service.  The shared service legal framework developed by Allerdale/Carlisle legal teams, and embodied into formal agreements by Eversheds solicitors, was designed with a view that it could be extended if/when required to accommodate additional shared services and/or partner council(s).

9.1.1	Revenues and Benefits Joint Committee

A joint member committee will be established which will include the appropriate portfolio holder(s) from each authority.

The exact powers of the committee will need to be determined, however it is anticipated that the Executive / Council at each organisation will grant delegated powers to the joint committee to provide the strategic control of the delivery of the Revenues and Benefits Shared Service. A single revenues and benefits service strategy will be developed, agreed and refreshed on an annual basis. This strategy will be approved by all councils and will form the basis for a forward planning of the service and its delivery over the medium term horizon (3-5 years).

9.1.2	Revenues and Benefits Joint Operational Board

The operational direction of the Revenues and Benefits Shared Service will be managed by a single Joint Operational Board comprising directors/heads of service from each organisation, supported by Finance, HR and other resources as required.

The Joint Operational Board will be responsible for directing the focus of the Revenues and Benefits Shared Service, including risk allocation, financial matters and overall service delivery control.

Responsibility for chairing and leading the joint steering board will rotate between directors, and hence councils, on an annual basis.

To ensure flexibility and responsiveness for the service, the Revenues and Benefits Partnership Manager will be granted delegated powers, within agreed budgets and policies, by the Joint Operational Board to act in the best interests of the service and its users.

9.1.3	Revenues and Benefits Shared Service Management Team

Day to day management and delivery of the Revenues and Benefits Shared Service will be undertaken by a single management team, led by the Revenues and Benefits Partnership Manager and supported by the three functional area managers within the organisational structure as described below.

9.1.4	Member engagement

The Revenues and Benefits Partnership Manager will be responsible for meeting with, and reporting to, portfolio holders on a joint basis with a schedule to be agreed with the three councils as well as presenting reports to executive committees as required.

In addition, the directors and/or Revenues and Benefits Partnership Manager will attend scrutiny committees at each council as required.

9.1.5	Shared service agreement

Subject to approval of the business case, a formal shared service agreement will be established between the councils to include (but not limited to):

- Governance arrangements as described above.

- Dispute resolution procedure, including independent arbitration arrangements.

- Agreement to the creation and adherence to a joint service delivery strategy for all three councils.

- The purpose and establishment of the Partnership.

- The duration, nature and governance of the Partnership.

- Services to be provided.

- Service provision details within agreed strategies and policies (e.g. counter-fraud strategy)

- The Joint Committee & Joint Operational Board.

- The accountable/lead Authority (if appropriate),

- Budget contributions, including capital funding obligation for the duration of the contract.

- Delegation of decision making,

- Review

- Indemnity

- Access to information

- Retention of records

- Bribery and corruption

- Conflict of interest

- Contract extension process

- Contract termination process

- Variations to the agreement

- Statutory compliance

- Procurement arrangements

- Performance levels and reporting

9.1.6	Service level management

Members of the Revenues and Benefits Shared Service Management Team will also act as service level managers working with stakeholders both within the three councils and with external bodies (including audit) to measure and maintain ongoing performance.

Customer satisfaction surveys will be undertaken on a regular basis, with scheduling to be agreed, which will be used as a benchmark and ongoing measurement of performance.

Performance management will be undertaken by all three managers with overall responsibility held by the Performance Manager for the provision of statistical and qualitative information to the Joint Operational Board.  The table below notes the draft performance requirements which have been built around the level of staffing and improvements expected of a joined up approach to service delivery.

DRAFT PERFORMANCE REQUIREMENTS

(Targets set by individual councils)

| Performance Definition | Year | Comment |
| --- | --- | --- |
|  | 2009/10 | 2010/11 | 2011/12 |  |
| Revenues |
| % of Council Tax collected within year demanded - Carlisle Copeland Allerdale | 97.3 98.5 97.75 | 97.4 98.5 98.0 | 97.5 98.5 98.25 | Very stretching targets bearing in mind the current state of economy. May need to be reviewed based on 2009/10 performance. |
| % of Council Tax collected within 3 years. | 99 | 99 | 99 | Meets losses of collection targets and allows for annual Council Tax surpluses to be made. |
| % of NNDR collected in year demanded - Carlisle Copeland Allerdale | 98.6 99.4 98.75 | 98.6 99.4 99.0 | 98.7 99.4 99.15 | Very stretching targets when NNDR collection reducing due to new empty rate regulations and state of economy (bankruptcies are increasing). |
| Benefits |
| Average of turnaround times for new claims and change of circumstance (measured in days). | 14 | 13 | 12 | Stretching targets - no DWP benchmarking figures yet, long term aim top quartile. Carlisle/Copeland currently achieving 16/17 days. |
| % Number of interventions, ie increases and decreases in Benefit compared to base number. | 100% | 100% | 100% | Numbers of interventions will be set for each authority based on DWP base data. Carlisle 2008/09 7,258. |
| Customer Contact |
| Response to letters and e-mails average working days. % of telephone calls answered within 20 seconds. Face to face customers on Revenues and Benefits matters seen within:- (minutes). | 10 85 15 | 10 85 15 | 10 85 15 | CLASB targets very ambitious particularly for letters and telephones at peak times. |

9.2	Proposed Organisation Structure

The proposed Revenues and Benefits Shared Service would operate over three sites with each site delivering all services directly to the customer.  Details of the functional roles and responsibilities are shown below:

The Partnership Manager would have overall strategic, operational and financial responsibility for the service and would be accountable to the joint operational board.  The Partnership Manager would be responsible for successfully implementing the new Revenues and Benefits Shared Service and would have responsibility for the ongoing developments of the shared service and working arrangements.

The Management Team would comprise of the Partnership Manager supported by the three Service Managers.  Shared responsibilities include:

- Rotating deputy partnership manager of revenues and benefits on 6 monthly basis.

- Responsibility for operational management (i.e. service delivery) and business development and improvement.

- Shared financial responsibilities.

- Support for, and engagement with, public and private sector partnerships.

- Taking an active role in the consideration and development of any further back office shared services.

- It is intended that the three service managers would be ‘hands on’ roles and facilitate revenues and benefits processing/determination at each of the locations.

- Each manager will manage a particular aspect of services as well as managing the location at which they are based.

The Benefits Manager would have responsibility for the Benefits Service delivery together with Customer Services Support, across the three locations, and the Assessment Teams would undertake the following functions:

- Benefits verification, determination and administration for all housing and council tax benefit claims.

- Administration, billing, collection and recovery of housing benefit overpayments and administrative penalties.

- Monitoring and determining requests for reconsiderations and appeals.

- Benefit fraud prevention, detection and deterrence.

- Applying discretions in appropriate circumstances.

- Providing resources for customer requirements to be handled by experienced and trained staff: avoiding duplicate handling.

The Performance Manager would have responsibility for the business support and development role, across the three locations, and the performance team would undertake the following functions:

- IT user-technical expertise and control.

- Creating and maintaining performance monitoring tools and options.

- Performance management and providing management information.

- Controlling the Discretionary Housing Payment (DHP) budget.

- Controlling benefits subsidy: including estimates, claims and handling audit 	inspections.

- Calculation of tax base estimates

- Controlling quality assurance.

- Control and balancing of records to the Valuation Office Agency lists.

- Designing and delivering appropriate training (regulations and software changes).

- Submitting statutory returns and information to Central Government.

- Developing service delivery e.g. e-government technology and agenda.

- Incoming post handling and document management system operations.

- Overall co-ordination of annual uprating and main billing: excluding responsibility document production and issue.

- Reconciliation and control of cash, credits/debits and interface balancing.

The Revenues Manager would have responsibility for the Revenues Service delivery together with Customer Services Support, across the three locations, and the Processing Teams would undertake the following functions:

- Administration, billing, collection and recovery of council tax and national  non-domestic rates and business improvement districts (BIDs).

- Processing and maintaining records of valuation list amendments.

- Administering discounts, reductions and exemptions.

- Applying discretions in appropriate circumstances.

- Using all and applying best methods applicable for maximising tax collection.

- Managing the external visiting resources available to assist operations.

- Providing resources for customer requirements to be handled by experienced  and trained staff: avoiding duplicate handling.

- The printing, collation and issue of all documentation in connection with  annual uprating and main billing: including liaison with printers and IT.

Procurement would be controlled and commissioned from within the Revenues and Benefits Shared Service; however actual procurement would be undertaken centrally by Corporate Procurement team(s).

9.3	Staffing Levels

The following table provides a summary of the proposed staffing levels, including transition levels from the old to the new structure: The draft organisational structure is shown in Appendix 4.

| Functional Area | Current | Proposed |
| --- | --- | --- |
| Managers (Heads of Service) | *1.00 | 1.00 |
| Managers (Locations/Teams) | 8.00 | 3.00 |
| Team Leaders | 14.70 | 12.00 |
| Senior Officers | 8.48 | 10.00 |
| Officers | 80.91 | 79.00 |
| Assistants | 22.42 | 19.00 |
|  | 135.51 | 124.00 |
| Net Result |  | -11.51 |

Currently there are three heads of service but at Allerdale and Copeland these  have other responsibilities for service delivery and customer contact centres and not just revenues and benefits. Therefore we have estimated that one full time head of service would be required.

Please note that the staffing allocations detailed within this table are an initial view and are subject to change as the Revenues and Benefits Shared Service is implemented, however it is anticipated that the overall total number of staff would not change.

9.4	Salaries and Terms & Conditions

New job descriptions and person specifications will be developed for all roles following the agreement of the business case and prior to any recruitment.

The new structure and posts would adhere to the nationally agreed ‘Green Book’ Local Government terms and conditions, subject to local variations.

There has been an examination and comparison of the job evaluation results in costing the initial business case. However certain jobs in the new structure will require re-evaluation under the employing authority’s JE model, for example managers, team leaders, senior officers and fraud officers. See HR section below.

Salaries will be set depending upon the outcomes of the job evaluation and pay review processes.

The exact approach to alignment of terms and conditions will be agreed as part of phase 1 and progressed by the HR assimilation process: subject to the approval of the business case.

9.5	Support Arrangements (Accountancy / HR / Legal / Project Management etc)

Internal arrangements will be finalised as part of the phase 1 implementation and will be subject to the final service delivery model adopted.

9.6	Financial Appraisal.

9.6.1. General

Between the 3 Authority’s, over £7.5million will actually be expended in 2009/10 in the form of employee related costs, premises related costs, transport, supplies and services and internally generated support service charges to administer the Revenues and Benefits function.  Unfortunately, due to the disparate accounting and cost allocation methods adopted in each Authority, particularly in respect of direct and indirect support service costs, it has not been possible to set out a meaningful like for like cost categorisation comparison for this business case.

This is not a critical omission at this particular stage of the project because it was acknowledged at the Project Board that in order to establish an initial financial case, concentration would be focused on salaries and salary related on-costs for back office staff and ICT expenditure requirements which are the key issues for the shared service. It is anticipated that further savings may be identified upon further analysis of the full financial position of each Authority’s service.

9.6.2. Staffing Costs

In respect of staffing costs, Table 1 below provides current 2009/10 cost levels   Authority by Authority calculated on the following basis:

-  In terms of overall staff numbers, 135.51 FTE posts were identified as being in –scope equating to 52.30 FTE’s at Carlisle, 39.52 FTE’s at Copeland and 43.69 FTE’s at Allerdale (i.e. excluding 5.39 FTE posts which have already been taken out of their establishment and the savings taken in advance)

-  The basic salary costs for these posts were evaluated on the grading outcomes of the Job Evaluation exercises conducted in each Authority. For comparative purposes, basic salaries were calculated for each post at the top of the new J/E grading structure within each Authority utilising 1/4/08 grading levels plus 2.5% (current offer 1%) in lieu of the outstanding and as of yet undecided April 2009 pay award.

-  Salary on-costs were calculated on a uniform basis with National Insurance and Superannuation charges being evaluated on the premise that all employees participate in the Local Government pension scheme. Similarly, for consistency purposes, a standard mid rate of superannuation contribution was utilised regardless of which Authority each post was located. It should be noted that the next Triennial pension revaluation is due to take effect on 1/4/2011.

# Table 1

|  | Allerdale £000 | Carlisle £000 | Copeland £000 | Total £000 |
| --- | --- | --- | --- | --- |
| Current costs based on post JE assumptions | 1,137 | 1,525 | 1,114 | 3,776 |

Benchmark information suggests that the 3 Council’s already operate in the lowest (i.e. most efficient) quartile in terms of staff numbers. However, the proposed structure for the 3 Authority shared service has 124 FTE posts representing an overall reduction of 11.51 FTE’s. This facilitates a significant reduction of the proportion of management posts but substantially retains the main processing team numbers in order to provide the resilience required.

Based upon the draft grading structure for the shared service, the overall cost has been assessed at £3,489k based at the top of the scale for each remaining member of staff, reflecting a saving of over £400k per annum after taking account of £119k in advance staff savings taken by Allerdale (which will be reflected in their savings share)

9.6.3	ICT Costs

With regard to current and future shared service ICT costs, Table 2 below details the current revenue costs of revenues and benefits software, licences etc.  Also the estimated revenues costs under Academy’s shared service proposals and the 5 year cost taking account of revenue and implementation cost.  A more detailed overview of the ICT systems and process is shown in Appendix 5.

Table 2

|  | Allerdale £000 | Carlisle £000 | Copeland £000 | Total £000 |
| --- | --- | --- | --- | --- |
| Annual revenue cost: Current: Proposed shared arrangement | 77.0 42.2 | 76.2 42.2 | 105.4 42.2 | 258.6 126.8 |
| Capital costs of implementing shared service ICT | 346.8 | 188.1 | 188.1 | 723.0 |
| Five year costs (not including initial capital outlay) Current Proposed Saving (rounded to nearest £5k) | 385.0 211.67 175.00 | 380.0 211.67 170.00 | 525.0 211.67 315.00 | 1293.0 633.0 660.00 |

Note 1

The above costs indicate a potential 50% reduction in annual revenue by adopting Academy in each authority.  Capital Costs are significantly higher in Allerdale as the proposal requires new hardware, a total suite of new software plus the associated data conversion and implementation.  All costs are as extracted from the Academy tender submission and a number of their initial service costs will be the subject of negotiation following confirmation of organisational requirements.  Initial negotiations have reduced the 5 year cost by £125,000 through Carlisle providing part of the training and some rationalisation in hardware configuration.

It should be noted that Allerdale will need to incur significant implementation costs irrespective of whether or not the shared service business case is robust.  Northgate have provided indicative implementation and revenue costs of approximately £487,355 (see note 2 below) over the same 5 year period.

The technical infrastructure proposed as part of the potential Capita Academy implementation has the following benefits:

- The proposed shared service arrangement with one system across the three councils would provide reduced revenue costs of around £655,000 over a 5 year period.

- The infrastructure would involve the system running across two server and storage environments running at two sites.  This, together with network links between the three main council sites would give the partnership greatly enhanced levels of business continuity resilience by removing the current reliance upon a single instance of each system.

- The proposed implementation of the Academy system will include functionality that would allow any user, with appropriate permissions, to operate effectively on behalf of each of the three Councils from their existing location.

- The migration to the Academy system, together with migration to the Civica Electronic Document Management system (as currently used by Allerdale) would also result in the provision of electronic document management again with resilience across multiple sites. This also allows both Carlisle and Copeland the opportunity to provide a corporate EDMS within their authorities. They currently use EDMS just for revenues and benefits services.

- The proposed implementation of the Civica system would also allow users at any physical location to access and work on case documentation in electronic format for customers at any Council.

- The proposed implementation would enable economies of scale in terms of both ICT based technical administration and user department based administration of each system.

Note 2

Allerdale have a proposal from Northgate to upgrade Pericles to Northgate’s own revenues and benefits software and operating system, the equivalent 5 year costs being:

| Capital costs | £213,920 |
| --- | --- |
| Revenue costs | £273,435 |
| Total | £487,355 |

The Northgate costs are based on their proposals, whilst the infrastructure and other third party costs are estimated. It should be noted that the current server and storage infrastructure for the Pericles system are at end of life and therefore could not be reutilised for a new system. Therefore there would be considerable extra costs to add to the total above.

When comparing the options this would not give Allerdale any form of resilience across multiple sites and would also involve increased resources for the Shared ICT Service to technically administer/support two separate revenues and benefits applications. The user department(s) would also need two sets of administrators for the user aspects of the systems. If the revenues and benefits shared service does go ahead, then Allerdale working on a separate system would also fundamentally undermine the capabilities of the new service to work effectively across the three councils.

9.6.4	Other Direct Costs

Direct costs in respect of training, travel and subsistence, printing and stationery, postage, office equipment and furniture, post office and bank charges, general expenses etc., will be based on current expenditure budget.  Whilst there should be some saving in direct costs, savings are likely to be small so will not be accounted for in this business case.

9.6.5	Recharges

It is assumed for this draft business case, that the revenues and benefits services will continue to pick up the cost of central recharges within each council on the same arrangements as currently. However a separate piece of work will be completed during the consultation phase.

9.6.6 Staff Restructuring Costs.

The organisational restructuring savings are based on an overall reduction of 11.51 FTE members of staff by 31/3/10. Some of this reduction can be attributed to currently held vacant posts on the existing funded establishment for some of the Authority’s and there is also some impending natural wastage.

However, there will still be a requirement for some redundancies at a management level and the current expectation is that up to 5 posts may fall into this category. As actual staff who may be affected by the proposed restructuring are unknown at the present time a provisional  sum of £415,000 has been set aside to cover any costs of redundancy and pension liabilities based upon envisaged policies likely to be adopted within each Authority. In addition to redundancy costs, it would be likely that there would be some need for salary protection and a sum of £11,000 has been set aside bringing the overall staff restructuring costs up to £426,000.

Provisionally, for overall illustrative purposes, these potential costs are allocated over each Authority in accordance with the standard split based on activity levels of 35%, 28% and 37% for Allerdale, Copeland and Carlisle respectively which is the same split to be utilised for sharing staff savings. At this stage however that the treatment of termination costs and savings has yet to be agreed by the 3 Authorities and the independent views of Meritec will be sought.

9.6.7 Additional Capital Costs and Savings

Table 3 below identifies estimated capital requirements for ICT development of £468,000 in 2010/11 on the basis that Allerdale, Copeland and Carlisle continue to run separate Revenues and Benefits Systems. In respect of Carlisle, the funding of £155,000 has already been approved and set aside under the CCC Medium Term Financial Plan. In respect of Allerdale, the funding would be subject to the next round of annual bids. Should the shared service go ahead, then Copeland would need to find funding of £155,000 to facilitate its share of the overall capital investment required. In addition it is deemed prudent to include a capital contingency of £100,000 which if actually expended would be shared out on a negotiated basis. For illustrative purposes Table 3 includes an equal allocation of £33,000.  It should be noted that the overall capital programme would require phased payments over 2009/10 and 2010/11.

The shared service would yield significant ongoing revenue ICT cost savings of £660,000 over the 5 year period. These savings are reflected in the table which shows each Authority taking an equal share of revised costs and varying levels of savings dependent upon existing costs.

The table also identifies overall anticipated staff savings of £2,030,000 over the 5 years 2010/11 to 2014/15.but at the same time makes a prudent provision for the costs of restructuring in the form of termination and salary protection costs of £426,000. Table 4 then goes on to identify the apportionment of the salary savings.

Table 3

|  | 2009/10 £000's | 2010/11 £000's | 2011/12 £000's | 2012/13 £000's | 2013/14 £000's | 2014/15 £000's | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Do Nothing |  |  |  |  |  |  |  |  |
| Allerdale |  |  |  |  |  |  |  |  |
| Capital |  | 314 |  |  |  |  | 314 |  |
| Rev-Salaries/on-costs |  | 1256 | 1256 | 1256 | 1256 | 1256 | 6280 |  |
| Rev-IT Software |  | 77 | 77 | 77 | 77 | 77 | 385 |  |
| Copeland |  |  |  |  |  |  |  |  |
| Capital |  | 0 |  |  |  |  | 0 |  |
| Rev-Salaries/on-costs |  | 1114 | 1114 | 1114 | 1114 | 1114 | 5570 |  |
| Rev-IT Software |  | 105 | 105 | 105 | 105 | 105 | 525 |  |
| Carlisle |  |  |  |  |  |  |  |  |
| Capital |  | 155 |  |  |  |  | 155 |  |
| Rev-Salaries/on-costs |  | 1525 | 1525 | 1525 | 1525 | 1525 | 7625 |  |
| Rev-IT Software |  | 76 | 76 | 76 | 76 | 76 | 380 |  |
| Shared Service |  |  |  |  |  |  |  |  |
| Allerdale |  |  |  |  |  |  |  |  |
| Capital |  | 347 |  |  |  |  | 347 |  |
| Rev-IT Software |  | 42 | 42 | 42 | 42 | 42 | 210 |  |
| Termination/Protection | 145 | 4 |  |  |  |  | 149 |  |
| Copeland |  |  |  |  |  |  |  |  |
| Capital |  | 188 |  |  |  |  | 188 |  |
| Rev-IT Software |  | 42 | 42 | 42 | 42 | 42 | 210 |  |
| Termination/Protection | 116 | 3 |  |  |  |  | 119 |  |
| Carlisle |  |  |  |  |  |  |  |  |
| Capital |  | 188 |  |  |  |  | 188 |  |
| Rev-IT Software |  | 42 | 42 | 42 | 42 | 42 | 210 |  |
| Termination/Protection | 154 | 4 |  |  |  |  | 158 |  |
| Total Staffing |  | 3489 | 3489 | 3489 | 3489 | 3489 | 17445 |  |
| Costs (Savings) |  |  |  |  |  |  |  |  |
| Allerdale |  |  |  |  |  |  |  |  |
| Capital |  | 33 |  |  |  |  | 33 |  |
| Rev-IT Software |  | -35 | -35 | -35 | -35 | -35 | -175 |  |
| Termination/Protection | 145 | 4 |  |  |  |  | 149 |  |
| Copeland |  |  |  |  |  |  |  |  |
| Capital |  | 188 |  |  |  |  | 188 |  |
| Rev-IT Software |  | -63 | -63 | -63 | -63 | -63 | -315 |  |
| Termination/Protection | 116 | 3 |  |  |  |  | 119 |  |
| Carlisle |  |  |  |  |  |  |  |  |
| Capital |  | 33 |  |  |  |  | 33 |  |
| Rev-IT Software |  | -34 | -34 | -34 | -34 | -34 | -170 |  |
| Termination/Protection | 154 | 4 |  |  |  |  | 158 |  |
| Staff Savings |  | -406 | -406 | -406 | -406 | -406 | -2030 |  |

Table 4

| Staff Savings Apportionment |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Less ABC | Savings | Annual |  |  |
|  |  |  |  | Advance | over the | Savings |  |  |
|  | £000's | % | £000's | Savings | 5yr period |  |  |
| Allerdale | 2,030 | 35 | 711 | -595 | 116 | 23 |  |  |
| Copeland | 2,030 | 28 | 568 |  | 568 | 114 |  |  |
| Carlisle | 2,030 | 37 | 751 |  | 751 | 150 |  |  |

Overall, although there is a significant amount of work still to do, the financial analysis to date shows that from a financial perspective there are significant overall savings to be made by the 3 Authorities from pursuing the shared service. The cost savings set out in this business plan are anticipated to be the minimum that could be achieved.

In order to progress to the next stage, the appointment of a Programme Manager would be required in November 2009 to initiate Phase 1 of the migration to a shared Revenue and Benefits service by April 2010. The cost of delivering Phase 1 has been assessed at £33,000 to cover the Salary and salary on-costs of the Programme Manager and some part-time project support together with some travel and subsistence costs. This sum would fall to be met equally between Allerdale, Copeland and Carlisle at cost of £11,000 per Authority financed from existing Revenues and Benefits base budgets.

9.7	Human Resource Arrangements

As detailed in the implementation section of this business case it is recommended that during phase 1 an evaluation of the most appropriate employing authority is undertaken.  The criteria used will be based on the lessons learned from the ICT shared service project and will be relevant to the revenues and benefits case.

Once a decision is taken on the employing authority, staff from the non-employing authorities will be transferred to the employing  authority’s payroll and terms and conditions whilst they continue to be based at their existing place of work.

For phase 1 implementation it is recommended that a programme manager will be employed  and will be able to call on the assistance/expertise of HR, Finance, Legal, ICT and Revenues and Benefits practitioners in the three authorities to progress the business case. HR implications will need to be properly considered and consulted on prior to the start date of the partnership.

Also learning from the experience of the ICT shared service it is essential that the aligning of terms and conditions are agreed prior to the commencement of the shared service. In order for this to happen the differences between the three organisations have been highlighted and work will commence on this after approval of the business case.

There has also been an examination and comparison of the job evaluation results in costing the initial business case. However certain jobs in the new structure will require re-evaluation under the employing authority’s JE model, for example managers, team leaders, senior officers and fraud officers.

There are a number of posts where the job descriptions will remain unchanged and staff will be recruited to these by ring fencing applications from staff who are currently fulfilling these roles or have been unsuccessful in applying for a higher level post within the shared service, for example a manager may want to apply for a senior officer post. If there are excess applicants for the post the selection process will be by conducting interviews and tests.

Where the jobs have changed or there is more than one possible applicant a process will be undertaken to establish which staff may be assimilated into posts, this is envisaged by using existing criteria by the employing authority. Any increases through JE reviews will be backdated to the start of the appointment.  Any decreases will apply from the date of the JE score.

Where possible a reduction in staff numbers will be achieved by natural wastage. However any requests for early and/or flexible retirement will be considered only where there is a business need or where compulsory redundancy is the only alternative.

Remote working will be encouraged where it has been identified that the role can be covered by this method of working.

All HR implications such as training and development requirements will be identified throughout phase 1 of the project. Specific, individual staff requirements will be identified during the annual performance management reviews and service plans developed for the shared revenues and benefits service.

Any revision of terms and conditions will be subject to consultation with Trades Unions.

It is envisaged that the work identified for HR will be completed by March 2010.

9.8	Phased implementation of the shared service

9.8.1	Migration to the New Organisational Structure

Based on the assumption that all three councils adopt the Academy / Civica operating systems to the agreed models by 1st July 2010, the migration to the new structure would be implemented in a phased approach, as a separate and distinct project.  The outline action plan below represents either known or reasonably assumed key dates or possible known or perceived constraints.  This is seen as very much a dynamic document which will change with time factors and there is a high probability that there will be addition to the key points already detailed. A detailed project implementation plan will be drawn up within the Project Initiation Document.

9.8.2	Initial Action Plan

Phase 1 (October 2009 to March 2010)

# Assumptions/Joint Agreement - The implementation of the shared service will at this stage need to be considered based on certain assumptions in the absence of final agreement.

1	The first and probably the most important assumption to the progression of the project as a whole is that there is universal approval of the draft business case by all three councils involved by September/October 2009.

2	Allerdale has made a conclusive decision and chosen Capita’s software system based on cost/benefit over the Northgate-IS proposal.

3	In terms of software systems for both Revenues and Housing and Council Tax Benefits, all three council will adopt Capita/Civica. It is assumed that the three councils will have the systems fully operational and implemented by July 2010. While this is the preferred date of implementation there is some contingency around this date up until the end of September 2010 at which point Northgate-IS withdraw support for Allerdale’s current Pericles system. Therefore September 2010 becomes a critical date in terms of system implementation.

4	Allerdale and Carlisle Shared IT service, and other technical users, being available to offer assistance for the implementation of Academy due to technical expertise and previous experience in the implementation of Academy. Also similar technical expertise is held with regard to Civica by Allerdale and knowledge and expertise can be offered to both Carlisle and Copeland. Because all three councils have both Capita and Civica in operation the assumption again is that because of pooled expertise and knowledge there could be a reduction in transitional costs because of previous experience with implementations.

5	All three councils are currently operating a vacancy management policy.

6	Phase 1 would commence with the appointment of a Programme Manager and support. The deliverables during phase one will include:

- Development and approval of a Project Initiation Document and action plan for the overall programme;

- Establishment of Programme Board

- Evaluation of the employing authority;

- Implementation of ICT systems;

- Finalisation of policies, practices and procedures;

- Finalisation and recruitment to the new structure;

- Finalise terms and conditions and HR issues;

- Finalise governance arrangements;

- Finalise support arrangement.

9.8.3	Phase 2 (April 2010 to July 2010)

- Final implementation of ICT systems

- Go live with new structure and shared service arrangements

9.8.4	Summarised Action Plan

| Key Date | Action | Constraints |
| --- | --- | --- |
| Sept/Oct 09 | Approval of draft business case by all three councils | Up to 10% savings being achieved on staffing costs |
| Sept/Oct 09 | The three councils to agree on a joint revenues and benefits operating system including sharing electronic document management system. | Business case approval – although Allerdale will need to take a decision either way due to withdrawal of Northgate-IS support for Pericles |
| Sept/Oct 09 | Appointment of Programme Manager | Availability of key staff. |
| Sept/Oct 09 | Production and approval of Project Initiation Document and establishment of Programme Board | Availability of key. |
| Oct 09 – July 10 | Implementation of shared systems (ICT) subject to discussions with suppliers. Allerdale to convert to agreed operating system with the other two councils converting to the same version and then all three councils converting to the same version of the DMS system | Availability of key resource both from software provider and internally |
| Oct 09 | Agreement on employing authority | Availability of key resources |
| Oct 09 – Dec 09 | Commencement of consultation process regarding joint t&cs and consultation with relevant bodies. Agreement to be reached by all parties and contracts drawn up and signed. | Availability of key HR, Legal and other professionals throughout consultation period |
| Jan 10- Apr 10 | Recruitment of permanent shared service management and staff . Implementation of shared service operation. Any staff migration in line with work life balance and business needs and personal choice but the majority of staff will remain at their current sites | The availability of key staff on a permanent basis Accommodation needs |

9.9	Communications

9.9.1	Consultation regarding the introduction of the new shared revenues and benefits shared service is crucial.  A full range of stakeholders, including members and customers at each council, partner organisations, trade unions and, most importantly, all current revenues and benefits staff at all three authorities affected by the change have been consulted with and updated throughout the period of business case development.

Communications officers at the three councils have issued regular newsletters to keep all parties briefed and engaged.

9.9.2	From August to September the draft business case will be widely consulted on with staff and trade unions, Executive and Overview and Scrutiny Committees (Allerdale and Carlisle) before consideration by full Council in September/October 2009.

10	Recommendations

The Project Board recommends that the preferred option in the business case – Joint Service Delivery – be agreed and consulted on.  The external verification should be completed as soon as possible within the consultation period and a final draft of this business case, containing all pertinent information following consultation should be provided to each Council for approval.

11	Appendices

# REVENUES AND BENEFITS BUSINESS CASE

APPENDICES – 28th July 2009

# Appendix 1 - Costs/ Performance Outsourced, In House and Shared Service Revenues and Benefits Operations

## Appendix 2 – Revenues and Benefits quick wins

Appendix 3 – Risk Analysis/initial Risk Log

Appendix 4 – Organisational Structures

Appendix 5 – ICT Systems

# APPENDIX 1 - Costs/ Performance Outsourced, In House and Shared Service Revenues and Benefits Operations

- Introduction

  - As part of the Revenues and Benefits shared service options appraisal it was agreed that the outsourcing option be investigated.

  - It has proved very difficult to get any robust figures for outsourcing options as:

- we would need to advertise for expressions of interest under European procurement rules and the Project Board have not sanctioned such an exercise;

- obviously details of outsourced contracts between councils and the private sector are confidential.

  - In the circumstances councils where Revenues and Benefits have been outsourced RA (Revenue Account Budgets) forms have been analysed (source Audit Commission website).  In the RA form councils allocate the actual cost of service provision in a particular year.  In respect of Revenues and Benefits this would include cost of outsourced Revenues and Benefits contract, client costs of monitoring contract (and resourcing work that cannot be outsourced, e.g. committal administration) and any recharges allocated to Revenues and Benefits (should be minimal for outsourced service).

  - For comparative purposes RA forms for Cumbria ‘in house’ provision and the few councils already operating in a shared service arrangement have also been analysed.

  - Performance against best value indicators for all the councils have also been compared.

- Comparative Results

  - In nearly all cases the cost of outsourced Revenues and Benefits operations are significantly higher than ‘in house’ or shared service operations, i.e. in our population group (see attached) total cost of provision of Revenues and Benefits Services per resident is:

2007/08	2008/09

In House		£17.54		£19.02

Outsourced		£25.79		£24.38

Shared Service	£22.52		£23.20

For comparative purposes, budgeted costs –

Carlisle 2008/09 = £19.91

Allerdale 2008/09 = £20.66

Copeland 2008/09 = £22.49

  - In the next population group up to 203,000 (no Cumbrian authorities in this group) the corresponding figure is:

2007/08	2008/09

Outsourced		£17.52		£17.69

Shared Service	£14.47		£16.90

It is interesting to note that the gap between outsourced contracts and shared service arrangements reduced in 2008/09.

  - When you look at larger councils the costs of Revenues and Benefits services increase before falling back (population numbers):

2007/08	2008/09

300,000	£30.06		£25.87

400,000	£19.28		£19.27

600,000	£16.37		£17.26

  - On cost comparisons outsourcing does not appear to be a valid business option, although the gap is narrowing.

  - Shared service operations of up to 203,000 (Carlisle, Allerdale and Copeland councils combined population approx 260,000) appear to deliver cost savings when compared to in house provision, i.e. they appear to be operating at approximately 15% less cost than our current in house provision i.e. £16.90 compared to £20.00 approx based on 2008/09 figures.

- Performance

  - When comparing performance (see Appendix   ) in respect of collection rates, benefit turnaround times, accuracy, and customer satisfaction shared services operations significantly outperform other service delivery options.

  - In respect of collection performance, in house provision performs better than outsourced provision.  In respect of benefits, very similar performance is apparent.

Note

- Individual council figures are available in working papers for scrutiny if required.

- All known shared service operations and fully outsourced (R&B) councils included in analysis, i.e. councils that outsource only their backlogs not included in analysis.

Peter Mason - Head of Revenues and Benefits Services, Carlisle City Council

21.10.08 (Updated with 2008/09 budgeted figures 15/4/09)

Appendix for Option 2 - Current status – Revenues quick wins

| Task | Responsibility | Timeline | Status | Expected benefits/savings |
| --- | --- | --- | --- | --- |
| Introduction of paperless direct debit at Carlisle – to increase customer service levels and help cashflow. | Carlisle CC | June 2009 | Will be achieved irrespective of business case completion | Improved customer service levels. Improved cashflow predictability and collection levels. |
| Establishment of joint training provision in Revenues, recording savings achieved by joint purchase | Carlisle CC, Allerdale BC, Copeland BC | Achieved May 2009 | Achieved May 2009 | Joint savings achieved of £2380 compared to three separate courses |
| Develop and maintain Anti-Poverty strategy for Revenues recovery. Aims are i) to collect outstanding debts in an efficient but sensitive manner and ii) to minimize hardship for debtors wherever possible. | Allerdale BC | July 2009 | Will be achieved irrespective of business case completion | Steady reduction in outstanding arrears. Minimise hardship for customers experiencing difficulty in making payments. |
| Achieve savings in costs of inspections through sharing of visiting resources of other departments, eg building control and benefits, and more use of postal reviews. | Allerdale BC | July 2009 | Will be achieved irrespective of business case completion | Expected savings of £5000 in salary costs plus mileage |
| Harmonise Revenues working practices wherever possible in line with recommended industry best practice (ACS). Because of the disparity in the current practices, this will not be a “quick win” and following discussion with David Airey it is obvious that much work lays ahead, should a shared service proceed. For instance, all three versions of EDRMS documents would need to be replaced by a new version held on the preferred shared software (currently 100 letters in Allerdale alone). Extra resources may be required to complete this task, and time allowed, before any “go live.” From the discussions with David Airey and in the work packages, the other main areas where harmonisation of working practices would be required are as follows; inspection and review policy for exemption/discount/ rate relief entitlement making and monitoring of pre summons payment arrangements Smoothing out of recovery timetable to avoid peaks and troughs in workload (particularly at Allerdale) Policy on withdrawal of summonses when i) customer completes a direct debit mandate or ii) pays in full before the court date Policy on pursuing committal as a method of recovery | Carlisle CC, Allerdale BC, Copeland BC | Before a potential shared service goes live. | Subject to successful business case outcome | Expected to improve to flexibility amongst staff at the three districts, with a consequential improvement in customer service levels eg quicker turnaround or correspondence. Also expected to improve collection levels marginally. |

Appendix for Option 2 – Current status – Benefits quick wins

| Task | Responsibility | Timeline | Status | Expected benefits/savings |
| --- | --- | --- | --- | --- |
| Introduction of electronic and telephone claims and notification of changes in circumstances – to enable more service access channels, to increase the speed of processing and to encourage timely reporting of changes. | Carlisle CC, Allerdale BC, Copeland BC | Scoping report completed Mar 2009 for implementation Apr to Dec 2009 | Likely to be adopted irrespective of business case completion as good practice. | Increased service access channels, increased speed of processing and promotion of timely reporting of changes. |
| Joint working on assessment and implementation plans for the new Audit Commission’s Revenues and Benefits Key Lines of Enquiry (KLOEs) inspection regime – to provide minimum standards of service levels and plan for continual improvement. | Carlisle CC, Allerdale BC, Copeland BC | 2009/2010 | Requirement for all councils: irrespective of shared service arrangements. | To deliver better value for money, promote high standards of governance and accountability and to encourage continual improvement in services in order to meet the changing and diverse needs of our communities. |
| Introduce best practice into Housing Benefit overpayment recovery procedures – introducing the use of collection agencies, County Court collection and aged-debt analysis of current methods deployed. | Allerdale BC – use of County Court & collection agencies. All – aged debt analysis | 2009/10 Completed Mar 2009. | Will be achieved irrespective of business case completion. | Improved Housing Benefit overpayment collection rates |
| Evaluating fraud and fraud support software with a view to recommending one system with a potential for joint procurement. | Carlisle CC, Allerdale BC, Copeland BC | Completed Mar 2009 | All investigative and evaluation work completed. | Potential for savings through joint procurement if a shared fraud service proceeds. |
| Strengthen the shared service working arrangements for appeals and discretionary housing payments across the four councils. | Carlisle CC, Allerdale BC, Copeland BC, South Lakeland BC | Completed March 2009. | Implemented. | Increased flexibility and resources for handling appeals and DHPs. Faster service and value for money use of resources for attending hearings. |
| Harmonise Benefits working practices, wherever possible, in line with recommended industry and Audit Commission best practice (ACS) | Carlisle CC, Allerdale BC, Copeland BC | Draft implementation plan completed 15tth June 2009. | Implementation subject to business case outcome. | Will improve flexibility, capacity and resilience between the three councils: leading to improved customer service. |

Appendix 3 - Risk Assessment and initial Risk Log

Throughout the whole implementation process there will be risks attached to certain processes below is a table of risks identified to date. Again this will be a dynamic log detailing the risks associated with various elements of the implementation of the business case. Below is the initial risk log for the project.

| No | Risk Description | Likelihood 1-4 1 – Low 4 - High | Impact 1-4 1 –Low 4 – High | Gross Impact (Likelihood x Risk) | Mitigation Action |
| --- | --- | --- | --- | --- | --- |
| 1 | Rejection of draft business plan by one or all of the councils | 2 | 4 | 8 | Up to 10% desired savings on direct costs are realised and documented correctly ensuring there are no anomalies in the figures Ensure there is chief officer/member commitment ahead of requesting final agreement and commitment to the project Ensure there are robust communication strategies in place to enable effective communication of progress and issues at all levels and at every stage |
| 2 | Allerdale adopting an alternate operating system to Carlisle and Copeland | 1 | 4 | 4 | Agreement of the business case Ensuring that there are negotiations to reduce the cost of the current tender by elimination of unnecessary costs Ensuring that there are cost savings to be realised from the adoption of a single software package across the three councils |
| 3 | Lack of availability of key resource to form the project implementation team thus delaying the projects initiation and implementation | 1 | 2 | 2 | Identify the staff required as soon as practicable Ensure that the duality of role will not place excess and unreasonable demands upon the identified staff Where necessary ensure delegation of duties to ensure performance and commitment to the shared service project is not jeopardised |
| 4 | Delay in the implementation of the shared IT systems due to lack of available resource/expertise from the software provider with regard to implementation and conversion to a single desired system | 2 | 4 | 8 | There is little that can be done about this apart from trying to secure resource allocation at the earliest possible juncture As this is very much in the hands of the software provider then a quick decision is desirable on the adoption of a single software application for the three councils |
| 5 | The current transformation process in Allerdale and Carlisle leading to the loss of key members of staff to make the formulation of a progression project board difficult | 2 | 4 | 8 | There is little mitigation to this if key members of staff are lost they will not be replaced Identification of replacement members of staff at the earliest possible juncture |
| 6 | No agreement of terms and conditions, and alignment of policies and procedures (HR, Legal, Union and Staffing issues) | 2 | 2 | 4 | Ensure that there is early commencement of full consultation with all relevant HR and Legal bodies. From similar experience this can be a protracted process therefore the earliest possible starting point is desirable Clear communication lines are maintained by one owner who coordinates and directs any debate or discussion to avoid confusion and loss of focus across the three councils |
| 7 | Reduction in quality of service due to implementation of the transition to the shared service and implementation of unified software | 2 | 3 | 6 | Manage the service level expectations with a key stakeholders prior to and during implementation Extra emphasis to be placed on performance and regular monitoring of this to be maintained throughout the process |
| 8 | Loss of control or perceived loss of control or direction by any of the three councils with regard to service delivery | 1 | 4 | 4 | Establishment of robust governance arrangements Look at the possibility of formulating a separate joint steering group with a rotating chair for agreed periods to deal with this possibility |

The Partnership Structure

Appendix 5 -  ICT Systems for Revenues and Benefits Shared Service

Fundamental to the delivery of a Revenues and Benefits service is its supporting ICT.  Indeed, advice from both external advisors and operational shared services confirms that standardisation of ICTs across the service is a critical success factor for a unified operation.

Achieving standardisation of ICTs presents significant challenges to any potential shared service for Allerdale, Carlisle and Copeland as there are significant differences in current ICTs in use.  The start point is the matrix of these differing ICTs, as follows:

| Council | Function | ICT system used |
| --- | --- | --- |
| Allerdale | Revenues and Benefits | Pericles from Northgate |
| “” | EDMS | EDM & Workfow from Civica |
| “” | CRM | Northgate CRM |
| Carlisle | Revenues and Benefits | Academy from Capita |
| “” | EDMS | Information@Work from Northgate |
| “” | CRM | Capita CRM |
| Copeland | Revenues and Benefits | Academy from Capita |
| “” | EDMS | Information@Work from Northgate |
| “” | CRM | Excelsior from CGI |

Although Allerdale and Carlisle have very recently embarked upon their new ICT Shared Service, and system rationalisation is a strategic objective, it is too early for the impact of the ICT shared service is to have begun to affect Revenues and Benefits in those two authorities.

The variances in the way the three Council’s ICTs operate need to be considered and differences in the main data flows and interactions between the front and back office understood.  The current key differences between the Councils are as summarised in the following overviews of how each council operates in relation to its ICT:

- Allerdale – use Northgate’s Pericles system and Civica’s EDM & Workflow to process Revenues and Benefits work.  The systems are comprehensively integrated and the Council use their own templates extensively for workflow.  Documents are scanned at source in the central scanning room and work is then allocated to specialist teams (Benefits) and generic teams (Revenues).  There is little in the way of integration with CRM.  The customer raises a call to the Contact Service Centres and a service request is raised in CRM.  Civica is used to forward information to the back office teams.  Barcoding technology is used on Notices that are issued (however this is not used by the other two Councils).  Annual notices are printed inhouse and shipped out to a mailing company for packing and posting (use Gandlake to manipulate print files).  Some self service is available to customers for viewing Council Tax information on-line.  Mobile working technology has been acquired but is not used and there is currently no home-working in place.  Pericles is largely used to manage the recovery process within Revenues with only a few letters being produced in Civica whereas Benefits produce all letters in Civica.  LLPG data is not used currently and neither is e-Benefits.  The hot key function between Pericles and Civica works well and both ways.  First point of contact for support is IT, who carry out patch releases etc and systems administration is carried out by the service areas.  Civica is deployed as the corporate EDMS (document management) system; this means that under a shared Revenues and Benefits service their EDMS will need to integrate back to the corporate EDMS at Allerdale so that all documents can be viewed from a single point.

Northgate position re Pericles and impact at Allerdale.  There is another very important consideration in relation to Allerdale.  During the course of the Business Case project Allerdale were informed by Northgate that they intended to phase out support of the Pericles product starting in October 2010.  Revenues and Benefits core software is vital to the council’s ability to operate an effective Revenues and Benefits service.  By its nature this software has to be frequently updated to reflect legislative changes and it would not be possible to operate a service with unsupported software.  An obvious route might have been to simply choose to switchover to the Capita Academy software as used by both Carlisle and Copeland.  However, procurement rules precluded this approach.  In the light of these circumstances, the Project Board decided to undertake a “market-testing” tender exercise to evaluate core system options not only for Allerdale but also for a potential three-council shared service requirement.  This approach would uncover whether a “new” system for the shared service could deliver savings for the core software system.  The results of this exercise are covered in more detail below.

- Carlisle – use Capita’s “Academy” Revenues and Benefits system along with Northgate’s Information@Work EDMS and Workflow to process Revenues and Benefits work, as does Copeland, although the systems are on different versions/patch releases.  However, these are not as deeply integrated as Allerdale and workflow is not as extensive.  CRM is not integrated at all and front office staff use the same forms as the customer which are filled in and then passed to the back office (CSC Agents don’t update the system directly).  Once the call is a work item then all customer contact is with the back office.  LLPG data is not used.  There is extensive manual form filling (and manual passing of data) which is then scanned and Northgate is used for Change of Address (e.g. memo indexed to Benefits, Benefits stop benefit, memo sent to Council Tax to change address etc).  Barcode technology is not used.  Carlisle has the more flexible payment options for Revenues.  e-Citizen is about to go live for viewing Council Tax information.  Data downloads are sent to Bailiffs.  Cash is still taken and Post Office swipe cards are used.  For Benefits, calls come in to a Customer Services team in Benefits and there are some front office staff in the Contact service Centres.  All work is driven through Northgate.  Post is scanned in by a separate team within Benefits. Mobile working is being used by downloading key data, completing a form and then uploading a PDF into Northgate.  Looking to use e-Benefits for requests by phone or through Contact Service Centres.  The hotkey function between Capita and Northgate works but problems are experienced.  IT provides the support for patch releases etc and systems administration is undertaken through Academy help desk.  Northgate is not a corporate system but there is some minor use by Creditors.  The Capita core system has been in place since 1993.  Carlisle use Post Office cards and there is an interface to the Post Office which sends data for card generation.  Home Working is widely used within the Housing Benefits team with approximately 10 Home Workers currently.

- Copeland – also use Capita’s “Academy” Revenues & Benefits and Northgate’s Information@Work EDMS and Workflow to process Revenues and Benefits work.  The Contact Service Centres take basic queries and log them on the CRM system and the request is then emailed or phoned through to the processing teams in the back office.  In Revenues work is allocated alphabetically and the recovery process is started from the reminder stage onwards (Carlisle recovery process is from summons onwards).  Paper forms are filled in, the work is completed and system updated.  Once the system has been updated, then the forms are scanned. Change of Address is emailed from Revenues to Benefits if urgent or through Northgate if not.  For Benefits, calls are passed on to Benefits Officers (on a rota basis) to deal with.  All work received is scanned but not verified as ready and all work is initiated through Northgate (Contact Service Centres have access to both the Capita Revenues & Benefits systems).  A clerical post team do the scanning.  Barcoding is used on CTax bills.  No cash is taken in the offices and Corporate pay point are used.  Technical software patch updates and upgrades are done remotely by Capita.

Customer Relationship Management systems (CRM) - All three Councils are using different CRM systems (Northgate, Capita and Experion) with little or no integration.  All three Council’s use the same Cash Receipting system (Civica ICON)

In summary, all three Councils are operating independent processes and systems (even though some are the same systems); there are currently no links between the three Council’s data and this would still be the case in the shared service.  In other words, the separation of each council’s data would remain although staff in the shared service could work on any council’s data as required.

Key options for the various possible system combinations of ‘core system’ and Document Management System.

Analysis has taken place of the options to deliver a system to support the recommended Option of Joint Service Delivery.  This section outlines how an ICT architecture could be deployed to realise the benefits of Joint Service Delivery.  Should approval be given to this Business Case and the introduction of the Shared Service proceeds, this will be developed further into a full implementation plan.

The following diagram illustrates a possible overlapping integration architecture that could help fully realise the benefits of the implementation of integrated systems (and assuming the future use of e-Benefits).

The architecture depicted in this diagram supports a Joint Service Delivery Shared Service that takes the form of a single service with a single management team running across the three sites.

The technical infrastructure would consist of a single Revenues & Benefits system with a single Electronic Document Management & Workflow System which would integrate with the three different CRM systems and the relative Contact Service Centres. Note that each Council’s data would be separately stored within this standardised framework.  Integration and interfaces would also be needed to the three Councils’ other systems (e.g. Financial Management Systems) which may also use the integration tools shown below.

The diagram below depicts the high level view of how the data flows could be introduced:

Areas where further investigation will be undertaken by the shared service.   There will be a number of areas where the implementation project will need to work with the Shared Service management and with key ICT suppliers to resolve a number of issues including:

- The EDMS solution will need to integrate back to Allerdale’s Corporate EDMS so that the Council’s Corporate Strategy of a ‘single view’ of the customer is maintained.

- The overall project will need to identify in detail how the existing systems will operate during the interim period of implementation.

- There are three different CRM systems and it will be paramount to the Shared Service that information and processes are carried out in the same way.  This raises a number of areas will need to be addressed during implementation, including:

    - ICT tools / middleware may be needed to ensure that data originating from the three individual CRM systems is presented in exactly the same way to the back office systems.  Information may also need to be pushed out to the CRM systems and this will need data to be taken from the back office system(s) and pushed through to CRM and presented in the appropriate way.

    - There are challenges in linking the person to the property at the CRM level and linking it to the back office systems with use of appropriate reference numbers.

System Resilience.  The Allerdale/Carlisle ICT Shared Service will be deploying infrastructure to make use of their two data centres via a dedicated telecoms link.  This can be exploited as part of an overall resilience strategy that will support business continuity to the three Shared Service sites.  The diagram below illustrates how the technical infrastructure might be deployed to support this.

In this model the loss of one data centre or a network segment will not mean complete loss of service as there is in-built resilience.  As part of the implementation process a number of areas would need to further investigation with suppliers, including:

- What size/type of data links will be required between Copeland and the data centre sites at Allerdale and Carlisle.

- What client configuration will be used at Copeland.

- Confirmation that if one data link goes down then how the other sites can still access the core systems.

- How Mobile Workers and Home Workers will access the system in the proposed solution.

- Server configuration across the two sites.

- How existing hardware/servers can be reused.

- Back up links required.

“Market Testing” of the core Revenues and Benefits software

As mentioned above, Allerdale have a major risk in that Northgate, the supplier of their current core Revenues and Benefits software package, Pericles, have announced that support for the product is being withdrawn from October 2010.  Whilst this was an unforeseen problem when the project was started, the consequences of this major risk have been considered by the Project Board and it has provided an opportunity to undertake a “market testing” exercise for the core software package for a full shared service.  In addition, the market testing exercise has also evaluated the software options for Allerdale in “standalone” mode, should it be determined that a Revenues and Benefits shared service is either not approved by one or all councils or it cannot be delivered in time for the 2010 Pericles support withdrawal deadline.

To complete the market testing exercise in a short timescale, based upon a comprehensive specification, external consultants Q2 Ltd were engaged to support the tender process.  (Q2 have successfully undertaken a similar procurement exercise for the Worcester Revenues and Benefits shared service).  The OGC Catalist procedures were used.  Catalist comprises a number of categories of products and services that have been pre-tendered (under full OJEU European rules) by OGC and a limited list of suppliers approved.  The tender for the “North West Cumbria Revenues and Benefits Shared Service” core ICT software was publicised via Catalyst in May and supplier responses required by the end of that month.  Only two suppliers responded (noting that the number of potential suppliers is no more than 4), one to confirm that they would not submit a tender response and the other, Capita Software submitted a full response to the tender.

Whilst disappointing that only a single supplier response was received, it has nevertheless been fully evaluated in terms of functionality and compliance with the business requirement, as well as cost comparison with current operations.  Obviously, the Capita solution (Academy) is already running two out of three of the councils so the main issues were (i) does their proposition for a new contractual arrangement for the three council shared service represent better value for money than the current contracts for Carlisle and Copeland as single users and (ii) for Allerdale, does it provide a viable new system solution to replace Pericles in terms of both functionality and affordability.

The evaluation and the tender process was lead by the Procurement Manager, Carlisle City Council on behalf of the project; the evaluation team included practitioners and IT staff from all three authorities.

# Footnotes

www.meritec.co.uk

See the 2004 review ‘Releasing Efficiencies to the Front Line’ by Sir Peter Gershon CBE at http://www.lcpe.gov.uk/Library/National_Strategies/gershon.pdf

See the 2006 review 'Service transformation: A better service for citizens and businesses, a better deal for the taxpayer' by Sir David Varney at http://www.hm-treasury.gov.uk/media/4/F/pbr06_varney_review.pdf

See http://www.cio.gov.uk/shared_services/introduction/

Cumbria Improvement and Efficiency Partnership www.ciep.org.uk

Note that during the course of this project the software supplier announced that it would not be supporting the Pericles software product after 2010; in the light of this, the Project Board decided to undertake a market testing of the main IT system for the Revenues and Benefits Shared Service

North Cumbria Shared ICT Business Case – Allerdale Borough Council/Carlisle City Council July 2008

Financial support from Cumbria Improvement and Efficiency Partnership (CIEP) assisted with this exercise.

See http://www.lge.gov.uk/lge/core/page.do?pageId=119175

Office of Government Commerce www.ogc.gov.uk

# Text boxes

Figure A – Location Y – Benefits Focus

(inc Appeals & Fraud)

Figure B – Location X – Performance Focus

(inc Post Handling)

Figure C – Location Z – Revenues Focus