| REPORT TO EXECUTIVE |
| --- |
| PORTFOLIO AREA: Promoting Carlisle |
| Date of Meeting: | 18th January 2010 |
| Public |  |
| Key Decision: | No | Recorded in Forward Plan: | No |
| Inside Policy Framework |

| Title: | Refreshing the Community Plan |
| --- | --- |
| Report of: | Policy and Performance Manager |
| Report reference: | PPP 02-10 |

Summary:

This report presents the framework proposed for refreshing the Community Plan.

Recommendations:

It is recommended that the Executive:

- Consider and comment on the proposed timetable to refresh the community plan.

- Request Overview and Scrutiny Panels to consider and comment on the refreshed plan in due course.

| Contact Officer: | Steven O’Keeffe | Ext: | 7258 |
| --- | --- | --- | --- |

- BACKGROUND INFORMATION AND OPTIONS

The Local Government Act 2000 requires local authorities to publish a Sustainable Community Strategy. Carlisle City Council first approved “A Community Plan for Carlisle 2007” at its meeting on 01 May 2007 in accordance with its responsibility under The Local Government Act 2000 requiring authorities to prepare a Sustainable Community Strategy or Plan for their area. This plan was refreshed in April 2008, adopted by Full Council on 29 April 2008 and to the Carlisle Partnership Executive at its meeting on 12 May and published at the Partnership Annual General Meeting 25 June 2008.

The changes in the Countywide Strategic Partnership and new proposals for collaboration on a single Community Plan for Cumbria are important developments. This new proposal (Leading Cumbria Together in Partnership 28 October 2009) provides an option for the Local Strategic Partnership to dovetail its planning with the Countywide Strategic Partnership. It is important that the Local Strategic Partnership has a separate plan around which it can rally its delivery groups.

- RECOMMENDATIONS

It is recommended that the Executive:

- Consider and comment on the proposed timetable to refresh the community plan.

- Request Overview and Scrutiny Panels to consider and comment on the refreshed plan in due course.

- REASONS FOR RECOMMENDATIONS

The reason behind the first recommendation is to establish the supportive role the council is going to play in producing the new Community Plan. The second recommendation is to ensure that overview and scrutiny include this plan in their work programme for 2010.

- CONSULTATION

This timetable is drawn from the initial Carlisle Community Plan (2007) and the refresh (2008). It is indicative of the detailed work that lies ahead and will develop as priorities are reassessed.

| Group | Date |
| --- | --- |
| Carlisle LSP Executive | 8th February 2010 |
| Carlisle City Council Executive | 15th March 2010 |
| Overview & Scrutiny Committees | March 2010 April 2010 |
| Conveners Group | 15th March 2010 |
| Local Thematic Groups | April 2010 May 2010 |
| Countywide Thematic Partnerships | To be confirmed |
| Carlisle LSP Executive | 17th May 2010 |
| Carlisle City Council Executive | June 2010 |
| Carlisle Partnership AGM (launch event) | 21st June 2010 |
| Full Council | July 2010 |

- IMPLICATIONS

  - Staffing: The production of the Community Plan will be undertaken by Carlisle City Council, Communications and Policy and Performance Teams.

  - Finance: There will be modest budgetary implications with regard to publishing the Plan, which can be met from within existing budgets.

  - Legal: The production of a Sustainable Community Plan for Carlisle is a statutory obligation for the City Council. (Local Government Act 2000).

  - Corporate: The City Councils new corporate plan will be an element in the network of plans co-ordinated with the Community Plan.

  - Risk Management: Risks will continue to be managed in accordance with the Risk Management Policy.

  - Equality & Diversity: The Sustainable Community Plan is designed to have positive effects on Equality and Diversity within the area and the plan will be impact assessed in accordance with City Council scheme.

  - Environment: The Environment has been identified as a cross-cutting theme by the Carlisle Partnership.

  - Crime and Disorder: The perceptions and confidence of citizens concerning crime and disorder continues to be a key element of the community strategy for Carlisle.

  - Rural issues: Rurality has been identified as a cross-cutting theme by the Carlisle Partnership.

  - Impact on Customers: – The purpose of the Plan is to describe the partnership vision for the area and how it can deliver that vision through its sub groups.