Carlisle and Eden Local Health Group meeting on 21 September concentrated on Physical Activity schemes, which had been considered the top priority for healthy life styles by members at the previous meeting.  The theme for the November meeting will be ‘Healthy Eating’.

Attended Cumbria Sub-Regional Housing Group meeting where it was clear that major funding will come to the Region via county wide strategy, but still vital to have a Carlisle Strategy as proof of justification for bids against funds.

Raffles Community Forum meeting, pleased to note that there is evidence that residents are now more confident in the strategy with the progress with new build.

Attended the launch of the Millennium Project Conference of Archaeologists and again assured of great international importance of finds from various Carlisle digs.

Spent an enjoyable hour as guest of Hallbankgate School as Bring your Councillor to School part of Local Democracy Week.

Carlisle Castle Development Group met and clear that citywide strategy will be required to ensure Heritage Developments are complimentary and not competitive.

Sure Start Carlisle South soft play area at Harraby Community Centre has started construction and Petteril Bank Project is ongoing, school section completed community sections still under construction.  Carlisle South Officers have given advice and guidance to Longtown Project.

Consultation underway on potential developments at Greystone Community Centre.

Sheepmount new track fully laid and waiting for lines to be painted.  Work due to start on re-roofing of old changing rooms.

Tenders received for front entrance and restaurant extension to Sands higher than available budget, discussions to take place to modify scheme to available budget.

Outline drawings received for improving Stony Holme clubhouse for consideration and plan to implement Autumn 2005.

Plan drawn for new play area at Fusehill Street to be considered upon with local community.

R Knapton

Health and Community Activities Portfolio

# Text boxes

PORTFOLIO:

HEALTH & COMMUNITY ACTIVITIES

Report of

Portfolio Holder:

COUNCILLOR

R KNAPTON