3. Affordability & Balancing the Housing Market

| Issues | Actions | Targets | Milestones | Outcomes | Action Owner & Support | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 Substantial property price increases in Carlisle, 90% in 2 years & 54% in 12 months to June 2004, & lower than average wage levels, mean local people unable to get onto the property ladder; price rises mean that even discount schemes are becoming unaffordable 3.2 Impact on labour market and building and sustaining broad economic base when house prices restrict movement of labour, particularly young people | Strengthen section 106 policy in Local Plan in collaboration with planning to secure affordable / shared ownership units and / or commuted sums on new developments | 25-30% of developments to be affordable/social units and/or ‘commuted sum’ payments; based on need and site development cost |  | A rise in affordable housing that is appropriate for the needs identified, i.e. family homes, homes in rural areas Housing aspirations of local people satisfied through outright / shared home ownership Affordable homes retained for perpetuity through shared ownership and homes to rent (as opposed to discount schemes) Community Plan objectives: 1, 2, 3, 4, 5, 6, Corporate Plan promises: 1, 2, 3, 4, 5 | Kamla Pattni, Carlisle City Council Tel 01228 81723 e-mail: KamlaP@carlisle.gov.uk | £100,000 per annum potential commuted sums £4million from Regional Housing Board for the sub-region for affordable housing 2005 depending on scheme(s) put forward Potential £4million 2006 £100,000 capital bid for grants to RSLs, yrs 1-4 |
| 3.3 Escalation of Right to Buy since LSVT has meant a reduction in social, rented accommodation, especially family homes (around 700 total) 3.4 A number of neighbourhoods unsustainable due to a range of social & economic factors leading to low demand for social housing | Produce a development plan which seeks to redress balance of social housing options | Within development plan for CHA | Plan produced by December 2004 | Ways in which the offer of social, rented housing may be improved are identified to increase availability of accommodation, especially family homes, to meet need Community Plan objectives: 1, 2, 3, 4, 5, 6, Corporate Plan promises: 1, 2, 3, 4, 5 | Laurie Brewis, Carlisle Housing Association | Plan commissioned by CHA Bid to Housing Corporation Land for development |

| Issues | Actions | Targets | Milestones | Outcomes | Action Owner & Support | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| 3.5 Cumbria not seen as a priority area in the Northern Way Strategy, 2004, i.e. a peripheral rather than Core City area, so some potential funding streams restricted 3.6 Housing Corporation’s “total cost indicator thresholds” leads to difficulties in putting together viable schemes | Lobby at sub regional level so Cumbria’s needs, including Carlisle, reflected in Regional Housing Strategy, currently being reviewed. To put particular emphasis on total cost indicator thresholds | Draft regional statement submitted October 2004 | Draft Regional Housing Strategy published November 2004 | Housing priorities of Cumbria recognised in Regional Housing Strategy to help secure additional £s resource Carlisle (& sub-region) builds track record on delivering schemes Community Plan objectives: 1, 2, 3, 5, 6, 8 Corporate Plan promises: 1, 2, 3, 4, 5 | Simon Taylor, Carlisle City Council | Existing staffing resource but with additional support from Audit Commission & GONW through Cumbria Housing Improvement programme & Achieving Cumbrian Excellence programme (ACE) |
|  | Sign-up to development of housing strategy for the sub-region | Formal commitment from Carlisle, January 2005 | Within project plan for strategy, 2005 onwards |  |  |  |
| 3.7 Planning constraints mean moratorium on [open market] rural house building reduces to zero number of new homes developed | Continue to progress housing developments in rural areas; Longtown- permission granted; Burgh by Sands & Cumrew – may come within “exceptions” scheme | 4 affordable units developed Longtown, 2004-2005 8 units developed Burgh by Sands, 2005-2006 Carry out housing needs survey, Cumrew, June 2005 | Submission to Housing Corporation to support Longtown, December 2004 Burgh by Sands bid, June 2005 | Increase in affordable housing in rural areas leading to more sustainable communities Housing needs survey to inform future development plans Community Plan objectives: 1, 2, 3, 5, 6, 8 Corporate Plan promises: 1, 2, 3, 4, 5 | Kamla Pattni Support from Impact (Longtown) & Two Castles (Burgh by Sands) | Housing Corporation £s -support to be determined |

| Issues | Actions | Targets | Milestones | Outcomes | Action Owner & Support | Resources |
| --- | --- | --- | --- | --- | --- | --- |
| 3.8 There is insufficient information on housing need, especially rural & BME population, young and older people | Work in the sub-region to develop a robust database of evidence of housing need that may be used with other intelligence on demographics, employment, crime and disorder, health, etc | To be agreed in the sub-region by the project group To review & update the database on an ongoing basis, but at least annually | Enabling Officer in post, September 2004 (temporary) For Carlisle: Phase 1 – Morton area, October 2004 Phase 2 – Stanwix, Upperby & up to 3 rural parishes, April 2005 Database reviewed & updated April 2006 | Greater understanding of housing needs for the council & its partners in Carlisle & in Cumbria More robust negotiations possible with private house builders in determining Section 106 agreements, based on need & priorities More robust proposals for funding to the Housing Corporation (and others) for schemes based on need and priorities Greater understanding of broader well-being and contribution to sustainable communities, particularly the impact that housing can have Community Plan objectives: 1, 5 Corporate Plan promises: 4, 5 | Simon Taylor, Carlisle City Council | Existing housing & planning staff within the 6 Cumbrian districts & Cumbria County Council |
|  | Work with other agencies, especially social services, health, social & private rented sector & lenders to improve intelligence about housing markets and need |  |  |  |  |  |
|  | Link to Cumbria wide Race & Diversity group to improve information on needs of minority groups |  |  |  |  |  |
| Issues | Actions | Targets | Milestones | Outcomes | Action Owner & Support | Resources |
|  | Establish methodology to carry out research with new recipients of Council Tax bills | Survey 50% new recipients by April 2006 | Survey 10% new recipients by April 2005 | As above | Kamla Pattni | Existing staffing resource |
| 4. Monitoring & Evaluation |
| Issues | Actions | Targets | Milestones | Outcomes | Action Owner & Support | Resources |
| 4.1 The action plan to deliver the Housing Strategy for Carlisle should be regularly monitored and reviewed to check on progress The action plan should be updated to reflect targets achieved and changing local, regional and national priorities | Review governance arrangements for the delivery and performance management of the strategy and action plan including a review of the roles and functions of individual partners, officers and groups, such as the internal and external Housing Strategy groups Regularly review progress of action plan; each action owner to provide updates to review group Update as; -targets and milestones achieved -new priorities and opportunities emerge -evidence of changing needs & demographics is gathered | Review governance arrangements by March 2005 including membership and terms of reference for housing strategy group(s) Progress reviews held every 3 months to raise awareness of issues for all stakeholders Annual review of priorities and resources to update action plan | Housing strategy review group(s) in place March 2005 1st review July 2005 & every 3 months thereafter First annual review in time for budget process 2005-2006, November 2005 | Priorities that were identified to deliver a better housing service to the people of Carlisle are delivered, improving general health & well-being Success may be celebrated as targets achieved New priorities are identified that reflect changes in the internal & external environment Community Plan objectives: 5 Corporate Plan promises: 4, 5 | Chair of Housing Strategy group | Housing Strategy group(s) including Carlisle City Council & strategic partners |

Key:

Community Plan objectives

- Communities - to ensure that people from all sectors of our local communities have equal access to services represented by the Local Strategic Partnership; that all our communities are safe and attractive and that participation and influence in the decision-making process across all sectors is significantly increased.

- Health and Well-being – to improve the health and well-being of our communities by reducing health inequalities, promoting healthy living and supporting locally accessible, high quality health care.

- Economy – to support and develop and economically sustainable and prosperous area where investment is encouraged, skills are developed and retained and new and existing businesses are supported.

- Young People – to provide a framework where children and young people can thrive and improve their life chances.

- Housing – to support the development and maintenance of decent, affordable housing and related services which meet the needs of local people and support economic and community development.

- Environment – to protect and enhance our environment

- Transport – to assist in the development of an effective, accessible and sustainable transport system.

- Promoting Carlisle and Eden – to promote the heritage and unique qualities of the area both locally, nationally and internationally.

## Corporate Plan promises

- To ensure Carlisle is a safe and attractive place where people are included and feel they belong.

- To develop a sustainable economy.

- To manage our environment responsibly.

- To improve local housing, health and well being.

- To provide sound Council management.

# Footnotes

Large Scale Voluntary Transfer [of Council owned housing stock]

The Housing Corporation’s method of assessing costs related to house development in different parts of the country; includes cost of land, house building, etc

Government Office North West