CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 24 July 2008 |
| Title: | PAY AND WORKFORCE STRATEGY PROJECT UPDATE |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 19/08 |

Summary:

The project has now entered its final stage (Implementation). An Action Plan has been drawn up for this stage and work is underway.

Questions for / input required from Scrutiny:

Members to monitor progress.

Recommendations:

Members to note progress and comment as appropriate.

| Contact Officer: | David Williams | Ext: | 7082 |
| --- | --- | --- | --- |

- BACKGROUND INFORMATION AND OPTIONS

1.1	The Pay & Workforce Strategy (PWS) project is being delivered, in partnership with the Trades Unions, through 6 work packages, i.e.

- Job Evaluation

- Equal Pay Review

- Review of People Policies and Terms and Conditions

- Single Status

- Workforce Development Plan

- PWS Implementation.

  - The project is in accordance with Prince 2 methodology and as such is overseen by a Project Board chaired by the Deputy Chief Executive. Regular progress reports are presented to Members of the Corporate Resource Overview and Scrutiny Committee, with the last one being 12 June 2008.

  - The project has now entered its final stage (Implementation). An Action Plan has been drawn up for this stage and work is underway. This plan also embraces the remaining actions that will complete the other work packages. Progress is reported in the right hand column of this plan. See Appendix 1.

- RECOMMENDATIONS

2.1	Members to note progress and comment as appropriate.

### PWS Implementation Action Plan May 2008 – March 2009

|  | Main work package | Tasks | Who leads | Duration | Target date | Progress @ 15/07/08 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Implement PWS | Draw up a pay policy; Principles Research market Consult (SMT, Members, unions, staff) Tie in with Single Status | Project Manager (DW) assisted by (new) Implementation Officer | 1 month | End of July 2008 | An Implementation Officer (Agency worker funded by Carry Forwards) started on 1 July. Research is underway. Unions have formally asked for 6 years ‘back pay’ and 3 years ‘protection’. The management response awaits 1.2 |
| 1.2 |  | Devise a pay structure: JE scores (see 4.1) Research markets for pay rates Pay modelling Costs Consult (SMT, Members, unions, staff) | Project Manager assisted by Implementation Officer, plus Payroll plus Finance | 1 month | End of August 2008 | Research underway. Training in the Pay Modellor has been arranged for new staff. |
| 1.3 |  | Member approval (Executive, CROS, Employment Panel, Council?) | Deputy Chief Executive | 1 month | End of September 2008 | Portfolio Holder is in the loop |
| 1.4 |  | Assimilate staff to new pay structure | Implementation Officer assisted by (new) Personnel Officer and unions | 1 month | End of October 2008 |  |
| 1.5 |  | Issue revised Statement of Provision to staff | Implementation Officer assisted by P&D staff | 1 month | End of October 2008 |  |
| 1.6 |  | Amend Trent so as to insert new staffing structure | P&D staff | 3 months | End of December 2008 |  |
| 1.7 |  | Implement outcomes of Phase 2 Job Evaluation (see 4.2) as in 1.3 – 1.6 above | Personnel Manager assisted by (new) Job Evaluator | 5 months | End of March 2009 |  |
| 1.8 |  | Consolidate implementation – documentation, correct job titles, clear reporting lines, updated job descriptions | Implementation Officer and (new) Admin Asst | 2 months | End of May 2009 |  |
| 2.1 | Single Status | Complete research and assessment of areas yet to be harmonised: Professional fees Extent/pay for shift work/premia payments Car allowances/leases Additional duties/Acting up Other allowances – tool, bonus, first aid, E planning, other representative roles etc Flexi/flexible working1 Time sheet removal1 | Personnel Manager assisted by Implementation officer and Personnel Officer – input also from P&D staff, some Service Heads and unions | 2 months | Proposals consulted on by end of August 2008 | Research underway and some practices reviewed. Initial proposals have been drafted e.g. professional fees, car allowances / leases, and discussions are underway with managers and with unions. |
| 2.2 |  | Cost and draft proposals | Personnel Officer | 1 month | End of July 2008 | Await Council approval to employ extra PWS staff |
| 2.3 |  | Consult on proposals | Personnel Officer | 1 month | End of August 2008 |  |
| 2.4 |  | Draw up final proposals & link to implementation | Personnel Officer | 1 month | End of August 2008 |  |
| 3.1 | Equal Pay | Assess current picture | Implementation Officer | 2 weeks | End of July 2008 | Analysis of the equal pay structure breakdown is underway |
| 3.2 |  | Carry out Equality Impact Assessments on proposed new pay structure(s) | Personnel Officer | 3 weeks | End of September 2008 | Work will start upon completion of 1.2 |
| 3.3 |  | Identify and explore validity of any outstanding Equality concerns | Personnel Officer | 1 month | By December 2008 |  |
| 3.4 |  | Create a draft action plan to address issues – including consultation as appropriate | Personnel Officer | 1 month | End of December 2008 |  |
| 4.1 | Job Evaluation | Complete Phase 1 (existing scored jobs): Complete all appeals Notify staff of outcome Publish scores Pass information to Pay Modeller in a form it can be used (see 1.2) | Workpackage Leader (CM) and Project Manager assisted by P&D staff | underway | End of August 2008 | Appeals are on schedule to be completed by 8 August. |
| 4.2 |  | Phase 2 Job Evaluation: Obtain information to allow outstanding jobs to be scored – new/amended jobs since Autumn 2007 Temp jobs anticipated to have gone but have not Casuals Career grades Arrange panels & type up/distribute the information Support and participate in Steering Panels Obtain any additional information required Support and participate in Appeal Panels Notify and publish scores Complete documentation See also 1.7 above | Personnel Manager assisted by Job Evaluator and Admin Assistant | 5 months | End of March 2009 |  |
| 4.3 |  | Complete documentation to enable it to be easily retrieved when required | Job Evaluator and Admin assist. | As in 4.2 | End of March 2009 |  |
| 4.4 |  | Set up an ongoing (‘mainstreamed’) Job Evaluation arrangement so as to score all new and changed jobs occurring after the end of the PWS project. Agree this with unions and Employment Panel | Personnel Manager | 1 month | To operate from 1 April 2009 |  |
| 5 | General – all packages | Document and monitor project and highlight any issues and potential slippage Draft and produce reports, briefing notes, consultation documents, PWS Board reports, minutes CJC at intervals Inform Portfolio Holder throughout CROS at intervals Communication e.g. surgeries, road shows, presentation, newsletters etc | Project Manager assisted by Implementation Officer | underway | End of March 2009 | Bid to draw down more money (for 4 new staff) has been endorsed by the Executive and goes to Council 15 July. Executive has also endorsed PWS Action Plan, which has been scrutinised by CROS. Council to be updated by Portfolio Holder on 15 July. A 2007/8 Budget Carry Forward was approved by the Executive but with 20% reduction. JE briefing for staff issued. Is an agenda item for the Management Briefing on 6 August |

# Footnotes

1 Timing not essential for PWS Implementation