| REPORT TO EXECUTIVE |
| --- |
| PORTFOLIO AREA: PERFORMANCE AND DEVELOPMENT |
| Date of Meeting: | 16 February 2010 |
| Public |  |
| Key Decision: | No | Recorded in Forward Plan: | No |
| Inside Policy Framework |

| Title: | CORPORATE PERFORMANCE MONITORING REPORT, 3rd QUARTER REPORT (April to December 2009) |
| --- | --- |
| Report of: | Policy & Performance Manager |
| Report reference: | PPP 06/10 |

SUMMARY:

This report presents the performance of the Council for the third quarter 2009/10.

RECOMMENDATIONS:

The Executive Committee is requested to:

- Consider and comment on the information contained in the report with a view to seeking continuous improvement in how the Council manages performance and monitors the new priorities.

- Consider how current performance and satisfaction levels inform the Transformation Programme and budget process.

- Refer the report to the relevant Overview and Scrutiny panels for consideration.

| Contact Officer: Gary Oliver |  | Ext: | 7430 |
| --- | --- | --- | --- |

- REASONS FOR RECOMMENDATIONS

The recommendations are made to ensure the ongoing development of the performance management framework. This report should assist in monitoring performance against the priorities and targets.

- BACKGROUND INFORMATION

This is the first quarterly report under the new priorities of ‘Economy’ and ‘Local Environment’. The City Council continues to develop its performance management framework in order to ensure an evidence base for decision making.

- IMPLICATIONS

- Staffing/Resources: The Policy & Performance Team is preparing a new framework that will eliminate any gaps in performance monitoring created as a result of closing the old priorities.

- Financial: Work continues to integrate performance and financial monitoring data and information.

- Legal: None.

- Corporate: The development of the new performance framework informs the new Corporate Plan for 2010/11 onwards.

- Risk Management: The risk of not addressing under-performance is managed through the Corporate Risk Register.

- Equality and Diversity: The Authority is on target to achieve this in the stated timeframe. A Single Equality Scheme is currently being developed that will assist with this process.

- Environmental: As this is now a priority, the National Indicators and local indicators that measure performance in this area will continue to be developed.

- Crime and Disorder: Monitored by the Crime and Disorder Reduction Partnership.

- Impact on Customers: New management information on satisfaction through the customer contact centre and the use of GovMetric will allow more regular assessment of satisfaction levels with key service.

Quarter 3 Performance Report

Year to date 2009/2010

Table of Contents

Executive summary	4

Overview of performance	4

Corporate Health	4

Personnel	4

Satisfaction	4

Priorities	5

Economy	5

Environment	5

Appendix A: Key to tables	7

Appendix B: Performance Tables	8

# Executive summary

This is the 3rd Quarter Performance Report for 2009/10. It contains all the indicators that the Council currently monitors on a monthly or quarterly basis.  Unless stated the report covers the period April 2009 to December 2009.  It is the first report that examines performance under the new priorities of Economy and Local Environment.

The table of indicators (Appendix B) has been amended to include the year-to-date figure for the same period last year and the forecasted year-end value. Because of the lack of quartile information available, the quartile position column has been removed.

# Overview of performance

Performance is generally very positive overall and for the new priorities.  There are only 6 out of all 41 indicators with targets that are significantly off target (red). 8 out of 15 “Economy” indicators are meeting the target and 5 are just outside (amber).  This ratio is similar for the “Environment” indicators where half of the 8 are on target and 3 are nearly there (amber).

# Corporate Health

## Personnel

Sickness absence (LI912) levels in the Authority continue to show a marked improvement on last year. In the eight months up to the end of November there were 5.42 working days lost per full-time equivalent (FTE) employee.  This is compared to 7.85 days for the same period last year.  Based on the current rate of absence, performance is set to be around 8.5 days by the end of March 2010.  This would be a drop of almost 30% on last year.

Much of this improvement is due to a considerable reduction in the proportion of sickness absence that is long-term (over 28 days), currently 44% of absence is long-term compared to 60% last year.  This change has occurred partly as a result of a change of focus by SMT in addressing long-term absence but also through ill-health retirements or a phased return to work. Hard work from managers supported by Personnel Officers and improved consultations between managers and Wellwork (our Occupational Health provider) have also significantly contributed.

Flexitime accrued by employees continues to be high.  This is unlikely to change until a more robust flexi policy is implemented and adhered to.

## Satisfaction

The overall satisfaction with the range of services measured by Govmetric system is “Average.”  The email module of GovMetric is now live so feedback is now recorded from three strands – Carlisle City Council Website, Customer Contact Call Centre and email correspondence.

Positive customer feedback is counted as 1, negative as -1 and average as 0.  The scores in the table below are an average of the feedback received for each service area.  To be “Good” the average score should be above 0.5, “Poor” is below -0.5 and “Average” is between -0.5 and 0.5.

The overall score for the quarter was 0.34 compared to 0.42 in the previous quarter.  The volume of telephone feedback levels was particularly low (158 compared to 484 in Q2) so to boost the sample the Call Centre are to concentrate their efforts in obtaining feedback for one day a week.

2 out of 11 service areas were classified as “good” and none as “poor.”

These indicators can be neatly used in conjunction with the Place Survey results to enhance service monitoring.

# Priorities

## Economy

In general, the Authority is performing well in the indicators under the priority of Economy.  Despite still being off target the percentage of available units let (LI913C1) increased in Quarter 3.  However, this is likely to be due to the festive period so target is still likely to be missed by year end.

The NI157 range of indicators relating to planning applications are all on target which is excellent considering the loss of key personnel in that department.  It should also be noted that the number of applications made is greater than in recent quarters.

The data around NI180 (the number of changes in circumstances which affect customers’ benefit entitlement) continue to cause us problems.  There is no data available for Quarter 3 in the central Housing Benefit Operational Database (Hobod)

so an estimate has had to be made.

Further work is ongoing to develop the performance framework around this priority.

## Environment

New indicators relating to fly tipping have been introduced to give a better view of how effectively we are combating fly tipping in the District. The existing measure, NI196, will now only be reported annually and the number of incidents of fly tipping (MI796a) and the number of enforcement actions taken against fly tippers (MI796b) will be reported monthly and quarterly instead.

Encouragingly the number of fly tipping incidents has fallen considerably in Quarter 3.  This could be a direct consequence of a larger than normal number of enforcement actions taken in Quarter 2.

The % of abandoned vehicles removed in 24 hours (LI317b) continues to be red, it is worth noting that 8 out of 9 vehicles were removed on time in Quarter 3 (21 out of 25 for the year to date).  Despite Quarter 4 having historically the greatest number of abandoned vehicles, we are unlikely to meet target for this indicator.

The waste indicators continue to be on target.  Whilst the proportion of waste recycled continues to be above 50%, the key point here is that the residual waste per household is falling.  It will be interesting to see what impact the disruption to household waste collections due to the ice and snow in January has on both the waste indicators and the fly tipping indicators.

# Appendix A: Key to tables

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 | December 2009 | 2009/10 | 2009/10 Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 08/09 Year to Date | 09/10 Year to Date | Year-end Forecast |  |  |  |  |
| LI*** |  |  |  |  |  |  |  | Aim to maximise |  |
| NI*** |  |  |  |  |  |  |  | Aim to minimise |  |
| MI*** |  |  |  |  |  |  |  | Aim to maximise |  |
| GI*** |  |  |  |  |  |  |  | Aim to maximise |  |

# Appendix B: Performance Tables

Theme Corporate Health Promise Sickness absence and flexitime balances

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI912 | Working Days Lost Due to Sickness Absence per FTE - Formally BV12 | Councillor Earp | 7.85 (Nov 2008) | 5.42 (to Nov 2009) | 11.9 | 8.57 | 9.32 |  | Aim to Minimise | Year on year sickness is much improved and well within target. 5 out of 6 directorates on target. |
| MI913c | Proportion of sickness that is long term | Councillor Earp | N/A | 44.24% | 59.97% | 44.24% | Information only, no annual target. |  | Data Only | Long term sickness continues to fall resulting in an overall improvement in sickness levels |
| MI914a | Flexi Balance - Whole Organisation | Councillor Earp | N/A | 6,834 | N/A | 6,834 | Information only, no annual target. |  | Aim to Minimise | Balance very high due to a problem with the staff in Bousteads that were recently put on the flexi system, Zeus. They are clocking in but not working flexi. As a result, they are accruing balances but these are cleared at the end of the period. Therefore the balance is way out. Zeus have been asked for help in this. |
| MI914b | % of employees with over 10 hours flexi | Councillor Earp | N/A | 26.46% | N/A | 26.46% | Information only, no annual target. |  | Aim to Minimise |  |
| MI914c | % of employees with less than MINUS 10 hours flexi | Councillor Earp | N/A | 4.22% | N/A | 4.22% | Information only, no annual target |  | Aim to Minimise |  |

Theme Corporate Health; Service Standards Promise Carlisle City Council - Internal Services; Quality marks and measures Aim Overall contact and satisfaction

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902 | GovMetric Customer Satisfaction - All Service Areas | Councillor Earp | N/A | 0.34 | N/A | 0.34 | 0.5 |  | Aim to Maximise |  |

Theme Priorities Promise Economy Aim Asset management and review

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI931C1 | Percentage of units let as a percentage of total units available to let - Formally LP57 | Councillor M Bowman | N/A | 88.54% | 90.53% | 88.54% | 95.00% |  | Aim to Maximise | Slightly improving trend, reflecting the short term retail lettings which have arisen over the festive season. |

Theme Priorities Promise Economy Aim Benefit processing

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902a | GovMetric Customer Satisfaction - Benefits |  | N/A | 0.49 | N/A | 0.49 | 0.5 |  | Aim to Maximise |  |
| NI 180 | The number of changes of circumstances which affect customers’ HB/CTB entitlement within the year. | Councillor J Mallinson | N/A | 14072 | 7470 | 15884 | 7258 |  | Aim to Maximise | Estimate only as no recent figures published in Hobod |
| NI 181 | Time taken to process Housing Benefit/Council Tax Benefit new claims and change events | Councillor J Mallinson | N/A | 12.91 | 7.53 | 7.53 | 13 |  | Aim to Minimise | Performance is as expected at this time. It is still expected to hit target as the Q4 performance always includes a large percentage of 1-day stats that bring the yearly average significantly down |

Theme Priorities Promise Economy Aim Efficient and effective regulation

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902e | GovMetric Customer Satisfaction - Licences |  | N/A | 0.18 | N/A | 0.18 | 0.5 |  | Aim to Maximise |  |
| NI 182 | Satisfaction of business with local authority regulation services | Councillor Bloxham | N/A | 81% | 79% | 81% | 83% |  | Aim to Maximise | Satisfaction with regulatory services is higher than anticipated |
| NI 184 | Food establishments in the area which are broadly compliant with food hygiene law as a % of total food establishments | Councillor Ellis | N/A | 92.16% | 88.94% | 92.16% | 70% |  | Aim to Maximise | Overall there has been an improvement in compliance with food safety legislation. This may be due to the use of ‘off the shelf’ food safety management systems and also to the implementation of ‘Scores on the Doors.’ The nature of some of the businesses, staff turn-over and closures, makes 100% unattainable. |

Theme Priorities Promise Economy Aim Housing and homes

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NI 154 | Net additional homes provided | Councillor Bloxham | N/A | 143 | 366 | 343 | 450 |  | Aim to Maximise | Half year performance consistent with previous years. Figures anticipated to increase significantly in the second half of the year but unlikely to reach target. |
| NI 155 | Number of affordable homes delivered (gross) | Councillor Luckley | N/A | 46 | 53 | 76 | 75 |  | Aim to Maximise | Half year performance consistent with previous years. Figures anticipated to increase significantly in the second half of the year. |
| NI 156 | Number of households living in temporary accommodation | Councillor Luckley | N/A | 22 | 37 | 22 | 34 |  | Aim to Minimise | This figure is a snapshot of the number of homeless households in LA arranged temporary accommodation on the last day of the quarter. The temporary accommodation includes: Bed & Breakfast: Hostels, Women's Refuges, RSL. |

Theme Priorities Promise Economy Aim Planning and development

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902f | GovMetric Customer Satisfaction - Planning & Building Control |  | N/A | -0.14 | N/A | -0.14 | 0.5 |  | Aim to Maximise |  |
| LI902i | GovMetric Customer Satisfaction - Town Planning |  | N/A | -0.15 | N/A | -0.15 | 0.5 |  | Aim to Maximise |  |
| NI 157a | Processing of planning applications: Major applications (Target Set Nationally) | Councillor Bloxham | N/A | 70.00% | 81.82% | 70.00% | 60.00% |  | Aim to Maximise | October's monthly performance exceeded the nationally set target and brough annual performance closer to meeting it. Continued good performance should see us exceed the national target at year end. |
| NI 157b | Processing of planning applications: Minor applications (Target Set Nationally) | Councillor Bloxham | N/A | 83.41% | 77.27% | 83.41% | 75.00% |  | Aim to Maximise | The Authority is performing above the nationally set target. |
| NI 157c | Processing of planning applications: Other applications (Target Set Nationally) | Councillor Bloxham | N/A | 90.81% | 88.30% | 90.81% | 87.00% |  | Aim to Maximise | The Authority is performing above the nationally set target. |

Theme Priorities Promise Local Environment Aim Highways and Parking

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI305b | Street lights repaired within seven days - Formally LP5 | Councillor Bloxham | N/A | 97.52% | 90.22% | 97.52% | 94.00% |  | Aim to Maximise | Staff holidays and weather conditions saw a dip in performance in December however the indicator remains well above target. |
| LI902g | GovMetric Customer Satisfaction - Roads & Transport |  | N/A | -0.48 | N/A | -0.48 | 0.5 |  | Aim to Maximise |  |
| LI902h | GovMetric Customer Satisfaction - Streets & Parking |  | N/A | 0.14 | N/A | 0.14 | 0.5 |  | Aim to Maximise |  |

Theme Priorities Promise Local Environment Aim Street and environmental cleanliness

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MI796a | Incidents of fly tipping. | Councillor Bloxham | N/A | 448 | N/A | N/A | Information only, no annual target |  | Data Only |  |
| MI796b | Enforcement actions taken against Fly Tipping. | Councillor Bloxham | N/A | 335 | N/A | N/A | Information only, no annual target |  | Data Only |  |
| NI 196 | Improved street and environmental cleanliness – fly tipping | Councillor Bloxham | N/A | N/A | 1 | N/A | 2 | Annual measure, status confirmed at year-end. | Aim to Minimise | Fly tipping has increased to 74 instances in August compared 50 in (and 49 in August last year). However, Enforcement has also increased from 43 instances last month to 80 instances, representing significant improvement. This is more in the single month of August than the whole of last year put together. The April - August year to date figure for fly tipping incidents this year has made a small increase (13 incidents) on the same period for 2008. This minimal increase in fly tipping may be due to charging for special collections but iis not considered a significant problem at this time. |

Theme Priorities Promise Local Environment Aim Tackling ASB

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI317b | Abandoned Vehicles - % removed within 24 hours of required time - Formally BV218b | Councillor Bloxham | N/A | 84.00% | 98.88% | 84.00% | 99.00% |  | Aim to Maximise | No abandoned vehicles in December means performance remains static from November. |

Theme Priorities Promise Local Environment Aim Waste and recycling

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902j | GovMetric Customer Satisfaction - Waste & Recycling |  | N/A | 0.63 | N/A | 0.63 | 0.5 |  | Aim to Maximise |  |
| NI 191 | Residual household waste per household (KG) | Councillor Bloxham | 368.29 | 313.81 | 481.64 | 475.51 | 480.02 |  | Aim to Minimise | 10 kg of residual per household less then last year (less is better). |
| NI 192 | Percentage of household waste sent for reuse, recycling and composting | Councillor Bloxham | N/A | 50.53% | 48.43% | 50.53% | 50.00% |  | Aim to Maximise | Not as much hh waste sent for reuse, recycling and composting as last year but overall hh waste is less this year therefore hh waste sent to land less. Probably due to the resession. Still looking to meet annual target. |

Theme Priorities Promise Local Environment Aim General

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902d | GovMetric Customer Satisfaction - Environmental Services |  | N/A | 0.06 | N/A | 0.06 | 0.5 |  | Aim to Maximise |  |

Theme Service Standards Promise Carlisle City Council Aim Climate change and air quality

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI485 | Total Council CO2 emissions | Councillor Bloxham | 803 | 1,360 | 1,204 | 5,638 | 5,706 |  | Aim to Minimise |  |

Theme Service Standards Promise Carlisle City Council Aim Financial transactions

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI472 | % of invoices paid on time - Formally BV8 | Councillor J Mallinson | N/A | 96.48% | 98.61% | 96.48% | 98.00% |  | Aim to Maximise | P.I short of target this month. Departments failing to perform are Tullie House, Council Tax and Comm Services (Bousteads Grassing). |
| LI902c | GovMetric Customer Satisfaction - Council Tax |  | N/A | 0.79 | N/A | 0.79 | 0.5 |  | Aim to Maximise |  |

Theme Service Standards Promise Carlisle City Council Aim Overall Contact and Satisfaction

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI902b | GovMetric Customer Satisfaction - Council Info |  | N/A | -0.27 | N/A | -0.27 | 0.5 |  | Aim to Maximise |  |
| LI902k | GovMetric Customer Satisfaction - Other Services |  | N/A | 0.07 | N/A | 0.07 | 0.5 |  | Aim to Maximise |  |

Theme Service Standards Promise Carlisle City Council Aim Racial incidents

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MI 601i | Racial incidents reported |  | N/A | 0.97 | N/A | 3.47 | Information only, no annual target |  | Aim to Minimise | Racist graffiti reported to CCC in June 09. Suggested target is 7.5 |
| MI 601j | Racial incidents resulting in further action |  | N/A | 100% | N/A | 100% | Information only, no annual target |  | Aim to Maximise | Suggested target is 100% |

Theme Service Standards Promise Carlisle City Council Aim Sports and recreation

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI357a | Number of attendances of Young people using the Multi Use Games Area formal courses at:- a. Melbourne Park - Formally LP70a | Councillor Ellis | 662 | 606 | 849 | 831 | 900 |  | Aim to Maximise | Due to further profiling of the ward area and the potential clashing of events, the target for 2009/10 has been revised downwards to 900 from 1250. |
| LI357b | Number of attendances of Young people using the Multi Use Games Area formal courses at:- b. Dale End Road - Formally LP70b | Councillor Ellis | 646 | 641 | 854 | 866 | 900 |  | Aim to Maximise | Very bad weather resulting in poor numbers this month. |
| LI357c | Number of attendances of Young people using the Multi Use Games Area formal courses at:- c. Hammonds Pond - Formally LP70c | Councillor Ellis | 617 | 759 | 825 | 972 | 850 |  | Aim to Maximise | Very poor weather resulting in low numbers this month, but the indicator remains on target. |

Theme Service Standards Promise Carlisle City Council Aim Tullie House

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LI310a | Visits to and Use of museums & galleries - All Visits - Formally BV170a | Councillor Ellis | 3,490 | 3,172 | 4,487 | 4,198 | 4,243 |  | Aim to Maximise | Visitor numbers marginally down on the expected position at this point in the year. |
| LI310b | Visits to and use of Museums & galleries - Visits in Person - Formally BV170b | Councillor Ellis | 1,943 | 1,936 | 2,507 | 2,614 | 2,800 |  | Aim to Maximise | At same level of visitors when compared with last year (year to date) but the target for this year looks difficult to achieve. |
| LI310c | Visits to and Use of Museums - School Groups - Formally BV170c | Councillor Earp | 11,951 | 8,865 | 15,693 | 11,890 | 12,501 |  | Aim to Maximise | The revamped sessions to be marketed to schools now for the Spring term but still need to allow time for the teachers to be retrained on the new sessions through Insets which will take best part of a calendar year to show the benefits of the new programme of lessons. |
| LI311a | Number of people participating in museums (off-site) community outreach activities - Formally LP71 | Councillor Earp | 6,618 | 4,921 | 8,125 | 6,168 | 7,939 |  | Aim to Maximise | A more focussed approach to both schools and community outreach - quality rather than quantity being delivered |
| LI311b | Number of people taking part in learning activities delivered by the Museum and Arts Service | Councillor Earp | 249,012 | 215,675 | 315,733 | 287,440 | 284,999 |  | Aim to Maximise | Good level of participation in learning activities |

Theme Service Standards Promise Shared Services & Partnerships Aim Carlisle and Eden CDRP

| PI No | Brief Description of Indicator | Portfolio Owners | December 2008 08/09 YTD | 2009/10 YTD | 2008/09 Value | 2009/10 Forecast | 09/10 Annual Target | Traffic Light Icon | Direction of Travel | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GI20CA | Assault with injury rate | Councillor Luckley | 5.43 | 5.25 | 7.07 | 6.96 | 7.78 |  | Aim to Minimise | Performance remains good. Both domestic violence and alcohol related violence remain a priority for the CDRP in 2010/2011. Countywide target is to reduce baseline by 5%. |
| LI305a | Recorded criminal damage crimes of per thousand population - Formally LP135 | Councillor Luckley | 17.11 | 14.09 | 22.45 | 19.11 | 17.36 |  | Aim to Minimise | Performance continues to improve, exceeding the maintenance target set at the start of the year. |
| LI317a | Recorded incidents of anti social behaviour per thousand population - Formally LP134 | Councillor Luckley | 85.63 | 80.61 | 110.66 | 108.16 | 86.13 |  | Aim to Minimise | Continued good performance. Successful partnership operation during Autumn tackled the seasonal peak in incidents associated with bonfires and fireworks. |
| LI320a | Assault with injury rate (NOT Domestic Violence) | Councillor Luckley | 4.35 | 4.22 | 5.59 | N/A | 6.15 |  | Aim to Minimise |  |
| LI320b | Assault with injury rate (Domestic Violence) | Councillor Luckley | 1.12 | 1.02 | 1.48 | N/A | 1.63 |  | Aim to Minimise |  |

# Text boxes

Annual Target / Traffic Light Icon

These columns show:

- 09/10 Target (set at the start of the year in the Corporate Improvement Plan).

- On Target?: How we will perform against these targets (based on the year-end forecast).

  - = above target

  - = within 5% of Target

  - = target not met

  - = data/information only PI (no target set)

Direction of Travel

This indicates if a larger or smaller figure is better for each indicator.

Year end Forecast

This shows a forecast for the performance outturn at the end of the year (based on the current year-to-date figure).

Report

Key / Guidance

Year to Date Figures

These show this years year-to-date figures and the figures from the same period from the last calendar year.

PI No (PI Number)

LI	=	Local Performance Indicator

NI        =      National Indicator

MI = Management Information

GI = Geographical information

(new performance framework)

Underlined = LAA