COMMUNITY OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 10th FEBRUARY 2005 |
| Title: | SHEEPMOUNT PROJECT UPDATE: FEBRUARY 2005 |
| Report of: | HEAD OF CULTURE, LEISURE AND SPORTS SERVICES |
| Report reference: | CLS024/04 |

Summary:

This is the 6th update report on the Sheepmount Project and includes details from the latest site meeting held on Monday 24th January 2004.

Recommendations:

That members note the report.

| Contact Officer: | MARK BEVERIDGE | Ext: | 7350 |
| --- | --- | --- | --- |

1.0	INTRODUCTION

1.1	This report provides members with the latest position on the Sheepmount at 28th January 2004.  A verbal update will be provided to the committee on the day of any changes which may have occurred in the intervening period.

2.	PROJECT PROGRESS TO DATE

2.1	Members are aware that during the recent flood the Sheepmount site was covered with water to a depth of several metres. At the height of the flood both lower and upper plateaux were covered completely, including the surrounding banking and all buildings on the site including the temporary site cabins were flooded. In the new building the water reached approximately 1.5m high up the internal walls. In the existing building the water was around 0.2m high up the internal walls.

| Construction Activities | Start | Complete | Progress/Comments (Progress as at 27/01/05 site meeting) |
| --- | --- | --- | --- |
| Football Pitches | 05/07/04 | 24/09/04 | 100% planned 95% complete against programme pre flood. Due to the flooding the new drainage system has been covered in silt. The sub contractor is testing the percolation of the drains to determine the extent of the damage. Cameras will be used to assess if any damage has been caused to the pipe work. |
| Track Extension | 05/07/04 | 24/09/04 | 100% planned 95% complete against programme pre flood. The track surface is covered in silt and will have to be cleaned off then tested for porosity. An assessment will determine if the track is recoverable or beyond repair and need to be renewed. The security fencing was damaged by the force of the water around 20 panels will need to be replaced and most posts will have to be reset. |
| Coach Turning and Access Rd on Bitts Park side of bridge. | 11/08/04 | 28/09/04 | 0% planned 5% complete A planning application has been made by Kiers to Carlisle City. |
| Car Park on Sheepmount | 09/08/04 | 29/09/04 | 100% planned 80% complete against programme pre flood. The Environment Agency has received the clarification sought from Kiers on the surface water run off arrangements. Tarmac was due to be laid in January 2005. Following the flood the car park was used as an access point by Railtrack to facilitate repairs to the West Coast Line. The surface was also damaged by the action of the floodwater and will need to be re-levelled prior to tarmac being laid. |
| New Pavilion Initial Site Work | 21/06/04 | 02/07/04 | 100% complete |
| Substructure | 05/07/04 | 06/08/04 | 100% complete |
| Superstructure | 02/08/04 | 13/12/04 | 100% planned Blockwork 100% complete Brickwork 100% complete Roofing 100% complete Some of the external brickwork was damaged and will be renewed during the recovery work. It will all need to be acid washed to clean it following the flood. |
| M & E | 01/11/04 | 17/12/04 | 40% planned 30% complete against programme pre flood. The flood damaged the underfloor heating pipework because the water lifted the screed. This has all been removed and taken back to bare concrete. Once the building has been dried out the screed will be re-laid along with the pipe work. The tiling which, had been laid has been removed due to water damage. |
| Services | 27/09/04 | 23/12/04 | The pipe work for the gas and water main is in the ground from the pavilion to the Sheepmount side of the West Coast rail-line. Kiers require United Utilities to obtain a licence from Railtrack to take the supply under the culvert, which runs, between the Sheepmount and Willowholme. To-date this issue has not been resolved. The Council has written to and spoken with both U.U. and Railtrack to try and facilitate a resolution along with the contractor. |
| Existing Changing Rooms | 10/01/05 | 24/03/05 | 0% Planned 40% complete against programme pre-flood. The flood has affected some of the work already completed and this will need to be re-programmed to take account of the work necessary to rectify the damage. |

3.0	IMPACT OF FLOOD/STORM DAMAGE

3.1	A tremendous amount of damage was caused across the site because of the flood in January. This will inevitably place the work behind schedule. Now the estimate from Kiers is that the work will be completed in mid summer 2005. However there are still a number of variables which could impact on that estimate, such as whether the track has to be renewed and the delivery times of material damaged in the flood. Another factor, which is now relevant, is the availability of sub-contractors who previously would have been programmed to complete their work by Easter 2005. Kiers are re-programming their work and plan to determine this by early February. This information once available will have to be discussed with them and the clubs to determine the impact on each of the parties concerned.

4.0	HEALTH AND SAFETY

4.1	Kier Northern inspects weekly and all reports are good.

5.0	FINANCE

5.1	10TH December 2004 marked the 9th payment of the contract period, no further payment has been made since that date

5.2	The external funders have paid their interim draw down payments to date totalling: -

Sport England 		-	£468,877.00

Football Foundation		-	£495,617.00

£964,494.00

6.0	AMENDMENTS TO DESIGN

6.1	The security fence surrounding the track area was the subject of some discussion between the UK Athletics and the City prior to the flood. This was to ensure that the fence was set out to accommodate the throwing area for the discus and hammer. Since the flood and damage to the fence, a representative from UK Athletics will now visit the site to discuss the issue prior to any rectification work being carried out.

7.0	USER GROUP

7.1	The project was discussed at the last user group meeting in January. The impact of the flood and its’ aftermath will and are having significant implications for the football and athletics clubs.  Club Representatives were given an outline of progress to date.

7.2	Football club representatives have asked about the possibility of financial assistance for the expense incurred during the period when the Sheepmount is out of use. This is to be determined with the Council’s insurers.

7.3	The principle issue for the two athletics clubs is access to the track. Until a decision has been reached on this it is not possible to give a date when the track will be available. This is a critical issue for the clubs, as they have to give notice to the clubs who would be attending the track for competitions this year. A decision has already been taken to cancel all early season events until the end of May.

8.0	OPENING

8.1	The plans for opening have now been thrown into some disarray and will have to be assessed in light of the new work programme and the impact it has on the 2005 season.

9.0	RECOMMENDATION

9.1	Members note the report.