CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 10th January 2008 |
| Title: | Corporate Risk Management |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 02/08 |

Summary: The purpose of this report is to give members of the Corporate Resources Overview and Scrutiny Committee the opportunity to consider the Corporate Risk Register.

Questions for / input required from Scrutiny:

To scrutinise and provide feedback on the Corporate Risk Register.

Recommendations:

The Committee is asked to consider and comment on the updated Corporate Risk Register and identify any emerging risks for consideration by the Corporate Risk Management Group.

| Contact Officer: | Carolyn Mitchell | Ext: | 7306 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	Corporate Resources Overview and Scrutiny

Date:	10th January 2008

1. 	Background

In accordance with the Council’s Risk Management Policy, the draft Corporate Risk Register is submitted to this Committee for consideration on a quarterly basis.

This Report contains the latest quarterly update of the Register.

The Risk Register is at Appendix 1 and the summary of changes made in the last

quarter is at Appendix 2.

2. 	Comments on the Corporate Risk Register

Members will note that any change to a risk score is shown by a symbol in the movement column.

During the last quarter, the Current Action Status / Control Strategy sections have been addressed and updated where applicable and scoring of certain risks amended accordingly.

Some new risks have been added to the Corporate Risk Register and these will be considered, and control strategies developed, prior to the next report.

In addition to scrutinising and commenting on the Risk Register, members of this committee are invited to suggest emerging risks for consideration by the Corporate Risk Management Group. If appropriate these will be incorporated into the Corporate Risk Register and members will be able to track their management at the next quarterly update.

3. 	Recommendations

The Committee is asked to consider and comment on the updated Corporate Risk Register and identify any emerging risks for consideration by the Corporate Risk Management Group.

# Appendix 1 - CORPORATE RISK REGISTER Updated 19th December 2007

# For consideration by Corporate Overview and Resources Committee 10th January 2008

# Note: amendments in last quarter marked in red italics (or italics only on the printed version).

| Ref | Risk Description | Impact | Likeli-hood | Risk Score | Move-ment | Current Action Status/Control Strategy | Responsible Officer & date last updated |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Pay and Workforce Strategy Failure in the implementation of PWS  financial impact  impact on staff including Low morale/demotivation Retention difficulties Increased call on resources Impact on business/productivity Failure to implement succession planning | 4 | 3 | 12 | = | Implementation Plan and Programme determined and published Prince 2 methodology applied Training commenced in specialist areas Regular Staff updates via Management Briefing and newsletters Continual monitoring of progress by Project Manager overseen by Project Board Project developed and delivered in partnership with Unions. Workforce Development Plan agreed, published and implementation started. Staff now benefiting from this via improved training/ development opportunities. Job evaluation scores were issued to staff on 31st August 2007 and staff briefing sessions carried out. Proposals for revised pay structures to be developed over the next few months. | Deputy Chief Executive 19/12/07 |
| 2 | Shared Services | 3 | 3 | 9 | = | A shared services Policy was agreed by the Council in March 2007. This clearly articulates that no shared services arrangement will be entered into by the City Council unless there are clear benefits for the authority that can be demonstrated in a full business case. This serves as a containment action that will reduce the impact of any shared services arrangements into which the City Council enters. It is likely that the authority will enter into shared services arrangements with other organisations as central government is keen to progress the shared services agenda. The Cumbria Local Authorities Strategic Board is co-ordinating the work on shared services. The council is participating in a number of shared services workstreams of which procurement is the most advanced. Work on Shared Services was delayed pending a decision on the reorganisation of Local Government which has now been received. The progression of the shared service agenda is a major part of the Council’s current strategy to find ongoing efficiency savings. Consequent Shared Services risks are being assessed including:- Promised savings not realised Promised service improvements not realised Partners not engaging to an equal extent Governance arrangements not responsive enough to allow changes or amendments to accommodate future service requirements. | Director of Corporate Services 29/11/07 |
| 3 | Carlisle Renaissance There is a strategic risk associated with withdrawal of the support of key partners at a sub-regional, regional and national level, loss of momentum and resultant loss of confidence within the local resident and business community. Capacity and the availability of resources are critical to this as well as effective engagement and communication mechanisms. Failure will be expressed in Reputational – failure to achieve stated objectives Financial – failure to secure and utilise funds appropriately Delivery – failure to manage a programme of growing scale and diversity. | 4 | 2 | 8 | ( | Consultants have been engaged to progress options for a Delivery Mechanism for Carlisle Renaissance to manage the delivery of development and infrastructure projects. A Detailed Application has been submitted for approval by the NWDA. This application will secure funding for additional development and project management capacity. The Economic Strategy for Carlisle will be launched in March 2008. This has been prepared in collaboration with leading private sector representatives from the Carlisle Partnership (LSP) and includes a detailed action plan for 2008-2011. | Director , Carlisle Re- naissance 19/12/07 |
| 4 | MediumTerm financial planning and maintaining asset values; failure leading to:- - risk of systems and procedures failing to address MTFP objectives - risk that expenditure not linked to key objectives and priorities - fails to be forward looking and programmed - lack of corporate ownership - failure to achieve balanced budget through the budgetary process - failure to match future commitments and aspirations compared to funding available - maintaining asset values | 4 | 2 | 8 | = | The MTFP and Capital Strategy were approved by Council on 17th July 2007. The MTFP and Capital Strategy are reviewed regularly in the light of current pressures arising and this will be done throughout the current budget process. In particular there is an added and growing risk to the Council's financial position from the CSR07, the PWS implications, shortfalls in income projections and budget pressures in a number of areas. There is a specific risk in failing to identify corresponding savings to offset the spending pressure identified and SMT are monitoring this aspect prior to reporting back to members. The Executive draft budget proposals will be issued in December 2007 for consultation. Clear strategy for linking resources to corporate priorities is to be developed. The work of the Capital Projects Group and Corporate Programme Boards will support the improvements to financial and performance improvements regarding the capital programme. | Director of Corporate Services 29/11/07 |
| 5 | Failure to have robust Business Continuity Planning arrangements - severe impact on business/provision of services - financial impact - reputational impact - legal liability These may include the risk of Flu Pandemic leading to:- inability to maintain services due to impact on staff and suppliers failure to contribute to emergency response due to extent of above | 4 | 2 | 8 | = | Marsh Limited are facilitating the development of a new Business Continuity Plan which should be available by the end of this year. Initial testing of this will be carried out in January 2008. | Deputy Chief Executive 19/12/07 |
| 6 | Carlisle Northern Development Route | 4 | 2 | 8 | = | The County Council selected a preferred bidder, Connect CNDR (a brand name for Balfour Beatty), on the 22 November. Final negotiations are expected to be completed by end March 2008 with a view to awarding the contract in early June 2008. Construction, which is expected to take 2 years would commence in September 2008. In addition to the construction of the CNDR the 30 year concession includes the management and maintenance of:- A7 (Junction 44 to Scottish Border) A689 (Junction 44 to Brampton Bypass) A595 from Newby West, south A6071 (Brampton Bypass to Scottish Border The completion of the CNDR would reduce the air quality on Scotland Road to below the threshold level." | Director of Community Services 19/12/07 |
| 7 | Potential loss of VAT reclaimed Potential loss of VAT Partial Exemption Status resulting in the potential for a significant amount of VAT to become irrecoverable and a potential cost to the Council of approx £200k. If the VAT the Council reclaims from Revenues & Customs (HMRC) on its exempt activities (mainly Industrial Estates, Miscellaneous Properties and Crematorium) exceeds 5% of the total amount of VAT recovered, then the whole amount of the VAT on the exempt activities can no longer be recovered. | 2 | 3 | 6 | ↓ | Following a full consideration of the options and issues, the Executive, on 30th July, decided to charge VAT on its commercial rents. This took effect from 1st September 2008. A transitional hardship relief scheme has been introduced for non VAT registered businesses who can prove hardship. It is currently envisaged that the 5% limit will not be breached for 2006/7. However, this is dependent on the total amount of input tax for 2006/7 reaching the predicted £2.9m and this will not be known until the end of the financial year. | Director of Corporate Services 29/11/07 |
| 8 | Financial Management Information provided must be accurate, robust & timely to enable Budget Holders to manage, failure leading to:- - poor management decisions - loss of credibility in information provided -Service Heads fail to focus on key objectives - Not linked to performance management - failure to adopt best practice and achieve value for money - specific risks identified associated with Contractor Plus system | 3 | 2 | 6 | = | The Council’s Financial Management arrangements have been assessed as adequate in the Audit Commission’s Use of Resources judgement, and also by the independent review of financial management conducted by IPF. Action has been taken on all areas of improvements required and an updated Use of Resources judgement is anticipated in December 2007, following which the Action Plan will be reviewed to pick up any outstanding issues. Work is ongoing with the Policy and Performance and Finance Teams to further improve linkages between use of resources and performance. The Executive recently approved a revised Financial Services Structure, designed to increase capacity in the service and deliver improvements.. A specific risk remains to the Council from the existing system utilised by the Community Services Directorate for ex DSO work and the ability to easily reconcile the system to the Councils core financial management system. A budget has been allocated and work is progressing to replace the Community Services system albeit this has been delayed due to the Local Government Reorganisation issues. A significant financial training programme has now been launched to improve the financial management standards throughout the authority. | Director of Corporate Services 29/11/07 |
| 9 | Failure to focus clear Corporate Priorities leading to:- - resources wasted on lesser priorities - key objectives not achieved | 3 | 2 | 6 | = | New Corporate Priorities now determined :- Greener , Cleaner and Safer The Learning City Carlisle Renaissance Further work is in place to ensure that these are the drivers for focussing activity and expenditure Work is now under way on realigning the priorities in the Corporate Plan. | Town Clerk & Chief Executive March 07 |
| 10 | Protection of IT E-records and data and hard copy information:- - failure will have business/financial impact - inability to meet legal/other obligation - impact on resources / cost of re-establishment | 3 | 2 | 6 | = | The Council has recently been assessed by the Audit Commission – Your Business at Risk. We have been ranked ‘better than average’ and a full action plan was presented to the Audit Committee in April. As part of the Business Continuity planning arrangements, the issue of hard copy storage and recovery will be considered. | Director of Corporate Services 13/09/07 |
| 11 | Failure to implement an effective IT Strategy:- - failure to meet IEG targets - failure to maximise benefits of e-business and e-procurement - increased security risks | 3 | 2 | 6 | = | An Information Strategy Group has been set up and has been working through the action plan developed following approval of the strategy in January 2006.. A revised strategy is currently under development and will be considered by Corporate Resources Overview and Scrutiny Committee in due course. Regular IEG Statements produced. Evidence file produced to assist in Audit Commission grant assessment during 2007/08. | Director of Corporate Services 29/11/07 |
| 12 | Performance Management challenges Failure to embed performance management in the culture of the Council at all levels - inefficient and ineffective management - misdirected/wasted resources - failure to meet target/continuous improvement | 3 | 2 | 6 | = | Quarterly Performance conferences now commenced to monitor and address performance corporately Performance Management included in Directorate’s Service Plans Performance Management Framework was published March 2007. New Performance Management IT system to be implemented in the next few months.. | Deputy Chief Executive 19/12/07 |
| 13 | Health & Safety management and systems failure could lead to:- - exposure to legal action - financial impact of failing to ensure recovery of all - reputational impact on Council - increased exposure of staff to H&S risks - creation of image of non-proactive employer - lack of understanding of Health and Safety Manager’s role | 3 | 2 | 6 | = | Council’ Health and Safety Policy fully adopted Qualified H&S Manager employed in a corporate role Clear H&S management systems installed across the Council Health and Safety action plan regularly updated and ongoing auditing of current practices Developing local Performance Indicators which will be reported on in the Council’s performance management reports to Corporate Resources Overview & Scrutiny Committee Continuing training of staff as appropriate including mandatory training for newly appointed employees Role of Health and safety to be included in Service plans H&S strategy under development. | Deputy Chief Executive 13/09/07 – no change |
| 14 | Financial Reporting following comments of audit Commission on standard of financial reporting- Failure will lead -reputational damage -have an impact on overall CPA assessment -poor relationship with District Audit | 3 | 2 | 6 | = | The Audit Commission judged the Council’s financial reporting standard for 2005/06 as part of the Use of Resources judgement to be inadequate. The 2006/07 Accounts were submitted to Council on 28th June following consideration by the Audit Committee and Executive. The Audit is now completed and has for the first time for many years been signed off by the statutory date. The audit commission have recognised the improvements made and the positive direction of travel. There are however still amendments deemed to be material and it is not at this stage known what judgement will be made under the Use of Resources judgement. | Director of Corporate Services 29/11/07 |
| 15 | Partnerships (including framework agreement & collaborative working arrangements) Existing partnerships and New and proposed partnerships , failure to ensure compliance with existing arrangements leading to:- - failure to meet stated objectives - reputational and financial impact - onerous terms and conditions, and inadequate exit strategy - increased exposure to risk - major review of compliance with partnership agreements or evidence of agreements not undertaken on a regular or structured basis | 3 | 2 | 6 | = | The Council now has a robust Partnership policy in place providing guidance on the nature and risks of partnerships and the new procedures were launched at the Management Briefing in March 2007 The draft policy will be considered by the Executive on the 21st of January 2008 and installed on the Corporate intranet shortly afterwards. The Use of Resources judgement has highlighted that the Council needs to improve its financial performance of partnerships including a link to outputs and ensure the results are shared with partners and acted upon. It has also highlighted that appropriate governance arrangements should be in place for all significant partnerships. Corporate Services Efficiency and Procurement team is responsible for the monitoring arrangements, this includes the update of the central register, completion of annual reviews of all significant partnerships, annual reports to members and quarterly progress reports to SMT. One to one assistance is given to officers when setting up new partnerships. Senior Management Team will ensure that their individual risks from partnership working arrangements should be included in Operational Risk Registers. | Director of Corporate Services 29/11/07 |
| 16 | Failure to implement Code of Corporate Governance failure to meet legal duty failure to adopt sound, consistent, transparent and auditable processes | 4 | 1 | 4 | = | The Code of Corporate Governance Action Plan is updated and reported to the Audit Committee quarterly. The Code itself has recently been fundamentally altered and guidance has now been received from CIPFA / SOLACE on the new arrangements. This is likely to require a fundamental review of our current arrangements and this will be implemented in time for the 2007/8 accounts. | Director Corporate Services 13/09/07 |
| 17 | Flooding | 3 | 2 | 6 |  | The flood defence project on the Eden is now substantially completed and will provide increased protection for properties in the Warwick Road area from river flooding. The flood defence project for the river Caldew has achieved all the approvals and is scheduled to commence on site in March 2008. United Utilities start work in March 2008 on major sewerage improvements in the Warwick Road and Willowholme areas. The "Making Space for Water Group" meet on a regular basis and flood response arrangements are reviewed regularly to provide an integrated response to incidents. | Director of Community Services 19/12/07 |

# Risks to be removed

| Ref | Risk Description | Impact | Likeli-hood | Risk Score | Move-ment | Current Action Status/Control Strategy | Responsible Officer & date last updated |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Failure to adopt consistent and effective Project Management procedure leading to:- - financial impact of failure (direct and indirect) - damage to Council’s reputation - principles not applied universally | 3 | 1 | 3 |  | Introduction and Implementation of Business Case philosophy for all significant projects and schemes to ensure executive and corporate monitoring at SMT and Capital Programme Board Introduction of Prince 2 project management and commencement of corporate awareness training Establishment of dedicated Project Manager post within new structure Consistent project management approach has been established within the Authority. Staff training ongoing. | Deputy Chief Executive 13/09/07 |
|  | Risks associated with increased threat of terrorism |  |  |  |  | This risk will be included in the Community Risk Register in line with the Civil Contingencies Act |  |
|  | Enhanced two-tier working |  |  |  |  | No specific risks for inclusion in the corporate risk register have been identified at present. This will be reviewed for possible inclusion later. |  |
|  | Foot & Mouth Disease and Blue Tongue |  |  |  |  | This risk will be included in the Community Risk Register in line with the Civil Contingencies Act |  |

Appendix 2 - Corporate Risk Register December 2007

# Quality Control Document (changes since October 2007)

For consideration by Corporate Overview and Resources Committee 10th January 2008

| REF NO | BRIEF DESCRIPTION | SCORE | COMMENTS |
| --- | --- | --- | --- |
| 1 | Pay and Workforce Strategy | 12= | Control strategy/action status updated |
| 2 | Shared Services | 9= | Control strategy/action status updated |
| 3 | Carlisle Renaissance | 8= | Control strategy/action status updated |
| 4 | Medium term financial planning | 8= | Control strategy/action status updated |
| 5 | Business Continuity Plan | 8= | Control strategy/action status updated |
| 6 | Carlisle Northern Development Route | 8= | Control strategy/action status updated |
| 7 | Potential loss of VAT reclaimed | 6( | Likelihood reduced. Control strategy/action status updated. |
| 8 | Financial Management Information | 6= | Control strategy/action status updated |
| 9 | Corporate Priorities | 6 = | No change |
| 10 | Protecting IT records | 6= | No change |
| 11 | Implement Effective IT Strategy | 6 = | Control strategy/action status updated |
| 12 | Performance Management | 6= | Control strategy/action status updated |
| 13 | Health and Safety | 6= | No change |
| 14 | Financial Reporting | 6= | Control strategy/action status updated |
| 15 | Partnerships | 6= | Control strategy/action status updated |
| 16 | Corporate Governance | 4= | Control strategy/action status updated |
| 17 | Flooding | 6 | Previously removed but returned to Corporate Risk Register on the advice of Corporate Resources Overview and Scrutiny committee. |
|  | Project Management | 3( | To be removed as risk score has dropped to 3 |
|  | Terrorism |  | To be removed - included in Community Risk Register |
|  | Enhanced Two-Tier Working |  | To be removed – review inclusion in future as more detail emerges |
|  | Foot & Mouth Disease and Blue Tongue |  | To be removed - included in Community Risk Register |