| REPORT TO EXECUTIVE |
| --- |
| PORTFOLIO AREA: FINANCE AND PERFORMANCE MANAGEMENT |
| Date of Meeting: | 20 November 2006 |
| Public |  |
| Key Decision: | No | Recorded in Forward Plan: | No |
| Inside Policy Framework |

| Title: | 3 YEAR FINANCIAL MANAGEMENT IMPROVEMENT PLAN |
| --- | --- |
| Report of: | The Director of Corporate Services |
| Report reference: | CORP58/06 |

Summary:

A ‘3 year’ Financial Management Improvement Plan has been drawn up (and actions being progressed) taking account of:-

- issues raised in the recent IPF report of financial management;

- the few outstanding actions from the Statement of Account Action Plan;

- actions set out in the Use of Resources Self Assessment in meeting the Council’s objective of improving its rating from a level 2 (performing adequately) to level 3 (performing well) in effective management of its resources.

The Improvement Plan is attached for Members’ consideration.

Recommendations:

Members are asked to approve the 3 Year Financial Management Improvement Plan which will be monitored by the Audit Committee.

| Contact Officer: | Angela Brown | Ext: | 7299 |
| --- | --- | --- | --- |

Note: in compliance with section 100d of the Local Government (Access to Information) Act 1985 the report has been prepared in part from the following papers:  IPF Report September 2006.

CITY OF CARLISLE

To:	The Executive								CORP58/06

20 November 2006

3 YEAR FINANCIAL MANAGEMENT IMPROVEMENT PLAN

- BACKGROUND

  - The Institute of Public Finance (IPF) has recently undertaken an independent review of the financial management arrangements of the Council, and the Executive and the Audit Committee considered the report on 25 September.

  - The report concluded that the City Council’s Financial Management arrangements met an acceptable standard for a typical District Council, but that significant improvements could still be made. The report contained an Action Plan highlighting areas for improvement.  Members noted that these improvements will be necessary if the Council is to achieve its ambitions of excellence in service provision.

  - The Executive requested that each of the points in the recommended IPF action plan be considered and, in consultation with the portfolio holder for Finance and Performance Management, an Improvement Plan for the City Council be developed with responsible officers, timescales and measures of success clearly and unambiguously identified.

  - The opportunity has been taken in setting out an improvement plan to deliver IPF recommendations to include outstanding items from the Statement of Accounts Action Plan and issues still to be addressed resulting from the 2006/07 Use of Resources Self Assessment.

  - Due to the scale, resource and cultural implications of some of the suggested improvements, the Improvement Plan will be delivered over a 3 year time span.  However areas highlighted in bold which, if not progressed, could result in reputational risk to the Council, i.e. late closure of accounts, adverse comment on Direction of Travel/Use of Resources assessment etc. – wil be given priority within the Improvement Plan.

- ACTION PLAN

  - The proposed Improvement Plan is attached for Executive comment and approval.

  - It should be noted that Use of Resources issues in the Plan will be subject to a 3 monthly monitoring report to Corporate Resources Overview and Scrutiny Committee.

  - Once approved by the Executive, the Action Plan will be monitored by the Audit Committee.

- CONSULTATION

  - Senior Management Team, the Portfolio Holder for Performance and Finance and senior Financial Services staff have been consulted.

- RECOMMENDATION

  - Members are asked to comment on and approve the 3 Year Financial Management Improvement Plan, which will be monitored by the Audit Committee.

- IMPLICATIONS

  - Staffing/Resources – there are staffing and financial resources implications in implementing an Improvement Plan of this nature and extra resources may be required.  It is possible that a reallocation of duties within Financial Services may release some capacity but the cultural shift of individual budget managers being more financially literate and so release capacity from the financial team will take time to bed in.  The training programme may also require additional resources to implement. A bid for a non –recurring £50,000 is being made as part of the 2007/08 budget process to help to address the resource problem in the short term pending a longer term solution being sought.

  - Corporate – SMT accept that financial management is an issue for the whole organisation and are committed to improving financial literacy

  - Risk Management  - There is a risk in not completing the action plan to the Council’s ambitions of achieving excellence in service provision. There is also a risk that the current workload of some of the senior staff in the Finance Unit is unsustainable and action needs to be taken to address the situation.

  - Equality Issues – None

  - Environmental – None

  - Crime and Disorder –  None

ANGELA BROWN

Director of Corporate Services

Contact Officer:	Angela Brown			Ext:	7299

Financial Management Improvement Plan

(01.10.06 – 30.09.09)

(Priority Tasks in Bold)

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| A. | Strategic/Corporate |  |  |  |  |
| A1. | Financial Management in Projects/ Initiatives |  |  |  |  |
| 1.1 | Carry out a status review (and reality check) on all current projects and initiatives Assess priorities and develop a “deferral strategy” where resources will be directed to improving basic stewardship aspects as an interim measure Ensure that a risk management approach is taken in doing this | SMT (via Projects Programme Board) | March 2007 | Realistic workloads and capacity to support corporate priorities. | (i) SMT will consider the impact of any new initiatives and additional resources will be requested where it is not considered feasible to deliver within existing capacity. (ii) In terms of current projects, this requires SMT consideration and will be considered by the Projects/Programme Board. |
| A2. | Structure of Finance Function |  |  |  |  |
| 2.1 | Assessment of workload / burden on each role within the finance function Detailed analysis of pattern of workload – establishing peaks and troughs Reallocation of tasks and responsibility where appropriate (including reviewing job descriptions) | S McGregor/ S McGregor A Brown | Jan 2007 | Increased capacity to support organisation. Better balance of workloads. | Initial review of duties and responsibilities actioned in February 2006. Further work ongoing. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 2.2 | Determine whether permanent increase in establishment or use of temporary resources at key times is best option. | A Brown/Chief Executive | Sept 2007 | New structure fully resourced by April 2008. | Awaiting results from above exercise. In the short term temporary accountancy resources taken on to 31.3.07 and a bid for additional temporary resources to cover 2007/08 will be made as part of the 2007/08 budget process. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| A3. | Budget Preparation and Financial Planning |  |  |  |  |
| 3.1 | Introduce more challenge into the budgeting process by: Developing “decision conference” approaches where members and senior officers can consider priorities and growth bids Improve public consultation in the budgeting process Developing Zero based budgeting techniques for areas (possibly on a rolling programme) | SMT SMT/Executive S McGregor | 2007/08 budget process 2007/08 budget process April 2009 | Better allocation of resources to priorities. Better achievement of performance against budgets allocated. More informed decision making by Members. Reduced level of ‘underspends’. | Service Head Conference September 2006. Strategic Planning Group (Senior Members and Officers) meet regularly to consider priorities and bids prior to the formal consideration by Members. Public consultation via Citizens Panel and State of City Zero based budgeting has a resource implication and this will be introduced depending on resources following initial consideration by SMT |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 3.2 | Improve forecasting to avoid underspends/ overspends by: Increased use of commitment accounting Stronger links with performance management – looking at activity as drivers of cost More stringent measures on continuing budgets (especially in areas of underspend) Integrate consideration of underspends more formally to the budget process Introduced action plans for significant variances Make service heads accountable for financial performance Change culture to a perception that “underspends” are not acceptable performance | S McGregor SMT SMT S McGregor Service Heads Service Heads Service Heads | 2007/08 budget process | Reduced level of both carry forward and net underspends. | Commitment accounting is currently being considered as part of the Procurement initiative led by the CPI. Work is being progressed as a priority during 2006/07 to improve the links with performance management |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 3.3 | Addressing the “underspend culture” by: Limiting carry-forwards (thresholds and time limits) Introducing tougher justification for carry forwards – reviewing criteria for evaluation Introduce targets with punitive measures as appropriate | A Brown | March 2007 | Better VFM in setting Council Tax and holding appropriate balances. | Carry Forward procedure to be reviewed for recommendation to the Executive. Improved budget monitoring and performance management procedures will improve the issue of work not completed within original timescales. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| B4. | Professionalism and Development of Staff/ Members Both Corporately and in Finance on Financial Management |  |  |  |  |
| 4.1 | Encourage continuing professional development and financial awareness training: Maximise benefit of corporate CPD registration Encourage increasing knowledge / training / experience of public sector finance issues (esp. local authorities) for non-CIPFA CCAB qualified staff Ensure time is made available for CPD activities Ensure all relevant Council staff participate in financial training programme | S McGregor S McGregor/ D Williams | March 2007 | Spread of finance knowledge throughout organisation. More generic financial advice. Reduced reliance on key finance personnel thereby increasing overall capacity. | Training/CPD programme already in place for CCAB qualified members. It is recognised that other finance staff would benefit from participating in more formal CPD activities and this will be further encouraged and progressed as part of the formal appraisal meetings. Extension of current programme is dependent on resources/workload which is addressed elsewhere on the Improvement Plan. With respect to authority wide financial training, a programme of training has already commenced and is being developed further. This will be incorporated into the Council’s Corporate Training Programme. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 4.2 | Establishment of knowledge management systems: Development and maintenance of procedure notes and update the Financial Guide Increase level of job rotation (or job shadowing) Sessions on roles and processes as part of regular management team meetings (or forums) Cascade learning points from training or external events | S McGregor | March 2007 | As above. | All of these issues are being progressed by Head of Financial Services and Head of Personnel and Development Services. SMT has agreed programme which is being finalised. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 4.3 | Encourage innovation and initiative by: Supporting staff suggestions for change (as appropriate) Delegate responsibility for trialling changes / new concepts Encouraging representation on initiative / project teams by more junior staff Where appropriate, delegate representation on project groups to lower management levels | S McGregor | March 2007 | Spread of knowledge and understanding. | Staff suggestions are made via TIR meetings. Whilst it is an excellent development technique, there is a risk that delegation of new initiatives and projects to more junior staff will result in a higher degree of errors whilst the learning curve is achieved. Currently a degree of shadowing is undertaken and this will be developed but this is limited by overall resource constraints. To a certain degree representation on project group is already delegated subject to the risk assessment set out above e.g. Capital Projects Board. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| C5. | Closure of Accounts/Financial Reporting |  |  |  |  |
| 5.1 | Refine closedown timetable Ensure close working with external audit Ensure early consideration of changing requirements, material events or new accounting treatments | S McGregor | Actioned in 2005/06 Accounts process but further improve-ments to be actioned for 2006/07 Accounts process (see comments) | Accounts Audited to Statutory deadline and positive Annual Governance Report from the Audit commission. This improvement is also a key requirement of the Use of Resources Improvement Plan. | There are major changes to the Accounting requirements for the 2006/07 accounts and the new SORP requirements are currently being considered. Further guidance from CIPFA is awaited. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 5.2 | Improve quality and indexation of working papers and evidence source: Make full use of disclosure and audit checklists Require that the Audit Commission clarify their timetable of work for the final accounts process Ensure a clear audit trail down to source reports / documentation Introduce quality control mechanism for the working papers Review 2005/06 papers and the action plan and provide the ‘missing’ information as part of the original papers to be handed to the Audit Commission 30/6/07 Identify high risk areas and work on these prior to the commencement of the 2006/07 closedown process. Develop property database. | A Taylor Director of Development Services | Actioned in 2005/06 Accounts process but further improve-ments to be actioned for 2006/07 Accounts process | As above. | Improvements have been made for 2005/06 as acknowledged by the Audit Commission. Further improvements are planned for 2006/07. The development of the Property database is a high risk area as it provides information on the assets of the council which is subject to considerable audit scrutiny. The Director of Development Services is currently considering options to develop this system. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 5.3 | Improve final accounts process: Carry out “dry run” closedown at end of Quarter 3 Reconciliation of systems provided as part of WPs | A Taylor | January 2008 | As above | This will be attempted but is a significant workload, hence timescale. Grants and WGA information needs to be improved. Set up partnership criteria governance, accounting processes subject to review to be completed by March 2007 in meeting Use of Resources good practice. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| D6. | In Year Monitoring and Forecasting |  |  |  |  |
| 6.1 | Develop clearer links with performance management, risk management and asset management. This can be done through: Using unit costs for activity Linking activity levels with budgets / spend Linking key PIs with spend | S McGregor | 2008/09 | Better understanding of link between costs and activities. | Would not be achievable in the current year from existing resources. The achievement of this would require further consideration. Clearer lines with performance management is a key priority for 2007/08 and this is being achieved through monthly performance conferences for Service Heads. |
| 6.2 | Improve commitment accounting by full implementation of electronic ordering to ensure all purchase orders are reflected in the FIS | S McGregor | Dec 2007 | Improved Financial Monitoring Information | Commitment accounting is currently being considered as part of the Procurement initiative led by the CPI. The Contractor Plus system operated by Community Services is currently being reviewed with a view to replacement within the next 12 months. |
| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| 6.3 | Develop reporting capability by: Making full use of Crystal Reports Training staff in Crystal where necessary Running workshops / sessions to establish what users would wish to see in their reports Ensure written financial reports are simplified as far as possible to aid understanding by Members and Officers | S McGregor | Dec 2007 | Improved financial and budget monitoring. | A full ledger development plan has been drawn up but currently the resources required to progress this are still being directed towards the bank reconciliation issue to satisfy Audit Commission requirements. Discussions with the supplier are ongoing to see how they can assist. |

Corporate Services

Carlisle City Council

7 November 2006

AB /  CH