AGENDA ITEM NO.		A11

CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 14th June 2007 |
| Title: | CARLISLE RENAISSANCE - NWDA PROGRAMME (PROGRESS REPORT NO. 2) |
| Report of: | DIRECTOR OF DEVELOPMENT SERVICES |
| Report reference: | DS.56/07 |

Summary:

This report summarises progress and developments in the delivery of the Carlisle Renaissance Year 1 Action Plan.

Questions for / input required from Scrutiny:

1.	Is sufficient progress being made in delivery?

Recommendations:

To note progress and developments in the Programme

| Contact Officer: | Neil Griffiths | Ext: | 7124 |
| --- | --- | --- | --- |

1.	INTRODUCTION

1.1	The Committee last considered the Programme in February when the Funding Agreement with the Northwest Regional Development Agency (NWDA) was yet to be signed and activity was limited to the development of the Economic Strategy.

1.2	The Funding Agreement was eventually concluded on 14th March and confirmed that activity under the Programme could continue to 31st March 2008, although some projects are scheduled to finish before that date.  Where external organisations were the lead on a particular project, Offer Letters from the City Council as Accountable Body also needed to be issued.  In three instances, tenders for project delivery were also required to be invited and awarded.

1.3	The Agreement was however, to some extent, out of date as it reflected the position of projects at the time of the approval of the original application in November 2006.  Things had obviously moved on and changes were required to individual projects in terms of timescale, activity, costs and funding.  Some of these were highlighted in the last progress report and are all summarised in Section 2.  It was too complicated to try and alter the Funding Agreement, as it would have meant a re-appraisal of the programme as a whole.  Therefore, once the Agreement was completed an application was made for the changes to the Programme.  Whilst this is a standard procedure, it is beyond the delegated powers of the Agency to approve locally, so had to be referred to Warrington.  Although nothing in writing has yet been received verbal confirmation of approval has.

1.4	The overall cost of the Programme remains the same, as does the NWDA’s contribution.

1.5	A subsequent change to the funding profile has also been requested.  This concerns how the grant will be split between revenue and capital.  The only capital expenditure originally identified in the Programme was the development of the Urban Design and Public Realm Framework, which totalled £457,000.  However, not all of the activity within the project can be classed as capital (approx. only 50%).  The funders of the project are the NWDA and the City Council.  The City Council funds (£100k) have been split 50/50 and a request has been submitted to the Agency to adjust their contribution.  The main contract under this project is scheduled to be awarded in July.

1.6	A financial claim was made for Quarter, 4, 2006/7 and is detailed in Section 5.

1.7	Section 6 provides a commentary on progress and developments so far.

2.0	CHANGES TO PROGRAMME

2.1	The table below sets out the programme by project detailing where changes have been sought.

| Theme | Project Title | Lead | REVISIONS |
| --- | --- | --- | --- |
|  |  |  | Activity | NWDA Outputs | NWDA Grant (£) | Total Cost (£) |
| Economic Strategy | Economic Strategy | Carlisle City Council | Outcome remains same ie production of medium -long term strategy and action plan. However, slippage in programme will push expenditure into Q2, 2007/8 | No change - None | No change – 100,000 | No change – 120,000 |
|  | Learning Village Scoping Study | Carlisle City Council | New Project - commission that will provide a basis for an understanding of issues surrounding developing the concept and practical implementation of the Learning Village. | None – no change | No change –10,000 | No change –10,000 |
| Skills & Worklessness | Bringing Regeneration Home | Carlisle Housing Association | Major change – CHA have wound down this project. It will now no longer be able to deliver significant outputs for Programme as only activity from Agreement date can be counted. Activity, however, still underway from last set of courses and Offer Letter to capture final outputs for Programme will be sent but at much reduced contribution. | Reduced from 20 to 5 New Jobs | Reduced from 53,000 to offer of 11,000 | Reduced from 167,000 to 45,000 |

| Theme | Project Title | Lead | REVISIONS |
| --- | --- | --- | --- |
|  |  |  | Activity | NWDA Outputs | NWDA Grant (£) | Total Cost (£) |
| Skills & Workless-ness…….continued | Job Brokerage | Carlisle City Council | New Project – this will address issues of worklessness, in particular within the deprived communities. It is being developed in such a way that it will deliver some of the key outputs, which would have been achieved through ‘BRH’. Proposed activity includes: Development of Employer Network Pre-employment support to individuals Personal Development / Motivational training Employment Support – CV Preparation, Job Search Techniques, Presentation Skills Job Placement Scheme – Wage Subsidy for up to 26 weeks Vocational Training | 17 New Jobs 40 assisted to get a job 5 basic skills 20 vocational skills | 35,000 | 75,000 |

| Theme | Project Title | Lead | REVISIONS |
| --- | --- | --- | --- |
|  |  |  | Activity | NWDA Outputs | NWDA Grant (£) | Total Cost (£) |
| Skills & Workless-ness..…..continued | Redundancy and Into Work Projects | Carlisle City Council | Some Changes and New Activity– Activity targeted at people recently made or currently under threat of redundancy and includes additional short term interventions to support unemployed/low skilled people into jobs in sectors where opportunities exist. This consists of a number of sub projects i.e. Retail Academy – changes required due to withdrawl of delivery partner Employment Support – primarily redundancy related small increase in resources Supermarket Employment Programme – pilot project linked to development opportunity on ex Cavaghan & Gray site – no change Events – supports Jobs Fairs – no change Sector Specific Training – new project to assist people in accessing jobs within food manufacturing Additional match funding opportunities available from Learning and Skills Council and Local Area Agreement. | 12 Jobs created 180 people assisted to get job 25 trained – level 2 12 trained level 3 21 receiving basic skills 155 vocational skills | No change - 135,000 | Increased from 250,000 to 306,000 |

| Theme | Project Title | Lead | REVISIONS |
| --- | --- | --- | --- |
|  |  |  | Activity | NWDA Outputs | NWDA Grant (£) | Total Cost (£) |
| Visitor Economy | Developing the Visitor Experience | Carlisle City Council | Significant Change – original project was focussed principally around the Christmas 2006 festival. Delays in finalising the Funding Agreement meant a reduction in activity and specific approval had to be gained from the Agency to claim expenditure prior to the Agreement date. This was granted and 37k was claimed in 2006/7, which, however, left significant resources for 2007/8. This budget has been allocated towards: Brand development study – draft brief prepared and likely to be tendered in next few weeks Events development Marketing | None – no change | Reduced from 100,000 to 97,000 | Reduced from 240,000 To 132,000 |
|  | Urban Design and Public Realm Framework | Carlisle City Council | No changes proposed to content of project. The purpose of this project is to provide a design manual for the City Centre, production of development briefs for key sites, and detailed design proposals for a series of public realm schemes. There will be one contractor delivering the bulk of the project. Tender likely to be let in mid July. | None – no change | No change - 357,000 (but see para 1.5) | No change - 457,000 |
|  | Castle Way – Reducing Impact | Cumbria County Council | No changes. Small scale study to examine feasibility of options. Final report produced on time and on budget. | None – no change | No change – 10,000 | No change – 10,000 |

| Theme | Project Title | Lead | REVISIONS |
| --- | --- | --- | --- |
|  |  |  | Activity | NWDA Outputs | NWDA Grant (£) | Total Cost (£) |
| Business Support | Tourism Business Support | Carlisle City Council | No changes. Provision of portfolio of services including training, marketing, on-line trading focussed on tourism sector. Tenders received and Offer Letters issued to Cumbria Tourism and Cumbria Rural Enterprise Agency (CREA). First businesses placed on courses. | No change 15 Businesses Assisted in manage-ment skills 15 Businesses Assisted in ICT use 5 people – work based training | No change – 55,000 | No change – 95,000 |
|  | East Cumbria Business Support | Cumbria Rural Enterprise Agency | No changes. Project aimed at filling current gap in general business support to, principally, new businesses throughout District. Tender received and Offer Letter issued to CREA. All business start up courses scheduled. First course completed. Follow up support underway. | No change 120 New Jobs 100 New businesses | No change – 70,000 | No change – 140,000 |
| Historic Quarter | Historic Quarter Tourism Research and Action Plan | Carlisle City Council | No changes. Provide a clear strategy and action plan on which to base future marketing, branding and tourism development of the historic quarter. Tender to be let in next few weeks | None – no change | No change – 75,000 | No change – 105,000 |

3.0	NWDA CLAIM SUMMARY – QUARTER 4 2006/7 - MILESTONES

3.1	The table below details the agreed predicted milestones of the Programme during the last claim and whether they were achieved.

| Milestone | Agreed Timescale | Actual/Outcome |
| --- | --- | --- |
| Employment Project – Begin sub project delivery for redundancy element | Quarter 4, 2006/7 | Achieved |
| Developing Visitor Experience 2006/7 – Claim for Christmas 2006 expenses | Quarter 4, 2006/7 | Achieved |
| Castle Way Study – Complete final report | Quarter 4, 2006/7 | Achieved |

4.0	NWDA CLAIM SUMMARY - QUARTER 4, 2006/7 - OUTPUTS

4.1	The table below details the predicted and actual outputs achieved during the period of the last claim.

| Gross Outputs achieved |
| --- |
| Output | Predicted 2006/7 | Actual 2006/7 | Future Forecast 2007/8 | Lifetime Forecast |
|  |  | Q1 | Q2 | Q3 | Q4 | 2006/7 Total | Total all years to date |  |  |
| 1a | Jobs Created |  |  |  |  |  |  |  | 152 | 152 |
| 2a | People Assisted to get a job | 25 |  |  |  | 39 | 39 | 39 | 156 | 195 |
| 3d | New Enterprise created |  |  |  |  |  |  |  | 100 | 100 |
| 4i | Businesses Assisted – Management/ Leadership |  |  |  |  |  |  |  | 25 | 25 |
| 4l | Businesses Assisted – ICT |  |  |  |  |  |  |  | 15 | 15 |
| 5e | Regeneration – Public Realm (£m) |  |  |  |  |  |  |  | 0.1 | 0.1 |
| 6a | People Achieve Level 2 |  |  |  |  |  |  |  | 35 | 35 |
| 6b | Basic Skills |  |  |  |  |  |  |  | 23 | 23 |
| 6c | Work based training |  |  |  |  |  |  |  | 5 | 5 |
| 6d | Achieve Level 3 |  |  |  |  |  |  |  | 13 | 13 |
| 6f | People on Vocational Training Course | 25 |  |  |  | 34 | 34 | 34 | 141 | 175 |

5.0	NWDA CLAIM SUMMARY - QUARTER 4 2006/7 – EXPENDITURE AND FINANCIAL CLAIM

5.1	The table below details the predicted and actual expenditure and NWDA claim for the last quarter (January – March) and predicted spend for the next quarter (April – June).

| Scheme | Sub Projects | 2006/7 | 2007/8 |
| --- | --- | --- | --- |
|  |  | Quarter 4 | Quarter 1 |
|  |  | Predicted (£) | Actual (£) | Variance (£) | Predicted (£) |
|  |  | Total | NWDA | Total | NWDA | Total | NWDA | Total | NWDA |
| Economic Strategy | Economic Strategy | 77,000 | 64,167 | 72,302 | 60,250 | -4,698 | -3,917 | 43,000 | 35,833 |
|  | Learning City Study |  |  |  |  |  |  | 10,000 | 10,000 |
| BRH/ Job Brokerage | Bringing Regeneration Home |  |  |  |  |  |  | 34,750 | 8,494 |
|  | Job Brokerage |  |  |  |  |  |  | 15,000 | 7,000 |
| Redundancy/ Into Work | Employment Projects | 30,000 | 13,236 | 18,876 | 8,328 | -11,124 | -4,908 | 57,000 | 25,148 |
| Visitor Economy | Developing Visitor experience 2006/7 | 37,000 | 37,000 | 37,497 | 37,497 | 497 | 497 |  |  |
|  | Developing Visitor experience 2007/8 |  |  |  |  |  |  | 45,000 | 28,420 |
|  | Urban Design Framework |  |  |  |  |  |  |  |  |
| Castle Way Study | Castle Way Study | 10,000 | 10,000 | 10,000 | 10,000 |  |  |  |  |
| Tourism Business Support | Tourism Business Support |  |  |  |  |  |  | 20,000 | 11,578 |

| Scheme | Sub Projects | 2006/7 | 2007/8 |
| --- | --- | --- | --- |
|  |  | Quarter 4 | Quarter 1 |
|  |  | Predicted (£) | Actual (£) | Variance (£) | Predicted (£) |
|  |  | Total | NWDA | Total | NWDA | Total | NWDA | Total | NWDA |
| East Cumbria Business Support | East Cumbria Business Support |  |  |  |  |  |  | 20,000 | 10,000 |
| Historic Quarter | Historic Quarter Tourism Research and Action Plan |  |  |  |  |  |  | 15,000 | 10,714 |
| TOTAL |  | 154,000 | 124,403 | 138,675 | 116,075 | -15,325 | -8,328 | 259,750 | 147,187 |

6.0	COMMENTARY

6.1	Progress has been made since the last report in all of the projects.  This report, however, has highlighted delays in the strategic Economic Strategy project.  Other large consultancy commissions i.e. historic quarter, urban design framework and brand development study will all be commissioned in quarter 1 or early quarter 2 of this year.  Some catching up of time and expenditure is required but at this stage is considered to be achievable.

6.2	Two projects the Castle Way and Learning Village Studies have been completed in financial terms.  The results will now need to feed into informing and shaping other elements of the programme, for example, the Historic Quarter study in the case of the Castle Way report.

6.3	Individual sub projects within the Employment Projects (retail academy and Job Brokerage) these are still to be developed to tender or delivery phase.  These will be subject to increased monitoring to ensure that realistic and worthwhile projects can be delivered within the programme period.

6.4	New projects and significant changes to existing projects have been able to be accommodated without unbalancing the programme as a whole and retaining the funding and output profiles.  The City Council now has the comfort of these changes being formally approved by the Agency.  The subsequent issue of the capital/revenue split within the Urban Design and Public Realm Framework, however, remains to be agreed.

6.5	The first quarterly claim produced outputs above those predicted, met all its milestones and was within 7% of the anticipated claim profile.