CARLISLE CITY COUNCIL                                                                                                                    Appendix One

REVIEW OF HOMELESSNESS SERVICE AND HOSTEL PROVISION 2004/05

OUTLINE DRAFT SERVICE IMPROVEMENT ACTION PLAN – 12/7/05 for period 2005 -07

| Area for Improvement | Specific Improvement Action (If Required) | Measurable | Attributable (Source) | Resourced | Time bound Phase 1 – end 31/8/06 Phase 2 – 1/9/06 – 31/12/07 | Risk Assessment If No Action Impact/ Likelihood* | Priority For Improvement Quick Win Medium Term Longer Term** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Key Themes for Partnership Development |
| 1. Approaches to allocations and lettings (social housing) may be impacting adversely on homelessness/temporary accommodation – blockages regarding accepted households moving into permanent accommodation | 1.1 District wide review of approaches to allocations and lettings 1.2 Review with RSL’s introduction of a common Housing register / Property shop / advice centre | Reducing numbers in temporary accommodation/ hostels Reducing time spent in temporary accommodation/ hostels Enabling households to move into permanent housing – bringing empty property back into use (pilot scheme with CHA) Development of Register / property shop / advice centre | Self assessment and external review As above | Staff time Partner time Housing Strategy Capital funding As Above | Phase 1 Start process by Nov 05 August 2005 Start process by Jan 06 | 9 6 | Medium term Long term |
| 2. Provision and need may not be in balance | 2.1 Mapping of provision of temporary accommodation/move on accommodation/ supported housing against need 2.2 Mapping of provision of homeless service against current and predicted homeless presentations | Balance between service provision and need | Self assessment and external review | Not yet clear | Phase 2 By March 2007 | 6 | Medium term |
| 3. Overall provision of support and accommodation – specialist and temporary service throughout the area | 3.1 Looking at the Value aspects within service provision which are assessed as part of the Supporting People Review process – Review has stated that service needs to move from level C provision to level B over the lifetime of the 3 year contract * | Value for money review carried out by Supporting People team in line with ODPM national guidelines on Quality Assessment for Support Services | Self assessment and external review – Supporting People contract review | To be established | Phase 2 By end 2007 * Quality Assessment Framework – ODPM 03 | 6 | Medium term |
| KLOE Sub Theme: Access, Customer Care and User Focus |
| 4. Gaps in staff knowledge in relation to full range of enquiries and referrals to other agencies | 4.1 Staff training using case study scenarios 4.2 Integration of the team 4.3 Use of logging system 4.4 Performance manage to improve the service | Demonstrable knowledge of full range of enquiries and ability to access appropriate information/make referrals | Self assessment and external review against KLOE No 8 | Training budget Establishment of systems – staff time | Phase 1 By April 2006 | 9 | QW |
| 5. Service standards are underdeveloped | 5.1 Develop challenging service standards, consult with service users, develop and implement monitoring system to ensure standards are met and performance communicated | Timescale standards met Positive feedback from service users | Self assessment and external review against KLOE No 8 | Minimal cost Staff time to develop and implement | Phase 1 By end August 2006 | 4 | QW |
| 6. Arrangements to identify and prevent potential cases of threatened (or imminent) homelessness are weak (e.g. CHA only notify once legal and only if tenant agrees) | 6.1 Develop improved “early warning” systems and procedures in partnership with RSLs, private landlords and mortgage lenders homelessness amongst ex-offenders and those with mental health issues 6.2 Continue partnership with probation and the CDRP (Crime and Disorder Reduction Partnership) to tackle offender accommodation problems 6.3 Continue and strengthen use of RESOLVE to prevent homelessness amongst young people | Prevention of homelessness (numbers of cases) As Above As Above As Above | Self assessment and external review against KLOE No 8 As Above As above As Above | Staff time Staff time Staff time / ODPM Grant Staff time / ODPM Grant | Phase 1 By March of 2006 2006 (to fit in with the Supporting People strategic review of Floating Support services) Immediately Immediately | 9 9 9 9 | Medium Long term Quick Win Quick Win |
| 7. Interview rooms not always equipped for the job | 7.1 Develop clear specification as part of re-building | Interview rooms are private, high standard and allow access to IT case files etc. | Self assessment and external review against KLOE No 8 | As part of post-flood refurbishment | Phase 1 In accordance with refurbishment programme timescales – end 05 | 9 | Medium term |
| 8. Not currently gaining customer feedback on homelessness service or using to develop service delivery or improvements | 8.1 Implement and use customer satisfaction measurement | Positive feedback from service users Suggestions, complaints routinely used to develop service delivery | Self assessment and external review against KLOE No 8 | Costs of data analysis – staff time Postage costs | Phase 2 By (suggest end August 2007 | 4 | QW |
| 9. Out of Hours (OOHs) service: Inconsistency of provision Quality not checked | 9.1 Resolve job description/single status issues 9.2 Gain staff commitment 9.3 Test effectiveness of OOHs service through mystery shopping 9.4 Publicising OOHs service 9.5 Profile OOHs service by assessing numbers and complexity of OOHs calls 9.6 Produce clear guidance and procedures for OOHs service | Effective OOHs service Positive feedback from service users | Self assessment and external review against KLOE No 8 | Costs of testing service through mystery shopping (explore potential for reciprocal arrangement with another district) | Phase 2 By end August 2007 | 6 |  |
| KLOE Sub Theme: Diversity |
| 10. Written information does not have community language straplines or offer of large print, Braille or audio versions | 10.1 Ensure all customer-facing material advertises availability of translations, large print, Braille and audio | All material routinely carries relevant strap lines (and customers can request information in alternative formats as required) | Self assessment and external review against KLOE No 8 | As leaflets, letters etc. re-printed (or add sticker at low cost) | Phase 2 By end of 2007 | 4 | QW |
| KLOE Sub Theme: Housing Advice, Homelessness Prevention and Options Services |
| 11. Significant repeat homelessness (many with history of ASB, criminality or dependency) | 11.1 Analyse and review causes as well as continued partnership working with other involved agencies 11.2 Establish safety net mechanisms and targeted preventative work | Reduction in repeat homelessness | Self assessment and external review against KLOE No 8 | Staff time | Phase 1 By Nov 2006 | 12 | Medium term |
| 12. Linkage between general housing advice and proactive welfare benefits advice need to be strengthened | 12.1 Further develop information sharing protocols and liaison meetings to discuss debt and benefits advice and case reviews of homeless/potentially homeless clients | Improved welfare benefits advice to homeless/potentially homeless clients and reduce incidence of homelessness/increase prevention | Self assessment and external review against KLOE No 8 | Staff time | Phase 1 By August 2006 | 9 | Medium term |
| 13. Approach to prevention of homelessness in partnership with other advice agencies (often ad hoc) could be structured and implemented better | 13.1 Develop and implement clear protocols with partner agencies (RSLs, CAB, Shelter, PROP, Probation, CASS, Housing/Council Tax Benefit, Jobcentre, health, etc)) | Protocols developed and implemented Reduction in homelessness | Self assessment and external review against KLOE No 8 | Staff time Partner time | Phase 1 By August 2006 | 9 | Medium term |
| 14. Advice services not yet compliant with community legal service standards | 14.1 Investigate and pursue CLS standards | CLS accreditation | Self assessment and external review against KLOE No 8 | Staff time Accreditation costs? | Phase 2 By June 2008 | 4 | Longer term |
| 15. Web site information not reviewed | 15.1 Review and update website with current service practices and standards | Content updated (and regularly reviewed) On-line application On-line advice | Self assessment and external review against KLOE No 8 | Staff time ICT resources | Phase 2 By June 2008 | 2 | QW |
| 16. Cumbria-wide arrangements seen as cumbersome and slow | 16.1 Review appropriateness with Cumbria-wide Homeless Group | Decisions of review of arrangements | Self assessment and external review against KLOE No 8 | Staff time | Phase 2 June 2008 | 4 | Medium term |
| 17. Targets for homelessness officers are not linked into corporate appraisal system | 17.1 Ensure that service targets are cascaded and reviewed as part of individual performance appraisal | Targets are set and being met | Self assessment and external review against KLOE No 8 | No cost | Phase 2 By end 2007 | 4 | Medium term |
| KLOE Sub Theme: Homelessness Services |
| 18. No case load reviews and case loads per officer are high | 18.1 Implement management case load reviews and ensure work is allocated consistently 18.2 Consider resourcing requirements using analysis of homeless presentations and projections | Reviews of caseloads and specific cases undertaken Staffing numbers appropriate to level of homelessness | Self assessment and external review against KLOE No 8 | Management time | Phase 1 By end 2005 | 9 | QW |
| 19. further Appeals process is currently unhelpful and not timely | 19.1 Look at best practice in appeals elsewhere | Appeals process conforms to best practice standards | Self assessment and external review against KLOE No 8 | Staff time Member training/Member time? | Phase 1 By August 2006 | 6 | Quick win |
| 20. Protocols with social services and health are insufficiently developed | 20.1 Build relationships through continuation of review groups as homelessness key partners liaison group | Effective relationships? | Self assessment and external review against KLOE No 8 | Staff time Partner time | Phase 1 On-going / immediate | 12 | Medium term |
| 21. Paperwork to support appeals process insufficiently robust to withstand legal challenge | 21.1 Establish and implement standard paperwork (IT based if feasible) to support legal process | Reduced legal challenges | Self assessment and external review against KLOE No 8 | Staff time Legal advice | Phase 1 By December 2005 | 12 | QW |
| 22. Procedures have not recently been updated to reflect current practices | 22.1 Undertake process mapping exercise and update procedures to reflect all aspects of the service | Procedures developed and systematically implemented | Self assessment and external review against KLOE No 8 | Staff time Internal/external consultancy support | Phase 2 By September 2007 | 4 | QW |
| 23. Staff training/induction on procedures, processing applications, interviewing skills or general good practice could be developed | 23.1 Use process maps and procedures to train and update existing staff and to induct and train new staff 23.2 Interview skills training Training on wider homelessness issues | Training plan developed and delivered | Self assessment and external review against KLOE No 8 | Staff time External training costs | Phase 2 By June 2007 | 6 | Medium term |
| 24. No quality assurance/monitoring in place to ensure robustness and consistency of decision-making | 24.1 Implement quality assurance checks on 10% of decisions | Consistency of decision-making Reduction in appeals | Self assessment and external review against KLOE No 8 | Management time | Phase 2 By end September 2007 | 4 | QW |
| 25. Letters/communication have not been assessed for plain language | 25.1 Develop standard letters and have them Crystal Mark validated 25.2 Link to computer-based process maps/procedures | Clear standard paperwork in place and used consistently | Self assessment and external review against KLOE No 8 | Staff time Cost of Crystal Mark assessment | Phase 2 By end September 2007 | 4 | QW |
| KLOE Sub Theme: Temporary Accommodation for Homeless Households |
| 26. No open access accommodation - to be linked with future models of support and accommodation provision assembled under phase 2 | 26.1 Review need and resources through homelessness key partners liaison group including Supporting People (SP) services and the SP 5 year strategy | Development of project | Self assessment and external review against KLOE No 8 | Staff time Cost of establishment or change of use? | Phase 1 End 2006 | 12 | Longer term |
| 27. Significant gaps in specialist provision e.g. young people leaving care, women’s refuges, last chance accommodation - to be linked with future models of support and accommodation provision assembled under phase 2 28. Engage partner organisations in a debate regarding housing and support provision for vulnerable people | 27.1 Map existing provision and review scale and appropriateness compared to need and resources through homelessness key partners liaison group including Suppoportng people services 28.1 A partnership vision and plan for housing and support provision in Carlisle | Identifying provision needs and project development | Self assessment and external review against KLOE No 8 | Staff time Cost of establishment | Phase 1 End 2006 June 2006 | 12 | Longer term |
| 29. Significant gaps in “move on” provision and lack of floating support - to be linked with future models of support and accommodation provision assembled under phase 2 | 29.1 Map existing provision and review scale and appropriateness compared to need and resources through homelessness key partners liaison group including Supporting People services | Identifying provision needs and project development | Self assessment and external review against KLOE No 8 | Staff time Cost of establishment | Phase 1 Start 2006 | 12 | Longer term |
| 30. Scope for increased dispersed properties – to be linked with future models of support and accommodation provision assembled under phase 2 | 30.1 Map existing provision and review scale and appropriateness compared to need and resources through homelessness key partners liaison group including Supporting People services | Identifying provision needs and project development | Self assessment and external review against KLOE No 8 | Staff time Cost of establishment | Phase 1 Start 2006 | 12 | Longer term |
| 31. “Buck passing” the most difficult clients | 31.1 Improve communication between agencies to proactively deal with these clients | Improved working between agencies | Self assessment and external review against KLOE No 8 | Staff time | Phase 1 Start 2006 | 16 | Medium term |
| 32. Legal challenge issues relating to provision of accommodation even when difficult clients evicted | 32.1 Reconsider legal position and establish clear criteria | Criteria established | Self assessment and external review against KLOE No 8 | Staff time Legal advice costs | Phase 1 By Dec 2006 | 12 | Medium term |
| 33. Lack of clear standards for Temporary Accommodation and no regular checks made | 33.1 Establish clear standards (including H&S assessment) and set targets for checks to be made | Checks undertaken and any follow up action implemented | Self assessment and external review against KLOE No 8 | Staff time | Phase 1 By March 2006 | 9 | QW |
| 34. Lack of risk assessment of staff working in hostels - staff feel under-valued and exposed to risk | 34.1 Undertake risk assessment and develop action plan to minimise risk | Action plan produced and implemented | Self assessment and external review against KLOE No 8 | Staff time | Phase 1 Immediate | 16 | QW |
| 35. Increasing use of B&Bs | 35.1 Undertake analysis to identify if short term blip or longer-term trend 35.2 Establish standards and checks for B&Bs where used 35.3 Develop action plan to reduce B&B through other means (as above) | Reduction in use of B&B | Self assessment and external review against KLOE No 8 | Staff time | Phase 1 immediate | 12 | Q/W |
| 36 Lack of budgets for storage of peoples belongings | 36.1 Consider if budgets needed and allocate or explore alternative proposals e.g use of hostel storage facilities,alternative council provision | Clear policy on storage of people’s belongings | Self assessment and external review against KLOE No 8 | Staff time Potential budget for storage established | Phase 1 By April 2006 | 12 | QW |
| 37. . Budgets for repairs and maintenance held by technical services | 37.1 Consider if this budget should be held by hostel service and work commissioned by them | Budget clarified | Self assessment and external review against KLOE No 8 | No cost | Phase 2 By end 2007 | 4 | Medium term |
| KLOE Sub Theme: Value for Money |
| 38. Issue of potential procurement options for both temporary accommodation and homelessness assessment have not been fully explored | 38.1 Undertake full options appraisal for all elements of service and develop procurement approach | Decisions taken on procurement options and implemented | Self assessment and external review against KLOE No 8 | Staff time Cost of tender exercise if required | Phase 2 By end 2007 | 9 | Medium term |

*Risk Assessment - Impact: 1= Negligible: 2 = Marginal: 3 = Critical: 4 = Catastrophic Likelihood: 1 = Extremely Remote: 2 = Remote: 3 = Reasonably Probable 4 = Probable

** Priority for Improvement – QW: Quick Win. Medium term and long term