January Flood - Emergency Planning Review – Action Plan

|  | Issue/Action | Lead Responsibility | Timescale | Resources/£ |
| --- | --- | --- | --- | --- |
|  | Alerting/Call-out/Communications |  |  |  |
| 1. | In light of network failures, consider multi-network roving mobile phones for up to 6 key responders | John Nutley/Michael Scott | 31/07/05 | Existing or bid within Business Planning process |
| 2. | In light of power failure affecting communications, advise all senior managers to have at least one none digital, non wireless telephone handset | John Mallinson | Done | Existing |
| 3. | In light of power failure advise all senior managers to have a battery powered radio | John Mallinson | Done | Existing |
| 4. | In light of Civic Centre inaccessibility, all senior managers to hold contact information for all their staff off site | CMT | 31/07/05 | Existing |
| 5. | In light of Civic Centre inaccessibility, Personnel Managers to hold back-up disc of contact information for all staff off site | D Williams | 31/07/05 | Existing |
| 6. | To assist key responders in holding Emergency Response Plans off site, consider provision of ultra-lightweight pocket PC’s | John Nutley | 31/08/05 | Existing or bid within Business Planning process |
| 7. | In light of extent of emergency and communications difficulties, provide greater level of cover for all emergency response roles | Emergency Planning Working Group | 30/09/05 | Existing |
| 8. | In light of importance to initial response review and enhance normal out of hours service contact arrangements | John Nutley | 31/08/05 | Existing or bid within Business Planning process |
| 9. | In light of rapid escalation and extent of emergency, review standby arrangements for key responders | Emergency Planning Working Group | 30/09/05 | Existing or bid within Business Planning process |
|  | Emergency Control Centre |  |  |  |
| 10. | To speed set–up of Civic Centre ECC, have laptop PC’c and wireless network access, together with enhanced first floor storage space | Michael Scott | In -hand | Insurance claim/existing |
| 11. | In light of Civic Centre inaccessibility, provide alternative ECC location at Bousteads Grassing | Mike Battersby | In-hand | Existing or bid within Business Planning process |
| 12. | In light of Civic Centre flooding, evaluate options to relocate stand-by generator to more resilient position | Mike Battersby | In -hand | Insurance claim/existing |
|  | Emergency Response Plan |  |  |  |
| 13. | Complete outstanding sections for Finance and Personnel Teams | Angela Brown/David Williams | 30/07/05 | Existing |
| 14. | In light of establishment of Customer Contact Centre, rewrite Public Information/Telephone Enquiry section | John Nutley | 30/07/05 | Existing |
| 15. | In light of changes to Environmental Protection Services Business Unit, rewrite their section | Mike Battersby | 30/07/05 | Existing |
| 16. | To enhance Welfare Response, include section integrating Community Support Team into welfare arrangements | Rob Burns | 30/09/05 | Existing |
| 17. | In light of extent of their involvement, include separate section integrating Commercial and Technical Services response arrangements | Mike Battersby | 30/09/05 | Existing |
|  | Reception Centres |  |  |  |
| 18. | To prevent conflicting priorities, designate senior manager to be lead officer instead of Emergency Planning Lead Officer | Maggie Mooney | 30/09/05 | Existing |
| 19. | To provider greater co-ordination, Designated Reception Centre lead officer to co-ordinate broader range of reception issues including interface with voluntary agencies, finance and liaison with site owners and operators in addition to co-ordinating CHA contractual responsibilities | John Mallinson | 30/09/05 | Existing |
| 20. | To ensure more rapid and comprehensive response, Housing/homelessness services to be fully integrated into Reception Centre activation and represented on site from set-up | Simon Taylor | 30/09/05 | Existing |
|  | Training and Exercises |  |  |  |
| 21. | To provide greater clarity and extend cover, provide senior managers with training in relation to Gold and Silver Command structure and operation | John Mallinson/County Emergency Planning Unit | 31/12/05 | Existing |
| 22. | To equip more senior managers to respond effectively in a wider range of scenarios, provide generic emergency management training in addition to established functional training programme | John Mallinson/County Emergency Planning Unit | 31/12/05 | Existing |
| 23. | To provide effective training for new emergency planning responders (as provided for by above actions), undertake additional targeted training sessions | John Mallinson/County Emergency Planning Unit | 31/12/05 | Existing |
|  | Business Continuity Plan |  |  |  |
| 24 | In light of experience, review council’s Business Continuity Plan | Karen Hook | 31/12/05 | Existing or bid within Business Planning process |
|  | Other Agencies |  |  |  |
| 25. | Commercial and Technical Services and Environment Agency to jointly review specific flood response arrangements, local plan and distribution of EA multi-agency plan | Mike Battersby/Environment Agency | In-hand | Existing |
| 26. | County Emergency Planning Unit be requested to lead on greater integration of GIS support into County General Emergency Plan on multi-agency, countywide basis. | County Emergency Planning Unit | 31/12/05 | Existing |