OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 28 September 2006 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.72/06 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 July to 31 October 2006, 1 August to 30 November 2006 and 1 September to 31 December 2006.

Recommendations:	To note the modifications, deferrals and departures from the previous Forward Plans.

| Contact Officer: | Elspeth MacKay | Ext: | 7034 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

2.1	Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the periods 1 July to 31 October 2006, 1 August to 30 November 2006 and 1 September to 31 December 2006 are outlined in Appendix A of this report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the previous Forward Plans be noted.

Contact Officer:		Elspeth MacKay						Ext: 7034

1st July to 31st October 2006

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.027/06 | Environmental Enhancements Infrastructure O&S Committee | The item was not included in the Forward Plan. It was considered by the Executive on 3 July 2006 under General Exception rules | Corporate Management Team |
|  | Reason: Any delay in the City Council’s consideration of the matter would also delay work on any approved programme of schemes should additional finance be made available. |
| KD.037/06 | Introduction of a Framework Agreement for a range of Consultancy Services Corporate Resources O&S Committee | The item was scheduled to be considered at the Executive on 3 July but has been withdrawn from the Forward Plan | Director of Corporate Services |
|  | Reason: Officers were waiting further information from the North West Centre of Excellence on their Framework Work Package. |
| KD.033/06 | Planning Enforcement Policy Infrastructure O&S Committee | Item was scheduled to go to Executive on 3 July and 29 August 2006 – but it is no longer going on 29 August. | Executive |
|  | Reason: The Executive, at the meeting on 3 July 2006, forwarded the Policy to Council. The Executive were really receiving the Policy for information as it is a Development Control Committee Policy which needs to be approved by the Council. The Infrastructure O&S Committee and the Development Control Committee have both been involved during the development of the Policy. |
| KD.035/06 | Belah Community Centre Community O&S Committee | Item was scheduled to go to Executive on 31 July but was withdrawn from the Forward Plan and deferred to an Executive date yet to be determined. | Senior Management Team |
|  | Reason: To allow further work to be undertaken by officers. |
| KD.038/06 | Supporting Sustainable Communities Community O&S Committee | Item was scheduled to go to Executive on 31 July but was withdrawn from the Forward Plan and deferred to an Executive date yet to be determined. | Senior Management Team |
|  | Reason: To allow time for officers to obtain the necessary information for the report to be linked into the Community Planning process for the Local Strategic Partnership. |
|  | Cumbria Minerals and Waste Development Framework | The item was not included in the Forward Plan. It will be considered by the Executive on 31 July 2006 under General Exception rules | Senior Management Team |
|  | Reason: An issues and options discussion paper was received from Cumbria County Council with a response required before the August meeting of the Executive. The paper was not received before the Forward Plan was published and therefore the item could not be included in the Forward Plan. |
| KD.028/06 | Energy Surveys – Improving our Buildings | The Plan stated that the matter would be considered by the Corporate Resources on 27 July and Infrastructure O&S Committee on 3 August 2006, but it was withdrawn from the agendas for these meetings | Director of Community Services |
|  | Reason: Agenda item withdrawn on day of despatch of reports |

1st August to 30 November 2006

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.040/06 | Partnership Approach to the Reconfiguration of Homelessness Accommodation Community O&S Committee | The Plan stated that the matter would be reported to Executive on 3 July. This is incorrect, the matter has not yet been to the Executive and will be considered on 29 August and 25 September 2006 |  |
|  | Reason: Error in entering the data into the Forward Plan database. The reference should have been entered against the Carlisle District Local Plan item – KD.040/05 |
| KD.032/06 | Equality and Diversity Policy Community O&S Committee | The Plan stated that the matter would be reported to Executive on 24 April and September or October 2006 – the latter dates have been revised to October, November or December 2006. It has also been clarified that that Corporate Equality Action Plan will be reported to Community O&S Committee on 31 August 2006, with the draft Policy being considered at a later date. | Head of Policy and Performance Services |
|  | Reason: The reporting dates have been clarified. The draft Policy will be considered by Community O&S Committee at a time when some of the consultation feedback should be available. |
| KD.034/06 | Concessionary Fares Infrastructure O&S Committee | The Plan stated that the item would be considered on 12 June and October 2006. Instead of October it will now be considered by the Executive in September and November and will go to Infrastructure in between. | Head of Revenues and Benefits |
|  | Reason: Spending is currently above budgeted expenditure and there is a need to make a decision more quickly than originally anticipated. |
| KD.030/06 | Improving the Environmental Performance of the Council Infrastructure O&S Committee | The Plan stated that the item would be considered by Executive on 3 July and 29 August 2006. The August date has been changed and it will now be considered by the Executive on 25 September 2006. It was due to be considered by Infrastructure O&S Committee on 3 August 2006 but was withdrawn from the agenda and will now be considered on 14 September. | Director of Community Services |
|  | Reason: As the item was withdrawn from the agenda for the Infrastructure O&S Committee on 3 August the matter has not yet been considered by O&S Committee. It has been deferred in order to allow O&S to comment at the meeting on 14 September 2006 |
| KD.042/06 | Multi-Use Games Area – Raffles Community O&S Committee | The Plan stated that the item would be considered by the Executive on 29 August 2006 but this has been deferred to the Executive on 25 September 2006. | Director of Community Services |
|  | Reason: Negotiations are ongoing with potential co-funders and have not reached a stage yet to enable a report to be produced to Executive. |
| KD.044/06 | Bitts Park Tennis Airdome Community O&S Committee | The Plan stated that the item would be considered by the Executive on 29 August 2006 but this has been deferred to the Executive on 25 September 2006. | Director of Community Services |
|  | Reason: Still awaiting resolution of the final account for Stoneyholme which will define the balance of Council funding. Discussions are ongoing with Carlisle Leisure Limited regarding the level and availability of their contributory funding. |
| KD.026/06 | Health and Safety Work Plan 2006-07 and progress with Health and Safety Improvement Plan for the Food, Health and Safety Team in Community Services Community O&S Committee | The Plan stated that the item would be considered by the Executive on 29 August 2006 but it has been deferred to the Executive on 25 September 2006 | Director of Community Services |
|  | Reason: To allow time for the collection of further information which has unfortunately been delayed. |
| KD.039/06 | Raffles Vision – Options for Vacant Properties Community O&S Committee | The item was due to be considered by Community O&S Committee on 12 October 2006, but the meeting has been re-scheduled and will now be held on 18 October 2006 | Meeting date changed by the Community O&S Committee |
|  | Reason: The Community O&S Committee in October 2006 has been re-scheduled |
| KD.046/06 | Carlisle Renaissance – North West Development Agency (NWDA) Funding Application 2006/07 Infrastructure O&S Committee | The Plan stated that the item would be considered by the Executive on 29 August 2006 but it has been deferred to 25 September 2006. The item was due to be reported to the Infrastructure O&S Committee on 3 August 2006 but was withdrawn from the agenda. It will be reported to Infrastructure on 14 September 2006 or 26 October 2006. | Director of Carlisle Renaissance |
|  | Reason: It was not possible to complete the report for the 3 August meeting as there was outstanding information from a third party sponsored project within the overall NWDA Programme Bid. Deferring the report until the Executive in September will allow further detailed work to be undertaken on the bid. |

1st September to 31 December 2006

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.046/06 | Carlisle Renaissance – North West Development Agency (NWDA) Funding Application 2006/07 Infrastructure O&S Committee | The item was due to be reported to the Infrastructure O&S Committee on 14 September 2006 but was withdrawn from the agenda. | Director of Carlisle Renaissance |
|  | Reason: In order that the matter may be referred to the Overview and Scrutiny Management Committee for a decision on how Overview and Scrutiny will deal with the NWDA funding, projects, performance, etc. |
|  | Office of the Deputy Prime Minister Flood Recovery Plan Community O&S Committee | The item was not included in the Forward Plan. It will be considered by the Executive on 29 September 2006 under General Exception rules | Deputy Chief Executive and Director of Community Services |
|  | Reason: Decisions on the re-allocation of funds from projects which have underspent their allocations must be taken by such a date that it is impractical to defer the decision until the item has been included in the next Forward Plan. |
| KD.041/06 | Housing Capital Programme Progress Update Report Community O&S Committee | The item was originally scheduled to go to Executive on 29.08.06 and 26.09.06. It will now be reported to 23.10.06 as well and to Community O&S on 18.10.06 | Executive |
|  | Reason: The Executive on 29.0.806 referred the report back to the Director of Development Services for further work on re-profiling the capital budget and progress with the various schemes |