OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 7 JULY 2005 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.032/05 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 May to 31 August and 1 June to 30 September 2005.

Recommendations:	To note the modifications, deferrals and departures from the Forward Plans for 1 May to 31 August and 1 June to 30 September 2005.

| Contact Officer: | Elspeth MacKay | Ext: | 7034 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the periods 1 May to 31 August and 1 June to 30 September 2005 are outlined in Appendix A of this report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the Forward Plans for 1 May to 31 August and 1 June to 30 September 2005 be noted.

Contact Officer:		Elspeth MacKay						Ext: 7034

1st May 2005 to 31 August 2005

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.012/05 | Performance Plan Corporate Resources O&S Committee – but will also go to other 2 O&S Committees | Dates of Overview and Scrutiny Committees have now been scheduled as follows: Community O&S – 9 June 2005 Infrastructure O&S – 8 June 2005 Corp Resources – 7 June 2005 | Dates of meetings agreed with Chairmen of O&S Committees |
|  | Reason: When the last Forward Plan was produced that dates of the Special meetings of O&S had not been agreed – the dates have now been finalised. |
| KD.030/04 | Development Plan for Carlisle Museums and Gallery Service Community O&S Committee | The matter was scheduled to be reported to Community O&S Committee on 9 June, but this has been changed to 21 July 2005 | Head of Culture, Leisure and Sport |
|  | Reason: The matter had been scheduled incorrectly – it should have been scheduled to go to Executive first and then to Overview and Scrutiny for comments. |
| KD.024/05 | Arts Strategy for Carlisle Community O&S Committee | Removed from Executive agenda | Leader and Executive Members |
|  | Reason: The matter is to be included in forthcoming work on developing a cultural strategy |
| KD.007/05 | Capital Strategy and Asset Management Plan Corporate Resources O&S Committee | Deferred from Executive on 13 June to 20 June 2005 (Special meeting). The matter was scheduled to go to Corporate Resources O&S Committee on 16 June, but this will also be deferred | Leader and Executive members |
|  | Reason: The Budget policy documents need more consideration in light of the updated Council priorities considered by the Executive on 13 June. The outturn reports have been deferred to allow more time to consider the financial position. |
| KD.018/05 | Draft Regional Spatial Strategy Infrastructure O&S Committee | Deferred from Executive in July or August or September to Executive in October or November 2005 | Head of Planning Services |
|  | Reason: The draft Regional Spatial Strategy was due to be published for consultation in July 2005. The NWRA have asked the Office of the Deputy Prime Minister for an extension of time to publish the draft until September 2005. This request has been supported by Government Office North West and it is assumed that this request will be granted. The Forward Plan has been amended to reflect this delay. |
| KD.025/05 | Information and Communications Technology (ICT) Strategy Corporate Resources O&S Committee | Deferred from 4 July and 1 August Executive meetings to 1 August and 26 September Executive meetings. The matter was scheduled to go to O&S on 28 July, but this will be deferred to 8 September 2005 | Head of Customer and Information Services |
|  | Reason: Delayed to enable fuller consultation to take place on the Strategy |

1st June 2005 to 30 September 2005

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.024/05 | Arts Strategy for Carlisle Community O&S Committee | Removed from Executive agenda | Leader and Executive Members |
|  | Reason: The matter is to be included in forthcoming work on developing a cultural strategy |
| KD.007/05 | Capital Strategy and Asset Management Plan Corporate Resources O&S Committee | Deferred from Executive on 13 June to 20 June 2005 (Special meeting). The matter was scheduled to go to Corporate Resources O&S Committee on 16 June, but this will also be deferred | Leader and Executive members |
|  | Reason: The Budget policy documents need more consideration in light of the updated Council priorities considered by the Executive on 13 June. The outturn reports have been deferred to allow more time to consider the financial position. |
| KD.018/05 | Draft Regional Spatial Strategy Infrastructure O&S Committee | Deferred from Executive in July or August or September to Executive in October or November 2005 | Head of Planning Services |
|  | Reason: The draft Regional Spatial Strategy was due to be published for consultation in July 2005. The NWRA have asked the Office of the Deputy Prime Minister for an extension of time to publish the draft until September 2005. This request has been supported by Government Office North West and it is assumed that this request will be granted. The Forward Plan has been amended to reflect this delay. |
| KD.025/05 | Information and Communications Technology (ICT) Strategy Corporate Resources O&S Committee | Deferred from 4 July and 1 August Executive meetings to 1 August and 26 September Executive meetings. The matter was scheduled to go to O&S on 28 July, but this will be deferred to 8 September 2005 | Head of Customer and Information Services |
|  | Reason: Delayed to enable fuller consultation to take place on the Strategy |