RESOURCES OVERVIEW AND SCRUTINY PANEL

Panel Report

| Public |
| --- |
| Date of Meeting: | 29 July 2010 |
| Title: | CORPORATE RISK MANAGEMENT |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 20/10 |

Summary:

The purpose of this report is to provide an update on risk management arrangements to members of the Resources Overview and Scrutiny Committee and to provide them with the opportunity to consider the Corporate Risk Register.

Questions for / input required from Scrutiny:

Scrutiny and feedback on the Corporate Risk Register.

| Contact Officer: | Jason Gooding | Ext: | 7009 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	Resources Overview and Scrutiny Panel

Date:	29th July  2010

- Background

In accordance with the Council’s Risk Management Policy, the draft Corporate Risk Register is submitted to this Panel for scrutiny (see attached appendix 1).

- Comments on the Corporate Risk Register

Following the restructure of the Senior Management Team and introduction of new Corporate priorities, a workshop was held to renew the Corporate Risk Register to reflect the new priorities and the Corporate Plan.

SMT and the Corporate Risk Management Group considered the issues and risks in delivering the Corporate Plan.  A risk management advisor from Marsh Ltd was also present to provide expert advice.

The corporate risks associated with delivering the Corporate Plan have been identified and assessed.  The current impact and likelihood of the risks have been scored according to criteria within the Council’s Risk Management policy.  The Action Status/ Control Strategies shown are the risk management strategies that are being adopted to reduce the impact and likelihood of the risks.

- Recommendations

The Panel is asked to scrutinise and comment on the renewed Corporate Risk Register as set out in Appendix 1.

| Corporate Risk Register Appendix 1 June 2010 |  |
| --- | --- |

| Title | Description | Current Risk Matrix | Matrix Review Dates | Current Risk Rating | Rating Description | Current Action Status / Control Strategy | Managed By |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Limited Resources | There is a risk that scarce resources are not directed to priority areas within the Council's key objectives of local environment and local economy |  | 15 Jun 2010 | 12 | Impact Critical Likelihood Reasonably probable | To make sure that the Transformation Programme, and the Medium Term Financial Plan and the Annual Budget are coherently focussed toward the appropriate allocation of resources to deliver the organisation's key objectives. | Deputy Chief Executive |
| Strategic Housing Authority | There is a risk that the Council fails to deliver in it's role as a strategic housing authority in achieving a balanced housing market |  | 16 Jun 2010 | 12 | Impact Critical Likelihood Reasonably probable | Develop and deliver the transformation of economic development to ensure the Council can make an effective contribution to economic development objectives for Carlisle. | Strategic Director |
| Use of Resources and Assets | There is a risk that the Council fails to adequately use resources and assets to stimulate, support and sustain economic growth in the area. |  | 16 Jun 2010 | 12 | Impact Critical Likelihood Reasonably probable | To put in place fit for purpose arrangements for the management of our strategic operation and investment. These will form the subject of the asset management strategy. | Deputy Chief Executive |
| Effective and Efficient Neighbourhood services | There is a risk that the Council fails to deliver effective and efficient neighbourhood services, and improve residents' perception of Carlisle through local environment issues. |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | To develop and implement a cost efficient approach to neighbourhood management with key Council Partners. | Assistant Director (Local Environment) |
| Workforce Planning | There is a risk that the Council is unable to continue to deliver and develop services due to lack of skills/capacity within the workforce |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | Workforce Planning Group established; Organisational Devt strategy being developed to address authority-wide issues; Workforce planning tools being developed to identify and address current workforce planning issues. | Chief Executive |
| Supporting Employers | There is a risk that the Council fails to adequately support employers during the economic downturn. |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | The review of Carlisle's economic development strategy will focus the City Council and other Partners on their role in supporting city employers and encouraging new development in the area. | Strategic Director |
| Vision for the City | There is a risk that there is no clear consensus/ vision for the City’s economy and no agreed strategy with Partners. |  | 16 Jun 2010 | 9 | Impact High Likelihood Reasonably probable | The review of the work of Economic Development and Carlisle Renaissance will be integrated toward a new Strategy and Action Plan. This will be prepared for the new working group and inform the delivery board that succeeds Carlisle Renaissance. | Assistant Director (Economic Development) |
| Delivering Key Objectives | There is a risk that Members, employees and Partners do not deliver the Council's key objectives of local environment and local economy |  | 15 Jun 2010 | 8 | Impact Critical Likelihood Remote | The Transformation Programme is being explicitly designed to deliver the Council’s objectives as described in the Corporate Plan. | Chief Executive |
| Equality | There is a risk that the Council fails to meet Equality framework targets. |  | 16 Jun 2010 | 6 | Impact High Likelihood Remote | The comprehensive equality framework is currently being worked on, to be adopted by the Council in preparation for IDeA in October 2010. This will include peer assessment as part of CIEP. | Deputy Chief Executive |
| Community involvement in decision making | There is a risk that communities are not sufficiently engaged in the Transformation programme. |  | 15 Jun 2010 | 4 | Impact Marginal Likelihood Remote | Having a clear engagement strategy so that those decisions that will affect the community are timely and appropriate. | Assistant Director (Community Engagement) |