CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 2 April 2009 |
| Title: | PAY AND WORKFORCE STRATEGY PROJECT UPDATE |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 06/09 |

Summary:

The project is in its final stage (Implementation). Although we had agreed a Final Negotiated Position with the trade unions in December the project has stalled and as a result the outcome will not now be implemented on 1 April as anticipated. Whilst one of the two main unions, GMB, has conducted a ballot of their members as we agreed the other is yet to do so. Indeed it appears, and for reasons as yet unclear, that not only is Unison unwilling to recommend that their members accept the deal that their local officials had negotiated it is now prepared to agitate against our agreed position.

The Senior Management Team is now developing its response to this situation.

Questions for / input required from Scrutiny:

Members to monitor progress.

Recommendations:

Members to note progress and comment as appropriate.

| Contact Officer: | David Williams | Ext: | 7082 |
| --- | --- | --- | --- |

- GENERAL PROGRESS

1.1	The Pay & Workforce Strategy (PWS) project has 6 work packages, i.e.

- Job Evaluation

- Equal Pay Review

- Review of People Policies and Terms and Conditions

- Single Status

- Workforce Development Plan

- PWS Implementation.

  - The project is in accordance with Prince 2 methodology and as such is overseen by a Project Board chaired by the Deputy Chief Executive. Regular progress reports are presented to Members of the Corporate Resource Overview and Scrutiny Committee, with the last one being 8 January 2008.

  - The project is in its final stage (Implementation) for which an Action Plan has been agreed. This plan also embraces the remaining actions that will complete the other work packages. Job Evaluation, Single Status and Equal Pay are the key elements at this stage. Progress is reported at-a-glance in the right hand column of the action plan (see Appendix 1) with more detail provided in the body of this report. In compliance with a request from CROS, this plan has been slightly modified to show revised target dates where appropriate.

  - Agreement had been reached with the trade unions in December on all aspects of single status and all elements of a new pay policy. Indeed, as was reported at your last meeting, in early January we had also achieved a Final Negotiated Position on the key issues of a pay-line, back pay and protection. We reported to you that two further steps remained before a formal agreement could be reached – a ballot of union members by the two main unions (GMB and Unison) and approval of the financial package by Members.

  - As regards Member approval, a meeting of the Employment Panel was to have been held in order for this panel to make a recommendation to full Council. This did not take place and due to reasons described in 1.6 below it is not now expected to meet for some time.

  - GMB have conducted their ballot and the result was a resounding endorsement of the deal. If this had been mirrored by Unison then there would have been sufficient time for us to have obtained the necessary formal approval from Members and to have then implemented on 1 April as scheduled. However, not only has Unison not progressed their ballot it appears that they are now actively agitating against the deal that was struck by their local officials.

  - The whole project has been conducted as a partnership exercise from the start, and this ethos had continued through three years of the project and indeed into the recent negotiations, with both unions going on record as saying that they would be recommending the deal to their membership. It appears that there has been an intervention by Unison nationally which has altered this relationship, one hopes only temporarily. It is our understanding that Carlisle City Council is not unique in having this recent experience.

  - There had been extensive communication of the agreed deal to employees who originally had been told that everything would change on 1 April. The effect that this delay and uncertainty is having on our employees is not hard to imagine. Unison’s recent and eventual communication to their members (they simply said nothing for two months) has further complicated matters. Employees are generally confused and unsettled, while some no doubt will welcome these developments others will be dismayed. As this report is being written, senior management are preparing a written communication to all employees.

  - These unwelcome recent developments have not only caused disappointment to the employer but there is also a significant impact upon the budget. Because we have no deal then there is no new Pay Policy nor a new Pay Structure with the result that ‘status quo’ terms and conditions for staff must remain in place for the foreseeable future. This means that many staff will receive increments on 1 April the removal of which had been factored into the outcome to achieve affordability. As a result unless costs are shaved elsewhere then the employer will face the burden of around an extra £100,000 as a result of the delay beyond 1 April.

  - We also now have no agreement to implement the single status arrangements to harmonise terms and conditions across the workforce. The costs of these improvements are covered within the chosen Pay Model: indeed all the individual elements of the deal are financially inter-dependent. For example, we know we need to remove potentially unlawful bonuses and attendance allowances and had successfully negotiated to do so, but the means to do so rests with the implementation of the outcome of job evaluation. If we do not have job evaluation then we will have to find another way of removing these historical anomalies. This may cause difficulties with GMB who hitherto have been very supportive.

  - Members asked at their last meeting that they be updated on staff turnover over the next 12 months, their expectation being that turnover will increase as a result of this project. The figures to date reveal that in fact turnover has decreased. The figures shown are those for avoidable turnover i.e. where the individual employee has a choice: full turnover would include e.g. staff coming to the end of temporary contracts and is less meaningful and as such is not shown:

#### Period							Avoidable Turnover

Oct - Dec 2007	      					1.8%

Jan - Mar 2008     	      					2.4%

Oct - Dec 2008 	      					2.6%

Jan - Mar 2009  (since pay structure announced) 	1.6%.

- SPECIFIC PROGRESS

  - Job Evaluation (JE)

    - Phase 1 Job Evaluation ended five months ago. Phase 2 of JE is well underway. This phase is scoring all those posts that:

- changed during the project e.g. through reorganisation

- are career graded i.e. other steps along the career path will now be scored

- are recently created new posts.

    - There will be a financial impact of Phase 2 estimated as being around £50,000. However, there was an allowance made in the project costing and negotiations for some increase in the budget as a result of Phase 2, which is scheduled to conclude within the next two months.

    - We are continuing with job evaluation through the current uncertainty as it is now a well-established, consistent, fair, and generally accepted method of determining the value of jobs. However, we have no new pay policy as yet which in theory could mean that our continued use of job evaluation beyond the project could be in doubt (see 2.4.1).

  - Single Status

    - Agreement was reached and implemented in April 2007 in three areas: holidays, sickness and overtime.

    - Agreement with the unions had also been reached last December in all of the remaining areas (bar one) although none can yet be implemented as explained in 1.10:

- Stand by/call out

- Professional fees

- Extent/pay for shift work/premium payments

- Additional duties/Acting up

- Bonus and other allowances e.g. tool, attendance, first aid.

    - The one remaining area was car lease/car allowances. SMT agreed that this matter be considered as part of the Green Travel Plan rather than within PWS and the unions were content with this. Since when CROS itself has decided to investigate.

  - Equal Pay

    - An analysis of our current pay structure from an equality perspective had been undertaken. No pressing issues were identified. Each pay model that was under consideration during the PWS Implementation stage included an analysis of the equality impact of the proposed new pay structure.

    - The final pay model, that was agreed at the time by both unions will, if it is implemented, remove virtually all pay gaps that currently exist between the sexes. Unison nationally now dispute this analysis although they have refused to show us their evidence to enable us to check the nature/veracity of their concerns.

  - Pay Policy

    - We had agreed a new Pay Policy for the authority providing consistent and robust principles and procedures. All the single status areas were assimilated and job evaluation was endorsed as the basis for determining pay in future.

    - Transitional arrangements such as back-pay and protection were agreed at the same time and included within the new pay policy.

    - Because only one of the unions have endorsed the outcome then the future of this policy is now in doubt.

- WAY FORWARD

3.1	SMT are now determining how to react to the recent surprising and disappointing unilateral departure by one union from the partnership approach adopted hitherto.

  - The letter officers had provided to CROS members, answering the detailed questions you raised at your last meeting, may well have provided clues as to why Unison have acted the way they have but local officials seem as unclear as we are.

  - A return to the negotiating table is the most likely first step. However, if Unison refuse to do so and/or continue on their current confrontational path then this authority may be forced to follow the action of several others around the country that have been faced with a similar situation and impose a settlement. Certainly status quo, after all that has happened and been achieved by the project, is an unlikely scenario.

4.	RECOMMENDATIONS

4.1	Members to note progress and comment as appropriate.

Appendix 1

### PWS Implementation Action Plan May 2008 – March 2009: Progress as at 20 March 2009

|  | Main work package | Tasks | Duration | Target date | Revised target date | Progress at 20 March 2009 |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Implement PWS | Draw up a pay policy; Principles Research market Consult (SMT, Members, unions, staff) Tie in with Single Status (see 2.1) | 1 month | End of July 2008 | Unknown | A new Pay Policy was agreed with both unions in December but now Unison are in dispute |
| 1.2 |  | Devise a pay structure: JE scores (see 4.1) Research markets for pay rates Pay modelling Costs Consult (SMT, Members, unions, staff) | 1 month | End of August 2008 | Unknown | A Final Negotiated Position was agreed with both unions in January but now Unison are in dispute |
| 1.3 |  | Member approval (Executive, CROS, Employment Panel, Council?) | 1 month | End of September 2008 | Unknown | Portfolio Holder is kept informed. CROS has received regular updates. An Employment Panel called for February was postponed given current uncertainty |
| 1.4 |  | Assimilate staff to new pay structure | 1 month | End of October 2008 | Unknown | Awaits outcome of 1.3 |
| 1.5 |  | Issue revised Statement of Provision to staff | 1 month | End of October 2008 | Unknown | Awaits outcome of 1.3 |
| 1.6 |  | Amend Trent so as to insert new staffing structure | 3 months | End of December 2008 | Unknown | Awaits outcome of 1.3 |
| 1.7 |  | Implement outcomes of Phase 2 Job Evaluation (see 4.2) as in 1.3 – 1.6 above | 5 months | End of March 2009 | Unknown | Phase 2 JE is well underway but its outcomes can not be implemented until 1.3 is concluded |
| 1.8 |  | Consolidate implementation – documentation, correct job titles, clear reporting lines, updated job descriptions | 2 months | End of May 2009 | Unknown | Awaits outcome of previous actions |
| 2.1 | Single Status | Complete research and assessment of areas yet to be harmonised: Professional fees Extent/pay for shift work/premium payments Car allowances/leases Additional duties/Acting up Other allowances – tool, bonus, first aid, E planning, other representative roles etc Stand by/call out Flexi/flexible working Time sheet removal | 2 months | Proposals consulted on by end of August 2008 | n/a | Concluded |
| 2.2 |  | Cost and draft proposals | 1 month | End of July 2008 | n/a | Concluded |
| 2.3 |  | Consult on proposals | 1 month | End of August 2008 | n/a | Concluded |
| 2.4 |  | Draw up final proposals & link to implementation | 1 month | End of August 2008 | Unknown | Reached agreement with both unions on all areas in December but Unison position is now unclear |
| 3.1 | Equal Pay | Assess current picture | 2 weeks | End of July 2008 | n/a | Concluded |
| 3.2 |  | Carry out Equality Impact Assessments on proposed new pay structure(s) | 3 weeks | End of September 2008 | January 2009 | Concluded |
| 3.3 |  | Identify and explore validity of any outstanding Equality concerns | 1 month | By December 2008 | Unknown | Awaits outcome of 1.2 and 1.3 |
| 3.4 |  | Create a draft action plan to address issues – including consultation as appropriate | 1 month | End of December 2008 | Unknown | Awaits outcome of 3.3 |
| 4.1 | Job Evaluation | Complete Phase 1 (existing scored jobs): Complete all appeals Notify staff of outcome Publish scores Pass information to Pay Modeller in a form it can be used (see 1.2) | underway | End of August 2008 | n/a | Concluded |
| 4.2 |  | Phase 2 Job Evaluation: Obtain information to allow outstanding jobs to be scored – new/amended jobs since Autumn 2007 Temp jobs anticipated to have gone but have not Casuals Career grades Arrange panels & type up/distribute the information Support and participate in Steering Panels Obtain any additional information required Support and participate in Appeal Panels Notify and publish scores Complete documentation See also 1.7 above | 5 months | End of March 2009 | End of May 2009 | Well underway with 40+ new and changed posts evaluated to date. Due to the complexity of existing career graded posts the end date has been put back to end of May. |
| 4.3 |  | Complete documentation to enable it to be easily retrieved when required | As in 4.2 | End of March 2009 | End of May 2009 | Underway |
| 4.4 |  | Set up an ongoing (‘mainstreamed’) Job Evaluation arrangement so as to score all new and changed jobs occurring after the end of the PWS project. Agree this with unions and Employment Panel | 1 month | 1 April 2009 | Unknown | We were going to use the arrangements agreed within the new Pay Policy but this is now in doubt. Implementation date was 1 April but now can not be predicted |
| 5 | General – all packages | Document and monitor project and highlight any issues and potential slippage Draft and produce reports, briefing notes, consultation documents, PWS Board reports, minutes CJC at intervals Inform Portfolio Holder throughout CROS at intervals Communication e.g. surgeries, road shows, presentation, newsletters etc | underway | End of March 2009 | Unknown | A project update is presented each month to Management Briefing. There have been regular PWS newsletters and also updates in Staff News. Publication of the final pay structure in mid January was accompanied by extensive communication and support arrangements. Date for a conclusion of project is now uncertain. |