## 2009-10 Prog
2009/10 CAPITAL PROGRAMME | [6 empty] | APPENDIX A
Scheme | Original | Carry | Other | Revised | Proposed | Potential | Revised
| Capital | Forwards | Adjustments | Capital | Carry | Savings | Capital
| Programme | from | To | Programme | Forward | Identified | Programme
| 2009/10 | 2008/09 | Programme | 2009/10 |  |  | 2009/10
| £ | £ | £ | £ | £ | £ | £
Current non-recurring commitments
Customer Contact Centre | 129300 | 20300 |  | 149600 | -49600 | -100000 | 0
Greystone Community Centre | 21000 |  |  | 21000 |  |  | 21000
Chances Park | 40000 |  | 753800 | 793800 |  |  | 793800
Willowholme Depot | 15000 |  |  | 15000 |  | -15000 | 0
Environmental Enhancements | 160000 | 58500 | -10000 | 208500 | -8000 |  | 200500
Family Hostel Replacement | 3490000 | 375600 | -690000 | 3175600 | -3081000 |  | 94600
| 3855300 | 454400 | 53800 | 4363500 | -3138600 | -115000 | 1109900
Recurring commitments
Housing Strategy - Housing Provision |  | 60000 |  | 60000 |  |  | 60000
Housing Strategy - Empty Homes | 100000 |  |  | 100000 | -40000 |  | 60000
Planned Enhancements to Council Property | 300000 | 7600 | 3400 | 311000 | -58700 |  | 252300
Willowholme Industrial Estate | 139000 | 0 |  | 139000 | -135000 |  | 4000
Kingstown Industrial Estate | 85000 | 469000 |  | 554000 |  |  | 554000
Durranhill Industrial Estate |  | 7400 |  | 7400 |  | -3500 | 3900
Play Area Developments | 50000 | 15100 | 106700 | 171800 |  |  | 171800
Vehicles, Plant & Equipment | 2069200 | -125500 | 13900 | 1957600 | -66000 |  | 1891600
ICT Shared Services | 261600 |  |  | 261600 | -55400 |  | 206200
IT Equipment | 39400 | 17000 | -21800 | 34600 |  | -9200 | 25400
CCTV | 70000 |  |  | 70000 | -35000 |  | 35000
| 3114200 | 450600 | 102200 | 3667000 | -390100 | -12700 | 3264200
New non-recurring commitments
Carbon Trust Initiative | 161000 | 2500 |  | 163500 |  |  | 163500
Old Town Hall - Strategic TIC | 150000 |  |  | 150000 | -150000 |  | 0
Trinity Church MUGA |  |  | 90400 | 90400 |  |  | 90400
Sub Regional Employment Sites |  |  | 1796000 | 1796000 | -256000 |  | 1540000
Connect 2 Cycleway |  |  | 60000 | 60000 |  |  | 60000
Roman Gateway |  |  | 60000 | 60000 | -57000 |  | 3000
RBS Shared Service |  |  | 61800 | 61800 |  |  | 61800
| 311000 | 2500 | 2068200 | 2381700 | -463000 | 0 | 1918700
Disabled Facilities Grants
Private Sector Grants | 1249000 | -43000 | 458000 | 1664000 |  | -617000 | 1047000
Housing Strategy - DFG's | 300000 |  |  | 300000 |  |  | 300000
| 1549000 | -43000 | 458000 | 1964000 | 0 | -617000 | 1347000
Continuing Schemes
Gateway - General Expenses |  | 29700 |  | 29700 |  |  | 29700
GIS |  | 14000 |  | 14000 |  |  | 14000
Millennium Gallery General Expenses |  | 60000 | -60000 | 0 |  |  | 0
Ghyll Bank Gypsy and Travellers Site |  | 1473300 |  | 1473300 |  |  | 1473300
Lowry Hill Park |  | 90000 |  | 90000 | -75700 |  | 14300
REAL/CTS New system |  | 53100 |  | 53100 |  |  | 53100
City WiFi |  | 13300 |  | 13300 |  | -3900 | 9400
Raffles MUGA |  | 101300 | -17400 | 83900 |  |  | 83900
Heysham Park Play Area |  | 49700 |  | 49700 |  |  | 49700
Petteril Riverbank Protection Work |  | 34300 |  | 34300 |  |  | 34300
Hammonds CCTV |  | 22200 |  | 22200 |  | -1200 | 21000
Caldew/City Centre Flood Defence |  | 20500 |  | 20500 |  |  | 20500
Historic Quarter |  | 773100 |  | 773100 | -719800 |  | 53300
Kingmoor Nature Reserve |  | 20500 |  | 20500 |  |  | 20500
Renaissance Improvements |  | 36100 | -10000 | 26100 |  |  | 26100
Minor Works Grants |  |  | 20000 | 20000 |  |  | 20000
Eden Bridge Garden Restoration |  |  | 20000 | 20000 |  |  | 20000
Belah Community Centre |  |  | 5100 | 5100 |  |  | 5100
Waste Minimisation |  |  | 33200 | 33200 |  |  | 33200
| 0 | 2791100 | -9100 | 2782000 | -795500 | -5100 | 1981400
Flood
ODPM Private Sector Renewal |  | 25000 |  | 25000 |  |  | 25000
Sheepmount Development |  | 45400 |  | 45400 |  |  | 45400
| 0 | 70400 | 0 | 70400 | 0 | 0 | 70400
Schemes yet to start
Housing Foyer |  | 300000 |  | 300000 |  | -300000 | 0
Document Image Processing |  | 45000 |  | 45000 |  |  | 45000
| 0 | 345000 | 0 | 345000 | 0 | -300000 | 45000
TOTAL CAPITAL PROGRAMME | 8829500 | 4071000 | 2673100 | 15573600 | -4787200 | -1049800 | 9736600

## Community
DECEMBER 2009 - CAPITAL BUDGET MONITORING | [10 empty] | APPENDIX B
COMMUNITY SERVICES
Position as at 31 December 2009
Scheme | Annual | Proposed | Potential | Revised | Budget | Expenditure | Variance | Potential | Potential | Adjusted
| Budget | Carry | Savings | Annual | to date | to date | to date | Carry | Carry | Variance | Details of major variances
| 2009/10 | Forwards | Identified | Budget | 2009/10 | 2009/10 | 2009/10 | Forwards | Forwards
|  |  |  | 2009/10 |  |  |  | to 2010/11 | to 2010/11
| £ | £ | £ | £ | £ | £ | £ | £ | £ | £
Sheepmount Development | 45400 |  |  | 45400 | 23463 | 8870 | -14593 | 0 | 0 | -14593 | Works expected to be completed within current financial year.
Sheepmount Drainage | 0 |  |  | 0 | 0 | 13222 | 13222 | 0 |  | 13222 | Funded from an earmarked reserve. Transfer will be actioned at year end. Contract awarded and works to commence in Spring 2010. Carry forward of balance from earmarked reserve into 2010/11 will be required.
CCTV | 70000 | -35000 |  | 35000 | 0 | 0 | 0 | 0 |  | 0 | Release of budget approved by Executive on 18th January 2010. £35,000 to be spent in February and March. Proposed carry forward of £35,000 required for 2010/11 to give total budget of £70,000 for 2010/11.
Kingstown Industrial Estate | 554000 |  |  | 554000 | 51504 | 49504 | -2000 | 0 | 0 | -2000 | Due to unforeseen circumstances this project has been delayed and will not complete until 2010/11. Carry forward will be required at year end.
Willowholme Industrial Estate | 139000 | -135000 |  | 4000 | 1000 | 0 | -1000 | 0 | 0 | -1000 | Project delayed until 2010/11 when works will be completed by United Utilities and Environment Agency. Carry forward has been requested.
Durranhill Industrial Estate | 7400 |  | -3500 | 3900 | 1850 | 1850 | 0 | 0 | 0 | 0 | Works now substantially complete.
Customer Contact Centre | 149600 | -49600 | -100000 | 0 | 0 | -2264 | -2264 | 0 | 0 | -2264 | Linked to corporate wide review of Customer Services.
Planned Major Repairs | 311000 | -58700 |  | 252300 | 66757 | 72112 | 5355 | 0 | 0 | 5355 | Budget released by Executive 14/04/09 CS21/09. Some delays in projects by a couple of weeks due to bad weather but no significant areas of concern.
Vehicles & Plant | 1957600 | -66000 |  | 1891600 | 1600200 | 1605866 | 5666 | 0 | 0 | 5666 | Replacement plan is on schedule.
Trinity Church - MUGA | 90400 |  |  | 90400 | 1702 | 1150 | -552 | 0 | 0 | -552 | The possibility of a small scale junior MUGA is being considered and is expected to be completed by the end of the financial year.
Talkin Tarn | 0 |  |  | 0 | 0 | 700 | 700 | 0 | 0 | 700 | Completion costs running over the year end.
Lowry Hill Park | 90000 | -75700 |  | 14300 | 14300 | 32220 | 17920 | 0 | 0 | 17920 | Funded by Section 106 monies. Construction postponed until after drainage is installed and weather improves. Drainage work is underway. Equipment has been bought ahead of works due to start next financial year and therefore negative carry forward will be required at year end due to the level of carry forward proposed. Carry forward revise to £40,000.
ODPM Making Space for Water | 25000 |  |  | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | The budget is the Council's matched partner contribution to the Making Space For Water Group due during 2009/10.
Play Area Developments | 171800 |  |  | 171800 | 1277 | 4497 | 3220 | 0 | 0 | 3220 | Budget released by Executive 27/07/09 - CS41/09. Schemes progressing as intended. Contract awarded for Harraby Play Area and work due to start on site in February 2010 to be completed by March 2010. Quotations are being sought for Longtown and Hammonds Pond, and St James Park is out to tender.
Synthetic Football Pitch | 0 |  |  | 0 | 0 | 184 | 184 |  |  |  | Completion costs running over the year end.
Renaissance Improvements | 26100 |  |  | 26100 | 7000 | 7075 | 75 | 0 | 0 | 75 | £11,000 earmarked for Hardwick Circus Murals. Completion expected by financial year end.
Environmental Improvements | 208500 | -8000 |  | 200500 | 75942 | 69549 | -6393 | 0 | 0 | -6393 | Projects progressing as intended and expected to be completed within current financial year.
Waste Minimisation | 33200 |  |  | 33200 | 33200 | 33270 | 70 |  |  |  | Funded by County Council Waste Infrastructure Capital grant.
Greystone Community Centre | 21000 |  |  | 21000 | 21000 | 21000 | 0 | 0 | 0 | 0 | Project funding is being managed in conjunction with Community Association. Project complete.
Chances Park | 793800 |  |  | 793800 | 480302 | 227942 | -252360 | 0 |  | -252360 | Scheme has now started and budget will be expended through to the end of the financial year.Any variances are due to contractor monthly estimations of expenditure and the project remains in budget. Project has been delayed by a couple of weeks due to weather resulting in a couple of weeks delay in receipt of invoices.
Small Scale Community Projects | 0 |  |  | 0 | 0 | 1189 | 1189 | 0 | 0 | 1189 | Project costs running over the year end.
Willowholme Depot | 15000 |  | -15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project on hold and budget returned to reserves pending further reports to the Executive.
Belah Community Centre | 5100 |  |  | 5100 | 5100 | 5052 | -48 | 0 | 0 | -48 | Project complete.
Castle Street Public Realm | 773100 | -719800 |  | 53300 | 46300 | 32551 | -13749 | 0 | 0 | -13749 | Full project has now been approved by Cumbria County Council and is expected to be completed by end of 2010. Carry forward into 2010/11 approved.
Raffles MUGA | 83900 |  |  | 83900 | 83900 | 83414 | -486 | 0 | 0 | -486 | Practical completion achieved. Final account to be agreed.
Petteril Riverbank Protection Work | 34300 |  |  | 34300 | 34300 | 25292 | -9008 | 0 | 0 | -9008 | Project completed on time. Final account to be agreed for phase 2.
Hammonds CCTV | 22200 |  | -1200 | 21000 | 16933 | 16933 | 0 | 0 | 0 | 0 | Installation complete. Some remaining software links to complete.
Caldew/City Centre Flood Defence | 20500 |  |  | 20500 | 8200 | 1492 | -6708 | 0 | 0 | -6708 | Project delayed by some minor design changes.
Kingmoor Nature Reserve | 20500 |  |  | 20500 | 17115 | 17115 | 0 | 0 | 0 | 0 | Installation of signage and boardwarks on-going.
Connect 2 Cycleway | 60000 |  |  | 60000 | 55000 | 34548 | -20452 | 0 | 0 | -20452 | Lighting improvements and bridge deck surfacing work to be completed in February. Possibility project might slip into 2010/11.
Heysham Park Play Areas | 49700 |  |  | 49700 | 49700 | 47883 | -1817 | 0 | 0 | -1817 | Project completed.
Energy Efficiency - Carbon Trust Initiative | 163500 |  |  | 163500 | 91955 | 86704 | -5251 | 0 |  |  | Budget released by Executive 14/04/09 - CS23/09. Budget is now fully committed.
Eden Bridge Garden Restoration | 20000 |  |  | 20000 | 10869 | 10895 | 26 | 0 | 0 | 26 | £20,000 additional contributions received.
Roman Gateway | 60000 | -57000 |  | 3000 | 3000 | 0 | -3000 | 0 | 0 | -3000 | Report presented to Executive on 18th January provided an update on scheme.
TOTAL | 6021600 | -1204800 | -119700 | 4697100 | 2801869 | 2509815 | -292054 | 0 | 0 | -287057

## Corporate
DECEMBER 2009 - CAPITAL BUDGET MONITORING | [10 empty] | APPENDIX C
CORPORATE SERVICES
Position as at 31 December 2009
Scheme | Revised | Proposed | Potential | Revised | Budget | Expenditure | Variance | Potential | Potential | Adjusted
| Annual | Carry | Savings | Annual | to date | to date | to date | Carry | Carry | Variance | Details of major variances
| Budget | Forwards | Identified | Budget | 2009/10 | 2009/10 | 2009/10 | Forwards | Forwards
| 2009/10 |  |  | 2009/10 |  |  |  | to 2010/11 | to 2010/11
| £ | £ | £ | £ | £ | £ | £ | £ | £ | £
IT Equipment | 34600 |  | -9200 | 25400 | 25400 | 25279 | -121 | 0 | 0 | -121 | A number of major purchases have had to be brought forward due to faults with existing hardware and budget has been reprofiled to reflect this. Savings of £9,200 identified.
ICT Shared Service | 261600 | -55400 |  | 206200 | 91000 | 93165 | 2165 | 0 | 0 | 2165 | Will be spent as part of the shared services arrangement with Allerdale Borough Council. Expenditure to date relates to Enterprise Licenses.
RBS Shared Service | 61800 |  |  | 61800 | 0 | 0 | 0 | 0 | 0 | 0 | Project in consultation stage.
Document Image Processing | 45000 |  |  | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | Project on hold pending creditor/debtor efficiency review.
City Wi Fi | 13300 |  | -3900 | 9400 | 2372 | 2372 | 0 | 0 | 0 | 0 | Budget will be used to improve WiFi coverage in Civic Centre which has been delayed due to IT shared service project.
REAL Asset Management System | 53100 |  |  | 53100 | 37546 | 38796 | 1250 | 0 | 0 | 1250 | Software has been implemented and tested.
TOTAL | 469400 | -55400 | -13100 | 400900 | 156318 | 159612 | 3294 | 0 | 0 | 3294

## Development Services
DECEMBER 2009 - CAPITAL BUDGET MONITORING | [10 empty] | APPENDIX D
DEVELOPMENT SERVICES
Position as at 31 December 2009
Scheme | Revised | Proposed | Potential | Revised | Budget | Expenditure | Variance | Potential | Potential | Adjusted
| Annual | Carry | Savings | Annual | to date | to date | to date | Carry | Carry | Variance | Details of major variances
| Budget | Forwards | Identified | Budget | 2009/10 | 2009/10 | 2009/10 | Forwards | Forwards
| 2009/10 |  |  | 2009/10 |  |  |  | to 2010/11 | to 2010/11
| £ | £ | £ | £ | £ | £ | £ | £ | £ | £
GIS | 14000 |  |  | 14000 | 129 | 129 | 0 | 0 | 0 | 0
Private Sector Grants - Minor Works | 20000 |  |  | 20000 | 0 | 1737 | 1737 | 0 | 0 | 1737
Disabled Facilities Grants | [10 empty] | These grants are mandatory. There is a time period between grant approval, works done and payment. Vacancies in the Adult Care Team for Occupational Therapists (OT) have been filled but there is now a 29 week waiting time for an OT assessment. An assessment is needed before a grant can be processed. Approved grants will appear as an underspend but is committed funding.If the funding is to be removed from the DFG 'pot', it will need to be ring-fenced in reserves for the funding of DFGs as this money is already committed/approved . 2009/10 is the last year of funding specifically for tenants of Riverside. Discussions with Riverside have been held regarding increasing their contribution and their board have looked at funding from next financial year. Current commitment levels are £470K for general grants and £190K for Riverside tenants.
- Private | 1664000 |  | -617000 | 1047000 | 696824 | 438654 | -258170 | 0 | 0 | -258170
- Housing Strategy | 300000 |  |  | 300000 | 252000 | 330386 | 78386 | 0 | 0 | 78386
| 1964000 | 0 | -617000 | 1347000 | 948824 | 769040 | -179784 | 0 | 0 | -179784
Housing Strategy | 160000 | -40000 |  | 120000 | 80000 | 76609 | -3391 | 0 | 0 | -3391 | This covers two funding streams. Empty Properties has £100,000 budget of which £15,500 has been spent and the remaining budget will fund outstanding commitment to grants approved and those being processed. Landlords have up to one year to draw down the grant approved. Approved grant will show as an underspend but is committed funding.Anticipate carry forward at year end of committed funding of approximately £40,000. Housing Provision budget of £60,000 is fully spent.
Housing Foyer | 300000 |  | -300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Report required to Executive to release budget. YMCA capital bid not awarded funding. Local YMCA merging with Flyde YMCA which has a turnover of £5 million. They have proposed a dispersed Foyer model with support delivered from the Resource Centre. Scheme may not progress in this financial year.
Resource Centre | 3175600 | -3081000 |  | 94600 | 52570 | 28973 | -23597 | 0 | 0 | -23597 | Resource Centre Planning appliation approved by Development Control Committee on 2/10/09. Design team for final part of project selected and construction to be put out to tender. Substantial carry forward required into 2010/11.
ODPM Private Sector Renewal | 0 |  |  | 0 | 0 | -2589 | -2589 | 0 | 0 | -2589 | Projects complete.
Ghyll Bank Gypsy & Traveller Site | 1473300 |  |  | 1473300 | 831218 | 736620 | -94598 | 0 |  | -94598 | Construction contract awarded and works on site started in September. Due to be completed late March. Initial set up and management in place with 5 year management contract to be tendered in spring 2010.
Old Town Hall - Strategic TIC | 150000 | -150000 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | Report required to Executive to release budget.
Sub Regional Employment Sites | 1796000 | -256000 |  | 1540000 | 1232431 | 1140209 | -92222 | 0 |  | -92222 | There has been a delay in awarding the contract for the demolition works which is the majority of teh remaining expenditure in 2009/10. The contract has now been awarded and work is progressing. Negotiations are being held with the funding body North West Development Agency with regards to reprofiling the allocated budget.
TOTAL | 9052900 | -3527000 | -917000 | 4608900 | 3145172 | 2750728 | -394444 | 0 | 0 | -574228

## LDS
SEPTEMBER 2009 - CAPITAL BUDGET MONITORING | [10 empty] | APPENDIX E
LEGAL & DEMOCRATIC SERVICES
Position as at 30 September 2009
Scheme | Updated | Proposed | Potential | Revised | Budget | Expenditure | Variance | Potential | Potential | Adjusted
| Annual | Carry | Savings | Annual | to date | to date | to date | Carry | Carry | Variance | Details of major variances
| Budget | Forwards | Identified | Budget | 2009/10 | 2009/10 | 2009/10 | Forwards | Forwards
| 2009/10 |  |  | 2009/10 |  |  |  | to 2010/11 | to 2010/11
| £ | £ | £ | £ | £ | £ | £ | £ | £ | £
Gateway - General Expenses | 29700 |  |  | 29700 | 0 | 0 | 0 | 0 | 0 | 0 | This sum is in respect of a retention we are currently holding back (on the advice of the County archaeologist) from the final stage payment due to Oxford Archaeology under the contract we have with them for completing the Millenium Scheme archaeological texts.
TOTAL | 29700 | 0 | 0 | 29700 | 0 | 0 | 0 | 0 | 0 | 0

## PPP (hidden)
JUNE 2009 - CAPITAL BUDGET MONITORING | [7 empty] | APPENDIX F
PEOPLE, POLICY & PERFORMANCE SERVICES
Position as at 30 June 2009
Scheme | Revised | Budget | Expenditure | Variance | Potential | Potential | Adjusted
| Annual | to date | to date | to date | Carry | Carry | Variance | Details of major variances
| Budget | 2009/10 | 2009/10 | 2009/10 | Forwards | Forwards
| 2009/10 |  |  |  | to 2010/11 | to 2010/11
| £ | £ | £ | £ | £ | £ | £
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Summary (hidden)
NOT FOR PUBLICATION
2009/10 CAPITAL SUMMARY - DECEMBER 2009
| Annual | Proposed | Potential | Revised | Budget | Expenditure | Variance | Potential | Potential | Adjusted
| Budget | Carry | Savings | Annual | to date | to date | to date | Carry | Carry | Variance
| 2009/10 | Forwards | Identified | Budget | 2009/10 | 2009/10 | 2009/10 | Forwards | Forwards
|  |  |  | 2009/10 |  |  |  | to 2010/11 | to 2011/12
| £ | £ | £ | £ | £ | £ | £ | £ | £ | £
Community Services | 6021600 | -1204800 | -119700 | 4697100 | 2801869 | 2509815 | -292054 | 0 | 0 | -287057
Corporate Services | 469400 | -55400 | -13100 | 400900 | 156318 | 159612 | 3294 | 0 | 0 | 3294
Development Services | 9052900 | -3527000 | -917000 | 4608900 | 3145172 | 2750728 | -394444 | 0 | 0 | -574228
Legal & Democratic Services | 29700 | 0 | 0 | 29700 | 0 | 0 | 0 | 0 | 0 | 0
PPP Services | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 15573600 | -4787200 | -1049800 | 9736600 | 6103359 | 5420155 | -683204 | 0 | 0 | -857991
0
Budget monitoring s/sheet | 15573600 | -4787200 | -1049800 | 9736600 | 6103359 | 5420156 | -683203 | 0 | 0 | -683203
| 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 174788
[5 empty] | 0 | 0