OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 2 FEBRUARY 2006 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.06/06 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 December 2005 to 31 March 2006 and 1 January to 30 April 2006.

Recommendations:	To note the modifications, deferrals and departures from the previous Forward Plans.

| Contact Officer: | Elspeth MacKay | Ext: | 7034 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the periods 1 December 2005 to 31 March 2006 and 1 January to 30 April 2006 are outlined in Appendix A of this report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the previous Forward Plans be noted.

Contact Officer:		Elspeth MacKay						Ext: 7034

1st December 2005 to 31 March 2006

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
|  | Cumbria Vision Draft Strategic Plan Corporate Resources O&S Committee | The item was not included in the Forward Plan. It was considered by the Executive on 19 December under General Exception rules | Corporate Management Team |
|  | Reason: A decision must be taken by December 2005 and it is impracticable to defer a decision. |
|  | Mid-term Review of Carlisle City Vision and proposals for the development of a Carlisle Local Strategic Partnership Corporate Resources Overview and Scrutiny Committee | The item was not included in the Forward Plan. It was considered by the Executive on 19 December under General Exception rules | Corporate Management Team |
|  | Reason: A decision must be taken by December 2005 and it is impracticable to defer a decision. |
| KD.018/05 | Draft Regional Spatial Strategy Infrastructure O&S Committee | Was scheduled to go to Executive in February or March 2006 but this has been changed to March or April 2006 | Head of Planning Services |
|  | Reason: The Draft Strategy was published in October/November 2005 and the consultation timescale was set |
| KD.040/05 | Carlisle District Local Plan Infrastructure O&S Committee | Date for the matter to be reported to Infrastructure O&S Committee was scheduled as 26 January 2006, but this has been changed to “on a date to be determined” | Local Plans and Conservation Manager |
|  | Reason: The matter was originally scheduled to go to Executive in November and January and at this time it was scheduled to go to O&S in January 2006. It was then re-scheduled to go to Executive in March and April, but the O&S date was not amended at that time. It will be scheduled to go to O&S at an appropriate time |

1st January to 30 April 2006

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
|  | Carlisle Renaissance All O&S Committees | The item was not included in the Forward Plan. It was considered by the Executive on 23 January under General Exception rules | Corporate Management Team |
|  | Reason: Considered under General Exception rules because of the need to make a decision within certain timescales |
| KD.002/06 | Carlisle Crematorium Cremator Replacement 06-07/07-08 Community O&S Committee | Deferred from 23 January 2006 to Executive on 20 February 2006 | Director of Community Services |
|  | Reason: To allow time for further information to be included in the report |
| KD.040/05 | Carlisle District Local Plan Infrastructure O&S Committee | Deferred from Executive on 14 November to and 20 February 2006, then deferred further to some time in April or May 2006 and then deferred further to June and July 2006 | Corporate Management Team |
|  | Reason: The Plan is delayed for a number of reasons relating to additional work to be undertaken. These are: Strategic Environmental Assessment (SEA) – The Planning Inspectorate have informed the Council that it will not have a report on an Inquiry available in order that the Council can adopt its Local Plan in time to meet the July deadline for European Regulations on the requirement for a SEA. Before July 2006 we did not need one, afterwards we do. Therefore additional assessment is being undertaken. This work is scheduled for completion by the end of February 2006. A consequence of this work is that we must undertake a further consultation on the Plan. Retail Capacity Study – since the last study, most capacity has been accounted for and the research base is being questioned, therefore an update is required. This will report in March Carlisle Renaissance – In order to incorporate this into the development plan system, the prospectus needs developing into something more robust. The Development Framework and Movement Study will achieve this. Once this work is done the linkages between Carlisle Renaissance and the Local Plan can be more clearly aligned. Options appraisal at the earliest is April. This results in the Plan not being revised until April with reports to Committee in June/July 2006 |