OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 26 April 2007 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.38/07 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 February 2007 to 31 May 2007, 1 March 2007 to 30 June 2007, and 1 April 2007 to 31 July 2007.

Recommendations:	To note the modifications, deferrals and departures from the previous Forward Plans.

| Contact Officer: | Rachel Rooney | Ext: | 7039 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

2.1	Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the periods 1 February 2007 to 31 May 2007, 1 March 2007 to 30 June 2007, and 1 April 2007 to 31 July 2007 are outlined in Appendix A of this report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the previous Forward Plans be noted.

Contact Officer:		Rachel Rooney						Ext: 7039

1st February 2007 to 31 May 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
|  | Communities for Health | The item was not included in the Forward Plan. It was considered by the Executive on 19 February 2007 under General Exception rules. | Deputy Chief Executive |
|  | Reason: |
| KD.007/07 | Responding to the Local Government and Public Involvement in Health Bill (on behalf of Cumbria Districts) | The item was scheduled in the Forward Plan to go to Executive on 19 March 2007 but has been removed from the Forward Plan. | Head of Revenues and Benefits |
|  | Reason: The matter was considered by Executive under General Exception rules on 22 January 2007 |
| KD.068/06 | Carlisle Renaissance – Development Framework and Movement Strategy | The item was scheduled in the Forward Plan to go to Infrastructure Overview and Scrutiny Committee on 19 February 2007 but it has been deferred to 19 April 2007. The meeting on 19 February had been changed to a private informal workshop. | Director of Carlisle Renaissance |
|  | Reason: |
| KD.071/06 | Housing Supply | The item was originally scheduled to go to Community Overview and Scrutiny on 15 February 2007. It has been deferred and will now be reported on 29 March 2007. |  |
|  | Community O&S |  |  |
|  | Reason: To allow consideration by the Executive then refer to Community Overview and Scrutiny Committee |
| KD.064/06 | Tullie House Development Plan | The item was scheduled in the Forward Plan for March 2007. It will not be going to Executive in March and has been removed from the Forward Plan until definite dates are received. | Head of Culture and Community Services |
|  | Community O&S |  |  |
|  | Reason: Awaiting the outcome of the decision from the Heritage Lottery Fund which is expected in the spring. |
| KD.061/06 | Cumbria Wind Energy Supplementary Planning Document and Sustainability Appraisal | The item was scheduled to go to Executive on 19 March 2007. It has been deferred and will now be reported to Executive on 11 June 2007. | Local Plans and Conservation Manager |
|  | Infrastructure O&S Reason: Awaiting consultation responses from external bodies. |
| KD.062/06 | Dalston Design Statement Supplementary Planning Document Infrastructure O&S | The item was scheduled to go to Executive on 19 March 2007. It has been deferred and will now be reported to Executive on 11 June 2007. | Local Plans and Conservation Manager |
|  | Reason: Awaiting consultation responses from external bodies |
|  | Budget 2007/08 – Consideration of Proposed Amendments agreed by the City Council on 6 February 2007 | The item was not included in the Forward Plan. It was considered by the Executive on 15 February 2007 under General Exception rules. |  |
|  | Reason: |

1st March 2007 to 30 June 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.014/07 | Section 106 Agreements in relation to Public Open Space and Play Areas | The item was originally scheduled to go to Infrastructure Overview and Scrutiny on 8 March 2007. It has been deferred and will now be reported on 19 April 2007. | Director of Community Services |
|  | Infrastructure O&S |  |  |
|  | Reason: To allow consideration by the Executive then refer to Infrastructure Overview and Scrutiny Committee |
| KD.13/07 | Rape Crisis Grant | The item was scheduled to go to Executive on 19 March 2007 and Community O&S on 29 March 2007.. |  |
|  | Community O&S |  |  |
|  | Reason: This has been overtaken by the Council budget decision and no longer requires an Executive Decision. |
|  | Transfer of City Council Land for the CNDR | The item was not included in the Forward Plan. It was considered by the Executive on 19 March 2007 under General Exception rules. |  |
|  | Corporate Resources O&S |  |  |
|  | Reason: Decision is being made by Government at the end of March and then the matter will go to Executive after this. |
|  | Extra Care Housing Scheme | The item was not included in the Forward Plan. It was considered by the Executive on 19 March 2007 under General Exception rules. |  |
|  | Reason: The Portfolio Holder had requested that this be reported to Executive on 19 March 2007 as there are a number of tight timescales surrounding the project. |  |

1st April 2007 to 31 July 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.019/07 | Customer Contact Centre | The item was scheduled to go to Executive on 23 April 2007. It has been deferred and will now be reported to Executive on 11 June 2007. | Director of Community Services |
|  | Corporate Resources |  |  |
|  | Reason: The report had been delayed due to the need for further investigation |
| KD.023/07 | Multi-Use Games Area Proposal – Play Raffles | The item was scheduled to go to Executive on 23 April 2007. It has been deferred and will now be reported to Executive on 2 July 2007. |  |
|  | Community |  |  |
|  | Reason: Deferred pending further work and consultation |
| KD.061/06 | Cumbria Wind Energy Supplementary Planning Document and Sustainability Appraisal | The item was scheduled to go to Executive on 11 June 2007. It will not be going to Executive in June and has been removed from the Forward Plan until definite dates are received | Local Plans and Conservation Manager |
|  | Infrastructure O&S Reason: Awaiting dates from external bodies. |
| KD.062/06 | Dalston Design Statement Supplementary Planning Document Infrastructure O&S | The item was scheduled to go to Executive on 11June 2007. It will not be going to Executive in June and has been removed from the Forward Plan until definite dates are received. | Local Plans and Conservation Manager |
|  | Reason: Awaiting dates external bodies |