CARLISLE CITY COUNCIL

SUPPORTING COMMUNTIES BEST VALUE REVIEW

# IMPROVEMENT PLAN – FIRST DRAFT 29/12/03

| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| 1. 1. The Council’s partnership role within its Community Leadership role (as defined by the Local Government Act 2000) needs to be considerably strengthened and articulated through the Corporate Plan and City Vision. | Consultation with CMT, EMG and JMT to ensure this key issue is acknowledged and progressed into the Prioritisation process of the Corporate Plan’s Themes, Objectives and Actions. Consultation with City Vision partners to ensure the Councils’ ‘Community Leadership role’ is progressed through the revised City Vision document. Consultation with Carlisle and Eden Local Strategic Partnership to ensure the Community Strategy reflects the Council’s role. | January – March 2004 – Prioritisation process of Corporate Plan. March – September 2004 – Review of City Vision January – June 2004 – Community Strategy | Strategic & Performance Services; EMG; Executive; Executive Directors | Staff time | Consultation relating to Prioritisation of Corporate Plan does not manage to highlight the ‘community leadership’ issues because of training and meeting deadlines. Regionalisation Agenda/Unitary Authority debates overtake the previous City Vision and Community Strategy. | Infrastructure Overview & Scrutiny Committee CMT EMG - To be undertaken near/following milestone dates. |
| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| 2. The Council should be aware of communities’ and other agencies’ sensitivities around partnership issues, and ensure that the Council does not dominate Partnerships, but rather acts as a facilitator, enabler and co-ordinator. 3. 3. There needs to be explicit statements made in corporate documents which champion the Council’s role in Supporting Communities, especially those in the most deprived rural and urban areas. | Will be part of the proposed brief for external work to be undertaken (please see Appendix 3) All other documents e.g. Business Plans, will identify this key issue | March – September 2004 See Key Issue (1) | Supporting Communities Best Value Review Team See Key Issue (1) | This action will be part of the overall costs of ‘Partnership’ work – approximately £9000 Staff time See Key Issue (1) | Inability to identify appropriate consultant/s Lack of commitment/ time of Council staff and development in this area of work Consultancy work does not meet deadline See Key Issue (1) | Supporting Communities Best Value Review Team Infrastructure Overview & Scrutiny Committee. See Key Issue (1) |
| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| 4. There needs to be a Regeneration Strategy and/or Framework in place which makes the strategic links between all Council policies, to ensure cohesion, and also the links with how the Council’s partnership role links to tackling anti-social behaviour; improves community cohesion; supports social enterprise and addresses financial exclusion. 5.There needs to be a robust Risk Assessment in place, which not only accords with the Councils’ own procedures, but also enables the Council to: | To be incorporated within the ‘Regeneration Framework’ being progressed by Economic & Community Development Business Unit. All other Policies to be championed by relevant Executive Directors/Business Unit Heads/Portfolio Holders/Elected Member representatives on key groups e.g. Community Safety Leadership Group; Housing Strategy Group Strategic & Performance Services to advise Business Units on carrying out Risk Assessments of all Partnerships, in relation to all key issues identified in this section. | Year One – January – December 2004 First Review to take place May 2004 | Economic & Community Development Business Unit Head Executive Directors Relevant Business Unit Heads Portfolio Holders/ Elected Member representatives Strategic & Performance Services; Financial Services; Executive Directors | Staff time The cost of permanent contracts attached to fixed term projects Potential additional funding to cover future staffing costs (once project ends) Staff time related to these actions | Lack of cohesion because of complex nature of action required Inability to recruit temporary staff on fixed term contracts. Financial implications for City Council to pick up staff and other revenue costs once project ends | CMT;EMG; JMT Executive Directors Infrastructure Overview & Scrutiny Committee |
| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| Show how the permanent posts established for relatively short-term projects will be supported once the funding ceases. Recognise that the future of delivery of regeneration and supporting communities is likely to be through Specialist Projects (e.g. Sure Start; NWDA) and also increasingly through mainstreaming local public service provision. This mainstreaming has to be forecast at an early stage of the project and in the core posts funded by the Council (5 in total) for the Sure Start programme, as soon as possible. The | Business Units undertaking Partnership work which includes recruitment of staff and discussing financial implications with Financial Services at an early stage – possible extension of the remit of VFM Review of Partnerships? Regular reports to Executive on the changing pattern of projects which rely on external funding sources; temporary staffing and exit strategies. Discussion with the Sure Start ‘Mainstreaming’ Group to look at models of good practice in terms of mainstreaming/succession strategies. Mapping exercise of number and range of externally funded posts across the Council |  |  |  |  |  |

| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| Rev Review Team has recognised that effective succession (rather than exit) Strategies is growing ever more pertinent for the City Council. 6. The capacity of Council staff in delivering ‘extra’ services as a result of the Council’s partnership role has to be considered at an early stage and needs to be risk managed and costed accordingly. | Agreement by CMT and EMG that wherever possible top-slicing of external funding allocations is undertaken to cover additional services. Effective time-recording undertaken by all staff involved in Partnership work | First review to take place May 2003. | Executive Directors and Business Unit Heads | Staffing costs | Staffing capacity overload Impact on service delivery Commitment to the ‘extra’ services not fulfilled | CMT Infrastructure Overview & Scrutiny Committee |
| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| 7. The role of the Council’s partnership role has to be considered in terms of all the other partnership work it is engaged in, to test both the impact and the capacity. 8.There needs to be an explicit Policy on the Councils’ Partnership role which takes account of the VFM Internal Review of Partnerships. Evidence gathered in this Best Value Review will inform and influence the Policy. | Mapping of Council’s current commitment to Partnership work. CMT, EMG and Executive (when appropriate) to agree all future partnership work This key issue will be part of the proposed brief for external work to be undertaken (see Appendix 3) | On-going March – September 2004 | CMT EMG Supporting Communities Best Value Review Team | Staff time This action will be part of the overall costs of the partnership work – approximately £9000. Staff time | Decisions taken outside ‘Lead Responsibility’ with potential to overload capacity of staff Possible risk-averse to partnership opportunities Results of mapping exercise not kept up to date, therefore unclear picture of current partnership undertakings. Inability to identify appropriate Consultant | CMT EMG Supporting Communities Best Value Review Team Infrastructure Overview & Scrutiny Committee |
| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| 9.There needs to be a much stronger awareness of the cross-cutting nature of Partnerships across the Council, both in terms of current partnership work and the potential for future work. This of course includes individual Business Units’ capacity to deliver. All Business Unit Heads are committed to partnership working, but not all are aware of how or if they can contribute. 10.Consideration needs to be given to top-slicing external budgets wherever possible to enable the Council to properly fulfil its role as Partner. | Initial awareness raising of Councils’ partnership work through CMT and proposed consultancy Strategic & Performance Services to maintain an up to date list of Partnerships which involve the City Council as lead body/and or representative partner CMT updated through Performance Monitoring and information sharing by Business Unit Heads. This key issue is now subsumed within Actions for Key Issues (6) and (7) | Ongoing | Business Unit Heads Strategic & Performance Services | Staff time | Business Units unaware of the context and impact of Partnership work across the Council Capacity overload Potential risk-aversion to cross-cutting work | Strategic & Performance Services |

| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| 11.A robust set of performance indicators needs to be developed and established, which measure the effectiveness of the Council’s partnership role. 12.Other Local Authorities and organisations need to be consulted and involved at appropriate times, to support the Council’s role and test out ideas of adding value to the Councils’ partnership role. The Council needs to acknowledge that it has much to learn from other organisations and they in turn can learn much from the Council. | Strategic & Performance Services to provide support and advice to ensure that the identified Performance Indicators accurately reflect the work being carried out. Will also be part of the proposed brief for external work to be undertaken (See Appendix 3) Supporting the Research Officer in Strategic & Performance Services to help identify good practice in other Local Authorities /Organisation. Will also be part of the proposed brief for external work to be undertaken (See Appendix 3) | March-September 2004 Ongoing | Strategic & Performance Services. Supporting Communities Best Value Review Team Supporting Communities Best Value Review Team. Strategic & Performance Services | This action will be part of the overall costs of ‘Partnership’ work – approximately £9000 Staff time This action will be part of the overall costs of ‘Partnership’ work – approximately £9000 Staff time | Inability to identify appropriate Consultant Inability to identify comparator Local Authorities/ Organisations | Supporting Communities Best Value Review Team Strategic & Performance Services Infrastructure Overview & Scrutiny Committee Supporting Communities Best Value Review Team |

| KEY ISSUE | ACTION | MILESTONE DATES | LEAD RESPONSIBILITY | RESOURCE IMPLICATIONS | RISK FACTORS | PERFORMANCE MONITORING ARRANGEMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| 13. 13. The Consultation process showed the Review Team that there are concerns in local communities about how the Council currently consults, which focus upon the issues of ‘over consultation’ and the need to feedback consultation outcomes promptly and appropriately. | Feedback to all consultees involved in this Best Value Review. Feedback to the Democratic Engagement Best Value Review Team and for this key issue to inform the Corporate Consultation Policy Awareness raising across Business Units | Ongoing with feedback to Supporting Communities Best Value Review Consultees by mid February 2004, following report to Infrastructure Overview & Scrutiny Committee on 22nd January 2004. | Supporting Communities Best Value Review Team Communications Team | Staff time | Inconsistencies in implementing Corporate Consultation Policy Inability to consult with most deprived groups of our local communities ‘Over consultation’ of some key groups e.g. young people | Supporting Communities Best Value Review Team. Communications Team |