OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 1 February 2007 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS.11/07 |

Summary:	To inform Members of changes to the Executive’s Forward Plans for 1 October 2006 to 31 January 2007, 1 November 2006 to 28 February 2007, 1 December 2006 to 31 March 2007 and 1 January 2007 to 30 April 2007.

Recommendations:	To note the modifications, deferrals and departures from the previous Forward Plans.

| Contact Officer: | Rachel Rooney | Ext: | 7039 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

2.1	Details of departures from, modifications to and deferrals in respect of the Forward Plans covering the periods 1 October 2006 to 31 January 2007, 1 November 2006 to 28 February 2007, 1 December 2006 to 31 March 2007 and 1 January 2007 to 30 April 2007.

are outlined in Appendix A of this report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the previous Forward Plans be noted.

Contact Officer:		Rachel Rooney						Ext: 7039

1st October 2006 to 31 January 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.051/06 | Revised Parish Charter Community O&S Committee | The item was originally scheduled to go to Executive on 23 October and Community on 18 October 2006. It will now be reported to Executive on 18 December 2006 and Community O&S on 23 November 2006 | Director of Development Services |
|  | Reason: The Parish Councils Association has requested further time for discussion and consultation on the Charter. |
| KD.059/06 | Office of the Deputy Prime Minister Grant – Investment Programme Community O&S Committee | The item was originally scheduled to go to Executive on 23 October. It has been deferred and will now be reported to Executive on 20 November 2006 | Portfolio holder and Deputy Chief Executive |
|  | Reason: To allow further time to develop a programme of potential schemes and to enable the Community Overview and Scrutiny Committee the opportunity to feed their views into the process. |
| KD.032.06 | Equality and Diversity Policy Community O&S Committee | The subject title was expanded to read “Equality and Diversity Policy - including Corporate Equality Action Plan and the Disability Equality Scheme” | Head of Policy and Performance Services |
|  | Reason: To clarify aspects included in the Policy |
|  | Concessionary Fares Infrastructure O&S Committee | The item was not included in the Forward Plan. It will be considered by the Executive on 25 September 2006 under General Exception rules | Director of Corporate Resources |
|  | Reason: To consider the outcome of negotiations with Stagecoach |

1st November 2006 to 28 February 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.032/06 | Equality and Diversity Policy Community O&S Committee | The item was originally scheduled to go to Executive on 18 December 2006. It has been deferred and will now be reported to Executive on 22 January 2007. | Head of Policy and Performance Services |
|  | Reason: The date of the Executive was deferred to allow for the Policy to go to Community Overview and Scrutiny Committee first. |
| KD.064/06 | Tullie House Development Plan Community O&S Committee | The item was originally scheduled to go to Executive on 20 November 2006. It has been deferred and will now be reported to Executive in February or March 2007. | Senior Management Team |
|  | Reason: The bid has not yet been submitted to the Heritage Lottery Fund. The outcome of the bid will be reported to the Executive in due course. |
|  | Nottingham Declaration | The item was not included in the Forward Plan. It was considered by the Executive on 20 November 2006 under General Exception rules. |  |
|  | Reason: The Director of Community Services contacted about this item after the publication of the Forward Plan. |
|  | Raffles Vision – Update on Options for Vacant Properties | The item was not included in the Forward Plan. It was considered by the Executive on 20 November 2006 under General Exception rules. |  |
|  | Reason: The timescale regarding the building works to the property require a decision regarding the transfer of the assets in order for the works to be completed within this financial year. |

1st December 2006 to 31 March 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
|  | Willowholme/Caldewgate/St Nicholas Development Brief | The item was not included in the Forward Plan. It was considered by the Executive on 18 December 2006 under General Exception rules. |  |
|  | Reason: The matter arose as a motion from the Council with a request that it be addressed as a matter of urgency.. |
|  | Response to the White Paper on “Strong and Prosperous Communities” | The item was not included in the Forward Plan. It was considered by the Executive on 18 December 2006 under General Exception rules. |  |
|  | Reason: The timescales for a response from the Council meant that there was not sufficient time to include it in the Forward Plan. |
| KD.061/06 | Cumbria Wind Energy Supplementary Planning Document and Sustainability Appraisal | The item was originally scheduled to go to Executive on 19 February 2007. It has been deferred and will now be reported to Executive on 19 March 2007. | Local Plans and Conservation Manager |
|  | Infrastructure O&S Reason: A joint officer meeting had been arranged for 16 January 2007 so all districts put the same information forward on feedback from the consultation. This means the deadline for Overview and Scrutiny on 27 January 2007 and Executive on 19 February 2007 will be missed. |

| KD.062/06 | Dalston Design Statement Supplementary Planning Document Infrastructure O&S | The item was originally scheduled to go to Executive on 19 February 2007. It has been deferred and will now be reported to Executive on 19 March 2007. | Local Plans and Conservation Manager |
| --- | --- | --- | --- |
|  | Reason: Delayed as the Government Office had a few concerns. The Parish Council have arranged a meeting for 19 January 2007. A part time officer is attending the meeting and won’t be in the office until after the Overview and Scrutiny Deadline. |
| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| KD.073/06 | Talkin Tarn Business Plan | The item was originally scheduled to go to Executive on 18 December only. It will now also go to Executive on 22 January 2007 for final approval. | Director of Community Services |
|  | Community O&S |
|  | Reason: To programme in consideration by Community Overview and Scrutiny Committee before final decision by Executive. |

1st January 2007 to 30 April 2007

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
|  | Response to the White Paper on “Strong and Prosperous Communities” | The item was not included in the Forward Plan. It was considered by the Executive on 4 January 2007 under General Exception rules. |  |
|  | Reason: The timescales for a response from the Council meant that there was not sufficient time to include it in the Forward Plan. |
|  | Caldew/City Centre Flood Defence Project | The item was not included in the Forward Plan. It was considered by the Executive on 22 January 2007 under General Exception rules. | Director of Community Services |
|  | Infrastructure O&S |
|  | Reason: The report follows a meeting with the Environment Agency and the receipt of the details about the project was received after the publication of the January to April Forward Plan. |
|  | Promotion and Enforcement of No Smoking Legislation | The item was not included in the Forward Plan. It was considered by the Executive on 22 January 2007 under General Exception rules. | Director of Community Services |
|  | Reason: On 22 December 2006 the Council was notified of a Government funding allocation for the promotion and enforcement of the no smoking legislation, this was after the publication of the January to April Forward Plan. |
|  | Carlisle Renaissance – Development Framework & Movement Strategy | The item was originally scheduled to go to Executive on 19 February 2007. It has been deferred and will now be reported to Executive on 19 March 2007. | Director of Carlisle Renaissance |
|  | Infrastructure O&S |
|  | Reason: The final consultants report was expected by 15 January 2007 but the report has been delayed until the end of January beginning of February and it will need to be discussed at Infrastructure O&S and the County Council’s LAC and Highways Committee before going to Executive. |
| KD.061/06 | Cumbria Wind Energy Supplementary Planning Document and Sustainability Appraisal | The item was originally scheduled to go to Executive on 19 February 2007. It has been deferred and will now be reported to Executive on 19 March 2007. | Local Plans and Conservation Manager |
|  | Infrastructure O&S Reason: A joint officer meeting had been arranged for 16 January 2007 so all districts put the same information forward on feedback from the consultation. This means the deadline for Overview and Scrutiny on 27 January 2007 and Executive on 19 February 2007 will be missed. |
| KD.062/06 | Dalston Design Statement Supplementary Planning Document Infrastructure O&S | The item was originally scheduled to go to Executive on 19 February 2007. It has been deferred and will now be reported to Executive on 19 March 2007. | Local Plans and Conservation Manager |
|  | Reason: Delayed as the Government Office had a few concerns. The Parish Council have arranged a meeting for 19 January 2007. A part time officer is attending the meeting and won’t be in the office until after the Overview and Scrutiny Deadline. |
| KD.068/06 | Carlisle Renaissance – Development and Framework Movement Strategy | The item was originally scheduled to go to Infrastructure O&S on 25 January 2007. It will now go to a special Infrastructure on 14 February 2007 | Director of Carlisle Renaissance |
|  | Infrastructure O&S Reason: It has been necessary to call a Special meeting of the Infrastructure Overview and Scrutiny to deal with this item. |
| KD.032/06 | Equality and Diversity Policy | The item was originally scheduled to go to Executive on 22 January 2007. It has been deferred and will now be reported to Executive on 19 February 2007. | Head of Policy & Performance Services |
|  | Community O&S |  |  |
|  | Reason: To allow more time for work by the Corporate Equality Group and opportunity for Overview and Scrutiny to comment. |
|  | Local Authority Business Growth Initiative (LABGI) Funding | The item was not included in the Forward Plan. It was considered by the Executive on 22 January 2007 under General Exception rules. | Director of Development Services |
|  | Reason: Officers have received information on future LABGI funded and needed to update Executive for consideration as part of the budget. |
| KD.064/06 | Tullie House Development Plan | The item was scheduled in the Forward Plan for February or March 2007. It will not be going to Executive in February. | Head of Culture and Community Services |
|  | Community O&S |  |  |
|  | Reason: Awaiting the outcome of the decision from the Heritage Lottery Fund which is expected in the spring. |
| KD.071/06 | Housing Supply | The item was originally scheduled to go to Community Overview and Scrutiny on 15 February 2007. It has been deferred and will now be reported on 29 March 2007. |  |
|  | Community O&S |  |  |
|  | Reason: To allow consideration by the Executive then refer to Community Overview and Scrutiny Committee |