| BEST VALUE REVIEW - REVENUES AND BENEFITS SERVICES APPENDIX 2 Project/Workplan Plan |
| --- |
| Area Weakness | Investigation | Desired Outcome | Responsible Officer | Timescale |
| Performance Monitoring | Look at performance where we are not achieving top or second quartile via - Benchmarking information, identity like authorities with top quartile performance, liaise, compare and challenge our workflow arrangements, resource management, practices/procedures etc. Investigate internally blockages, unproductive routines etc. Stakeholder Consultation. | Achieve top or second quartile in all BVPIs by 2005/06 | P Mason (PM) E Turner (ET) M Wilson (MW) | December 2004 |
| Telephone Service to Public | Look to improve telephone service to public which Customer Consultation (June 2003) suggests is poor in respect of being able to get through without affecting assessment/processing performance. Via Business Process Re-engineering Assess likely impact of Corporate telephony Resources as part of the Customer Contact Initiative (economies of scale) Stakeholder consultation Compare and challenge our service with Authorities obtaining better satisfaction levels. | 75% success rate of completed calls on Revenues and Benefits telephone enquires by 1.4.2005 (currently 10%) | P Mason S Tweedie | June 2004 |
| Forms, Publicity and Written Correspondence | Customer Consultation (June 2003) suggests the Council’s forms, publicity and written correspondence are unsatisfactory particularly in respect of benefit forms Note: Forms etc, can only be improved ‘at the margins’ as most forms are either statutory or contain statutory information e.g. CTBI claim form Via Compare and challenge our forms etc in benchmarking terms with authorities that are obtaining better customer satisfaction levels ensure software provider is a consideration. Review forms and particularly advice on how to complete, where customers indicate via consultation that they are finding them difficult to understand. Investigate whether additional help and advice in completing forms particularly to the old, infirm and disabled would improve understanding. Stakeholder consultation needs to investigate whether dissatisfaction is due to designer volume of information required. | Improved satisfaction levels of Council’s form, publicity etc. Satisfaction levels currently running at 38% for benefit forms and 55% for Revenues. Note: Next statutory survey 2006/07. Bearing in mind most forms etc content is statutory a realistic outcome would be to improve satisfaction levels to over 50% across the Unit. | E Turner M Wilson | October 2004 |
| Staff Sickness | Look to improve staff attendance levels which are currently in bottom quartile Via Look at how to improve consultation and liaison with Personnel in progressing long-term sickness absence cases. Review current practice against new absence management policy. Look to champion corporately Homeworking Initiative (results in pilot authorities suggest leads to big reduction in short-term sickness levels). | Reduce Unit’s sickness levels currently averaging 15 days per person, year on year to 12 days per person by 2006/07. | M Wilson E Turner CMT | December 2004 |
| Managing Backlogs | Identify actions required to address backlog situations quicker and over shorter time scale. Via Learn from initiatives introduced to address previous backlogs in producing risk reduction plans/initiatives to be rolled out immediately backlog situations materialise. Look at best practice in managing staff turnover in identifying robust staff training initiatives. Review Practices in respect of managing staff leave and absence etc. | Improve workflow turnaround times to top/second quartile in all processes. | M Wilson E Turner | April 2004 |
| Not analysing effectiveness of methods of recovery | A BFI criticism was that the Council is not analysing success rates of different methods of recovery. Investigate how to target resources at most effective recovery method. Investigations required on all debts on how to analysis success rates of different recovery methods and use information to inform recovery practices and procedures. | To maintain improvement in collection rates year on year in reaching 2 quartile by 31.3.2006 | M Wilson J Chamberlin | September 2004 |
| Staff Flexibility | To investigate resources throughout peaks in Unit’s duties and responsibilities including providing support to new Customer Contact Centre at busy times. Investigate as part of the business process re-engineering exercise currently being undertaken (cross reference to backlog management). Define priorities for service where Business Unit boundaries interfere with service. | Improve service particularly to customers at work peaks i.e. main billing, mass benefits recalc etc. Measure increased customer satisfaction through the 3 yearly customer satisfaction survey (BVPi 80). Detail in team plans. | P Mason M Wilson E Turner S Tweedie | July 2004 |
| Lack to face-to-face Customer service points | Will be investigated part of Customer contact centre initiative | Introduce more fact to face Customer Service points. | S Tweedie | June 2004 |
| Failure to fully meet HB/CTB performance Standards (Note Major Resource Implications) | Investigate why the Council is not meeting DWP Performance standards i.e. 23% of the 666 standards not being met Via Assessing resource requirements (if any) to meet standards where standards reflect the Council’s corporate priorities etc. Look at the implications of giving priority to performance standards effecting public. Compare and challenge our service with authorities obtaining better performance against standards. | Meet 85% of standards (currently meeting 77%) by 1.4.2005. | E Turner | June/Sep/2004 January 2005 |
| Reliance on IT | By over 70 staff in the Unit for every aspect of their work Via Analysing computer downtime in liaison with IT staff to ascertain whether any further risk reduction measures or different working practices can be agreed to reduce computer downtime. | Reduce computer downtime resulting in increased efficiency of the Unit i.e. reduced processing times. Also improved staff moral and customer satisfaction. | P Mason M Wilson E Turner M Whitworth | January 2005 |
| Delays in Appeals Administration | Whilst the Unit is evidencing year on year improvements in Revenues and benefits administration, delays in adjudicating on benefit appeals has been a long-term problem for the Unit. It will be investigated/addressed in liaison with the advice agencies Via Investigate whether streamlining forms and document work flows will improve performance in consultation with Advice Agencies. Investigate targeting in-house benefit assessment resources more effectively Investigate how to be more proactive in directing claimants to advice agencies to obtain professional advice on progressing their appeal. - Stakeholder consultation. | Reduce appeals turnaround times to 20 days (from 40) with effect from 1.10.2003 | P Mason M Sharp | February 2004 |
| Areas where Best Value Review will be proactive in progressing Corporate Agenda | The review will inform on Revenues and Benefits input to the following corporate initiatives particularly relevant to the Unit including Introducing customer Contact Centre Inform on most efficient staff resource transfer, contribute to CRM scrips, piloting new arrangement in Revenues etc. E government - Look how E.government initiatives can facilitate service improvements in the Unit. Review of front and back office functions - Inform on most efficient back office structure in supporting Customer Contact Centre. Review of staff security on external visits (lone workers). - Feedback on draft policy - Investigate and Implement effective procedures to increase district staff safety. | - Proactive in meeting Corporate targets. | P Mason/ S Tweedie M Wilson/E Turner P Mason C Bell/ E Turner | June 2004 Ongoing June 2004 June 2004 June 2004 |
| Areas where Best Value Reviews will be proactive in Championing External Opportunities | The Review will inform on the following external opportunities Regional Government - Economies of scale Government Welfare Agenda - Investigate resource implications etc of building choice and responsibility into practices and procedures e.g. giving responsibility for rent payment back to tenant. | - Proactive in meeting Corporate targets. | P Mason E Turner | Ongoing Ongoing |
| Areas where Best Value Reviews will be proactive in assessing External Threats | The review will inform on the following external threats facing the Unit (and Council) including Competition for key staff white collar - Review staff grades in relation to similar internal and external job duties and responsibilities 2. Government Agenda in outsourcing processing type work - challenge internal provision Closure of Post Offices reducing customers payment options - Review other options e.g. allpay | Inform Corporate Agenda on these issues. | P Mason P Mason M Wilson | Ongoing Ongoing Ongoing |

Staff in bold type to lead on review of this work area.

Revenues & Benefits

Carlisle

24 March 2004

PM/EL/Amended Project Plan 3.04