AUDIT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 22 June 2007 |
| Title: | 3 YEAR FINANCIAL MANAGEMENT IMPROVEMENT PLAN |
| Report of: | The Director of Corporate Services |
| Report reference: | CORP31/07 |

Summary:

This report advises members on progress made in delivering the outcomes as set out in the 3 Year Financial Management Improvement Plan since 23 January 2007.

Recommendations:

- The Audit Committee is requested to note and comment on the progress made in delivering the 3 Year Financial Management Improvement Plan as set out in Appendix 1.

- Agree that for future monitoring purposes that the ‘more relevant’ Use of Resources Action Plan noted by the Audit Committee on 18 April 2007 be re-branded as the Financial Management Improvement Plan for the reasons set out in 3 of the report.

| Contact Officer: | Peter Mason | Ext: | 7270 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	The Chairman and Members of the					CORP31/07

Audit Committee

22 June 2007

ANCIAL MANAGEMENT IMPROVEMENT PLAN

1.	INTRODUCTION

  - The Executive, on 20 November 2007, approved the 3 Year Improvement Plan to improve the Council’s Financial Management arrangements and resolved that progress against plan targets would be monitored by the Audit Committee.

  - At its meeting of 23 January 2007 the Audit Committee considered progress against the 3 year Financial Management Improvement Plan.  The aim of the plan being to:

- Meet recommendations as set out in an independent review of financial management arrangements undertaken by the Institute of Public Finance;

- Incorporate outstanding items from the Statement of Accounts Action Plan;

- Address issues resulting from the 2005/06 Use of Resources Action Plan.

  - This report advises members of progress made since 23 January 2007.  It also advises that the implications of the Audit Commission continually updating (and making much harder to achieve) the Use of Resources assessment criteria are that the 3 Year Financial Management Improvement Plan needs re-focusing.  This will enable the Improvement Plan to better reflect the latest requirements of the Use of Resources assessment criteria.

2.	PROGRESS MADE IN IMPLEMENTING IMPROVEMENT PLAN SINCE 23 JANUARY 2007

  - Progress made since 23 January 2007 is indicated in the ‘Improvement Plan’ comments field (see Appendix 1).

  - Significant progress has been made in the review of the Financial Services Unit, i.e. workload peaks and troughs; roles of staff within finance function.  A report on the initial findings was discussed by SMT in May 2007.  The recommended changes in staff resource requirements to achieve the Council’s ambition of excellent financial management service provision was supported in principle, i.e. an additional Accountant and an Accountancy Assistant to replace the temporary resources currently employed (self financed from within the Directorate).  However with the uncertainty over the future of Local Government in Cumbria and the knock-on effect of difficulties in recruiting, SMT proposed to postpone the Financial Services restructure until after the Government’s announcement of its proposals in July 2007.  In the meantime the temporary arrangements currently in place will continue.

  - As mentioned above, with the current uncertainty of the future of Local Government in Cumbria it would be very difficult to recruit experienced practitioners in any event.  Indeed in the last month two of the unit’s experienced accountants have resigned to take up positions elsewhere in the region and this may impact on service provision.

  - Other progress in delivering the 3 Year Financial Management Improvement Plan has been reflected by the Audit Commission in an improved 2006/07 Use of Resources assessment.  This was reported to the Audit Committee on 18 April 2007.

- USE OF RESOURCES 2007/08 ONWARDS

  - This report to the Audit Committee of 18 April included an updated Use of Resources Action Plan detailing:

- Audit Commission 2006/07 Use of Resources feedback and observations;

- New harder tests to be introduced for 2007/08.  Further harder tests are due to be introduced for 2008/09 but are still subject to consultation.

  - It is the Council’s progress in meeting the requirements of continually changing Use of Resources criteria that it will be formally assessed in evidencing improved financial management.  It is therefore proposed that this Action Plan will be re-branded as the Financial Management Improvement Plan for Audit Committee and Corporate Resources Overview and Scrutiny for monitoring purposes at future meetings.  The next progress report is due in August/September 2007.

  - The Council has to provide its submission and supporting evidence detailing improvements made against Use of Resources criteria by 31 July 2007 (Value for Money by 30 June 2007).  The next monitoring report in August/September 2007 will reflect the improvements reported.

- RECOMMENDATIONS

  - The Audit Committee is requested to note and comment on the progress made in delivering the 3 Year Financial Management Improvement Plan as set out in Appendix 1.

  - Agree that for future monitoring purposes that the ‘more relevant’ Use of Resources Action Plan noted by the Audit Committee on 18 April 2007 be re-branded as the Financial Management Improvement Plan for the reasons set out in 3 of the report.

ANGELA BROWN

Director of Corporate Services

Contact Officer:	Peter Mason			Ext:	7270

APPENDIX 1

Financial Management Improvement Plan

(01.10.06 – 30.09.09)

(Priority Tasks in Bold)

| UOR Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | General |  |  |  |  |
| 1.1 1.4 | Assessment of workload / burden on each role within the finance function Detailed analysis of pattern of workload – establishing peaks and troughs Reallocation of tasks and responsibility where appropriate (including reviewing job descripti ons). | S McGregor/ S McGregor A Brown | Actioned | Increased capacity to support organisation. Better balance of workloads. | Initial review of duties and responsibilities actioned in February 2007. Annual workload (and ad-hoc where identified) by task and responsible officer has been mapped and resource requirements to meet workload, particularly at work peaks, has been assessed. Finance staff consulted on draft proposals for reallocation of tasks in March 2007. Revised structure discussed by SMT/CE May 2007 |
| 1.6 | Determine whether permanent increase in establishment or use of temporary resources at key times is best option. | A Brown/Chief Executive | Sept 2007 | New structure fully resourced by September 2007. | Awaiting results from above exercise. In the short term temporary accountancy resources taken on to 31.3.07 and a bid for £50k temporary resources for 2007/08 was approved as part of the budget process. Report drafted. May need to go to Council if >£60K virement. |
| 1.6 | Establishment of knowledge management systems: Development and maintenance of procedure notes and update the Financial Guide Increase level of job rotation (or job shadowing) Sessions on roles and processes as part of regular management team meetings (or forums) Cascade learning points from training or external events | S McGregor | March 2008 | As above. | All of these issues are being progressed by Head of Financial Services and Head of Personnel and Development Services, i.e. (i) Job shadowing will be considered (resource intensive) once staff comfortable with revised tasks after finance restructure. |
| 1.6 | Encourage innovation and initiative by: Supporting staff suggestions for change (as appropriate) Delegate responsibility for trialling changes / new concepts Encouraging representation on initiative / project teams by more junior staff Where appropriate, delegate representation on project groups to lower management levels. | S McGregor | Ongoing | Spread of knowledge and understanding. | Staff suggestions are made via TIR meetings and the monthly Teanable these to be made l work is planned to e. Whilst it is an excellent staff development technique, the delegation of new initiatives and projects is dependant on time available and to be effective requires a period of training/learning and is resource intensive (for managers). Representation on project groups is delegated where it is deemed that it will be effective and confident accurate advice will be provided. i.e. representation delegated on CPB Annual Accounts, Market Management, AMOC. This is subject to the capacity to develop skills in the relevant areas. |
| 1.1 - 1.3 1.8 | Annual Accounts Make full use of disclosure and audit checklists Require that the Audit Commission clarify their timetable of work for the final accounts process Ensure a clear audit trail down to source reports / documentation Introduce quality control mechanism for the working papers to reduce/eliminate errors Review 2005/06 papers and the action plan and provide the ‘missing’ information as part of the original papers to be handed to the Audit Commission 30/6/07 Identify high risk areas and work on these prior to the commencement of the 2006/07 closedown process. Ensure accounts are SORP compliant. Improve evidencing of figures and reasoning to support accounting treatment Significantly reduce errors in the accounts Reconciliation of systems provided as part of WPs Respond promptly to Auditors queries | A Taylor | Actioned in 2005/06 Accounts process but further improve-ments are being actioned for 2006/07 Accounts process | As above. Move Use of Resources score for Financial Reporting above the current score of 1 | Improvements have been made for 2005/06 as acknowledged by the Audit Commission. Further improvements required are being analysed and are being implemented as part of the 2006/7 Final Accounts process, which has now commenced. Work is ongoing to improve the standard of working papers which support the figures and accounting treatment within the accounts |
| 1.1 1.5 | Refine closedown timetable Ensure close working with external audit Ensure early consideration of changing requirements, material events or new accounting treatments | S McGregor | Actioned in 2005/06 Accounts process but further improve-ments to be actioned for 2006/07 Accounts process (see comments) | Accounts Audited to Statutory deadline and positive Annual Governance Report from the Audit commission. This improvement is also a key requirement of the Use of Resources Improvement Plan to move score to overall 3 by March 2008. | There are major changes to the Accounting requirements for the 2006/07 accounts. The implications of the changes have been considered and additional work is planned to enable these to be made as part of the 2006/7 Final Accounts process and timetable. An action plan for the improvements required has been drawn up (reported to the Audit Committee 18/4/07) and is being monitored against. Still considered inadequate. |
| 1.2 | Improve final accounts process: Carry out “dry run” closedown at end of Quarter 3 | A Taylor | January 2008 | As above | This will be attempted but is a significant workload, hence timescale. The revised finance structure will facilitate. |
| 2.4 | External accountability Consult with stakeholders on publishing annual report and summary financial information | A Brown | Aug 2007 | UOR score of 3 achieved | Consultation being undertaken with the Citizens Panel and Corporate Resources Overview & Scrutiny Committee. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| 2 | General |  |  |  |  |
| 1.20 | Financial Management in Projects/Initiatives Carry out a status review (and reality check) on all current projects and initiatives Assess priorities and develop a “deferral strategy” where resources will be directed to improving basic stewardship aspects as an interim measure Ensure that a risk management approach is taken in doing this | SMT (via Projects Programme Board) | Ongoing | Realistic workloads and capacity to support corporate priorities. | (i) SMT consider the impact of any new initiatives and additional resources will be requested where it is not considered feasible to deliver within existing capacity, e.g. White Paper work. (ii) Capital Projects Board is currently reviewing projects and assessing resource requirements. Note 2007/08 Capital Programme modest to progress/resource slippage from 2006/07 projects. Consider deferral strategy. |
| 1.7 1.8 | Introduce more challenge into the budgeting process by: Developing “decision conference” approaches where members and senior officers can consider priorities and growth bids. | SMT | Each budget process | Better allocation of resources to priorities. Better achievement of performance against budgets allocated. | Service Head Conference September 2006. Strategic Planning Group (Senior Members and Officers) meet regularly to consider priorities and bids prior to the formal consideration by Members. |
| 1.8 | Improve public consultation in the budgeting process. | SMT/Executive | 2007/08 budget process | More informed decision making by Members. | Public consultation via Citizens Panel and State of City. Need to use the results to inform Council priorities. |
| 1.19 | Developing Zero based budgeting techniques for areas (possibly on a rolling programme). | S McGregor | April 2009 | Reduced level of ‘underspends’. | Zero based budgeting has a resource implication and this will be introduced depending on resources following initial consideration by SMT. This initiative will be further considered as part of the Improvement Review programme. The inputs such as energy costs being investigated. |
| 2.20 2.20 | Improve forecasting to avoid underspends/ overspends by: Increased use of commitment accounting Stronger links with performance management – looking at activity as drivers of cost More stringent measures on continuing budgets (especially in areas of underspend) Integrate consideration of underspends more formally to the budget process Introduced action plans for significant variances Make service heads training for financial performance Change culture to a perception that “underspends” are not acceptable performance. Limiting carry-forwards (thresholds and time limits) Introducing tougher justification for carry forwards – reviewing criteria for evaluation Consider introducing punitive measures as appropriate if underspend culture exists. | S McGregor SMT SMT S McGregor Service Heads Service Heads Service Heads A Brown | 2007/08 budget process March 2007 | Reduced level of both carry forward and net underspends. Better VFM in setting Council Tax and holding appropriate balances. | Commitment accounting is currently being considered as part of the Procurement initiative led by the CPI. Work is being progressed as a priority during 2007/08 to improve the links with performance management. However, reliant on our software suppliers, CIVICA, for providing ledger software update. Significant variances have now been defined as the higher of £60,000 or 10% of gross service expenditure or income, i.e. Service Heads will now be required, with Financial Services staff support, to produce robust action plan to extinguish variances. This needs to be built into the Financial Procedure Rules. Training for Service Heads underway on account ability culture and process of managing variances. Currently no resources identified to progress activity based costing. Not realistic. Carry Forward procedures have been reviewed by SPG. Improved budget monitoring and performance management procedures will improve the issue of work not completed within original timescales. Report to SMT/SPG in February 2007 recommending suggested carry-forward limits, tougher justification for carry-forwards etc, particularly where underspend has not resulted in poor performance. |
| 3.3 3.11 | Managing Asset Base Develop property database. Develop local performance measures evaluating asset use in relation to corporate objectives. Ensure plan in place to manage the repairs backlog evaluating asset use in relation to corporate objectives | Director of Development Services | Aug 2007 | UOR score of 3 achieved | The development of the Property database is a high risk area as it provides information on the assets of the council, which is subject to considerable audit scrutiny. Responsibility for Management of assets is disjointed. York Consulting Improvements in repairs backlog needs evidenced. Evidence that investment and disposal decisions are based on thorough option appraisal and whole life costings. |
| 3.12 | Evidence that investment and disposal decisions are based on thorough option appraisal and whole life costings. | Service Heads | Ongoing |  | The Director of Development Services is currently considering options to develop this system and a report will be presented to SMT on progress in the near future. However, progress hindered by staff turnover within property Services. Financial Services Section will provide advice for the required action plan. Some progress made on asset valuation work. Not progressed – Use of Resources issue. |
| 1.5 1.10 1.13 1.15 1.16 1.20 | Delivering Strategic Priorities An annual improved review of budgets Cash flow monitoring for investments in detail acceptable to the Audit Commission Stronger links between the Corporate Improvement Plan and the MTFP Risk assessments and sensitivity analysis to be included in MTFP Improved links between the MTFP and key strategies. Improved procedures needed for new policy and capital developments | S McGregor | Aug 2007 | Achieve UOR level 3 | Work progressing with C Curr on linking Corporate Improvement Plan and MTFP. |
| 2.10 2.12 | Managing performance against budget Financial systems to be regularly tested to ensure they are secure Review the financial performance of partnerships and share results with partners | I Beckett M Mark | Aug 2007 | Achieving UOR level 3 | Internal Audit in conjunction with the Audit Commission will review bank reconciliation. Recent review of partnership practices and procedures should show progress in this area |
| 1.4 | Develop reporting capability by: Making full use of Crystal Reports Training staff in Crystal where necessary Running workshops / sessions to establish what users would wish to see in their reports Ensure written financial reports are simplified as far as possible to aid understanding by Members and Officers | S McGregor | Dec 2007 | Improved financial and budget monitoring. | A full ledger development plan has been drawn up. Civica, have subsequently provided resources to ensure the most current version of the Financial Management System is implemented. This was achieved prior to the 31st March. Further assistance is now required to ensure staff are trained in the enhancements including Crystal reporting. Financial reports (where the content is complicated/ technical to meet statutory requirements), e.g. Treasury Management, one page summaries in layman’s terms now included as part of report. Easy to understand budget booklet has been prepared to assist in future consultation exercises. Summary Statement of Accounts has been produced. |
| 1.19 2.15 | Encourage continuing professional development and financial awareness training: Maximise benefit of corporate CPD registration Encourage increasing knowledge / training / experience of public sector finance issues (esp. local authorities) for non-CIPFA CCAB qualified staff Ensure time is made available for CPD activities Ensure all relevant Council staff participate in financial training programme | S McGregor S McGregor/ D Williams | Ongoing | Spread of finance knowledge throughout organisation. More generic financial advice. Reduced reliance on key finance personnel thereby increasing overall capacity. | Training/CPD programme already in place for CCAB qualified members. It is recognised that other finance staff would benefit from participating in more formal CPD activities and this will be further encouraged and progressed as part of the formal appraisal meetings. Extension of current programme is dependent on resources/workload, which is addressed elsewhere on the Improvement Plan. With respect to authority wide financial training, a programme of training has already commenced and is being developed further. This has been incorporated into the Council’s Corporate Training Programme, which is underway. |
| 3.2 | Develop clearer links with performance management, risk management and asset management. This can be done through: Using unit costs for activity Linking activity levels with budgets / spend Linking key PI’s with spend | S McGregor | 2008/09 | Better understanding of link between costs and activities. | Would not be achievable in the current year from existing resources. The achievement of this would require further consideration. Clearer lines with performance management are a key priority for 2007/08 and this is being achieved through quarterly performance conferences for Service Heads. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| 3 | Financial Standing |  |  |  |  |
| 1.3 1.9 | Spending within available resource Review policy on reserves to ensure levels remain appropriate. Maximise best use of resources by identifying underspends and overspends. | A Brown | Aug 2007 | UOR score of 3 retained | If reserve levels are exceeded the costs and benefits of holding balances will be considered and reported to Members. |
| 1.2 | Improve commitment accounting by full implementation of electronic ordering to ensure all purchase orders are reflected in the FIS | S McGregor | Dec 2007 | Improved Financial Monitoring Information | Commitment accounting is a major factor in the implementation of e-procurement, which is currently being developed by the Development & Support Team as part of the Cumbria Procurement Initiative (CPI). The Contractor Plus system operated by Community Services is currently being reviewed with a view to replacement within the next 12 months. A short list has been produced and the evaluation process is currently underway. It is anticipated that the contract will be awarded 1st of June 2007. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| 4 | Internal Control |  |  |  |  |
| 1.3 1.7 1.8 | Managing significant business risks Link risks in the risk register to corporate objectives Ensure complex partnerships risks are considered and actively managed Ensure staff get training and guidance on managing risk |  | Aug 2007 | UOR score of 3 | Working towards this. Risk management process will be reviewed and updated at least annually. |
| 2.3 2.8 2.12 2.13 2.7 | Maintaining sound system of internal control Sources of assurance supporting the SIC to be passed to Members Develop new Business Continuity Plan that is implemented promptly and reviewed regularly Ensure governance arrangements in place for significant partnerships Produce and review timely traditional bank reconciliations Updated procedure notes for all key financial systems | I Beckett | Aug 2007 | UOR score of 3 achieved | J Gooding is working on a new Business Continuity Plan Procedure notes are currently under review, progress being monitored by J Chamberlin |
| 3.13 3.8 3.14 | Promote Probity and Propriety in the conduct of business Ensure strong counter fraud culture supported and promoted by Members and senior officers Promote whistleblowing policy to contractors Promote proactive fraud and corruption work that is risk assessed and adequately resourced. | I Beckett | Aug 2007 | UOR score of 3 achieved | Draft Counter Fraud Policy developed. Gap analysis being undertaken to inform action plan of required improvements. |

| Ref | Recommended Action for Improvement | Agreed Responsibility | Indicative Timescale | Measure of Success | Progress/Comments |
| --- | --- | --- | --- | --- | --- |
| 5 | Value for Money |  |  |  |  |
| .1 | Achieving good value for money Some good practice but needs further evidence and embedded Improve the evaluation of service quality and cost factors to target relative improvements in VFM, including the effectiveness of increased investment. | P Mason | Ongoing (3 to 5 years) | UOR score of 3 in the longer term | Council is relatively high spending and connections between high expenditure and high performance. High performance is not demonstrated across all service areas. Increased investment has been targeted at priority areas and improvement trends resulted. Efficiency targets set and monitored. Processes stating to develop to identify particular areas for efficiency gains. Evaluation of accessibility across localities and for vulnerable groups is not developed. |
| .2 | Managing and improving value for money Improve the availability and use of corporate intelligence on equity of access to services and variation in locality performance and need. Ensure the best application of resources by reviewing profiles of underspending at corporate and service level. | P Mason | Ongoing (3 to 5 years) | UOR score of 3 in the longer term | Some positive trends, improvements in performance alongside increased cost efficiency. Currently some slippage against project timetables and the overall annual programme, recent developments to monitoring information should assist further development. Corporate processes do not show strong links between cost, activity and performance evaluation. Procurement processes are developing and spending patterns reviewed. |