CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 23 February 2006 |
| Title: | SICKNESS ABSENCE |
| Report of: | Head of Member Support & Employee Services |
| Report reference: | ME 01/06 |

Summary:

This report provides details of the Council’s performance under BVPI 12 – average no of days sickness absence per employee – for quarters 1-3 of 2005/06 and updates members on progress with the 2005/06 Improving Attendance Action Plan.

Recommendations:

Members note the report

| Contact Officer: | Jean Cross | Ext: | 7081 |
| --- | --- | --- | --- |

SICKNESS ABSENCE Quarters 1 - 3  2005/06

- Introduction

Members last considered a report on this subject on 1 December 2005. This report updates members on sickness absence performance for the period April – December 2005 and the progress to date against the Improving Attendance Action Plan for 2005/06.

- Performance

The table below shows the average number of days sickness absence taken by each employee in the period April to December 2005.  It includes for comparison purposes the figures for the same period in 2004/05, the whole year 2004/05, the estimated outcome for 2005/06 and the targets for improvement.

Table 1: Comparison of Performance

|  | April – December | Whole Year | Targets |
| --- | --- | --- | --- |
| 2005/06 | 8.58 days | 11.8 days* | 11.58 days |
| 2004/05 | 9.45 days | 12.87 days | 11.52 days |

* estimate

As can be seen, there is a slight improvement in performance and when we extrapolate this for the full year, we look set to have an absence level of 11.8 days, which is 1.9% over target.

Members may be interested in further detail of the performance for the April – December period. Appendix 1 provides a comparison of the 9 months 2004/5 and 2005/6, by Business Unit.  As can be seen there are small improvements in more than 50% of the business units. The reduction in the time lost through sickness from the same period last year is 555 days. Applying a mean cost per employee to this figure yields an estimated value of £43800. This will be contributing to the Gershon savings.

- Area Working in Commercial and Technical Services

It was hoped that area working would contribute to increased attendance.  Analysis has shown that during the first 9 months of operating, absence levels have reduced by around 20%.

- Improving Attendance Action Plan

Appendix 2 provides an update on progress against the Action Plan.

Main progress includes

- The grouping of illnesses categorised as ‘stress, depression, anxiety, neurasthenia, mental health and fatigue syndromes’ remains one of the major causes of absence, accounting for 22.5% of the days lost in the 9-month period.  Work is continuing to better identify the extent and nature of the problem caused by stress within the Authority in order to enable us to focus remedial activity.

- The number of return to work interviews being carried out continues to be monitored and apart from a dip over the Christmas holiday period, continues to show significant improvement, as seen in the table below.

| Period Monitored | Total No. Absences | Percentage of Return to Work Interviews held by Business Units |
| --- | --- | --- |
| January 2006 | 133 | 90.2% |
| December 2005 | 118 | 85.6% |
| November 2005 | 105 | 92.4% |
| October 2005 | 123 | 94.3% |
| September 2005 | 135 | 74.0% |
| Sept – Dec 2004 | 358 | 55.0% |

- Conclusions

A number of actions are being pursued to reduce sickness absence and continued monitoring will be carried out to judge the effects of them.  Cautious optimism can be given to the improvement in attendance levels.

- Recommendations

That members note the report.

Appendix 1

Sickness Absence by Business Unit

| Business Unit | Average days absence per employee |
| --- | --- |
|  | Quarters 1 - 3 |
|  | 2004-05 | 2005-06 |
| CLS | 8.63 | 12.07 |
| CTS | 12.86 | 11.76 |
| CIS | 7.26 | 3.54 |
| ECD | 8.42 | 8.99 |
| EPS | 7.90 | 7.37 |
| EXEC Group | 1.29 | 4.04 |
| FS | 2.89 | 4.00 |
| LDS | 6.84 | 2.94 |
| MSES | 4.88 | 3.82 |
| PLANNING | 5.51 | 4.56 |
| PROPERTY | 10.11 | 2.15 |
| RBS | 8.03 | 5.95 |
| SPS | 8.58 | 2.32 |
| TOTAL | 9.44 | 8.58 |

Appendix 2

Improving Attendance Action Plan 2005-06

| Action | Timescale | Targets | Progress |
| --- | --- | --- | --- |
| Devise a diagnostic tool to allow BU Heads to assess their readiness/capability to manage sickness absence to enable them to draw up action plans to address them | By October 2005 | Proposals to CMT by September; Management Briefing presentation October 2005; Completion of assessment by BU Heads by end October 2005 | Business Units have completed this now and are working through it. |
| Management Briefing presentations | Two between during the year | October 2005 and March 2006 | Deferred in favour of a full briefing to be devoted to ‘sickness absence’ within the next two months |
| Continue with ‘Improving Attendance’ working group – joint with Trades Unions – focus on timeliness and usefulness of management information | Quarterly | Meetings arranged for July 2005, October 2005 and January 2006 | On-going |
| Homeworking Pilot | Pilot run and assessed by March 2006 | Pilot to start September 2005 | Started Sept 05, and evaluation of the project is underway. Initial indications are that there has been a significant reduction in absence. |
| Pilot to establish baseline measurement of ‘Stress’ within the Authority – using HSE Stress Questionnaire | Once development work by HSE complete | Pilot by October; subsequent action informed by Pilot outcome | Pilot completed; being ‘rolled out’ to the rest of the authority starting with Corporate Services |

| Carry out Manual Handling training tailored to specific job activities | End of September 2005 | Refuse Collectors trained by Sept 2005 | On-going |
| --- | --- | --- | --- |
| Appoint a BU ‘Attendance Champion’ | By June 2005 | June 2005 | Done – June 2005 |
| Continue with offering corporate training courses Good Practice (module D6 in MDP) Absence management procedures & return to Work Interviews | During 2005/6 During 2005/6 |  | Included in current Corporate Training Last course was on 26 January 2006 Continues to be offered within the MDP |
| Continue with provision of information: CROS CMT BU Heads | Quarterly Quarterly Quarterly |  | On-going |
| Continue with provision of advice to managers in specific cases | On-going |  | On-going |
| Occupational Health Pilot – continue with purchasing robust advice selecting parts of poor performing BUs for more intensive and proactive intervention | On-going as soon as possible | Review effect January 2005. If there is a Business Case – put this to Members by March 2006 | Pilot is well under way and a full assessment of the impact will be made after it is completed in March 06. Early anecdotal evidence has indicated much faster response times. |
| Health Surveillance of all employees who may be exposed to hand/arm vibration equipment | During 2005/6 | All relevant individuals screened and any issues highlighted addressed | Commenced and in progress |