## Summary - to be hidden (hidden)
2009/10 CAPITAL SUMMARY
| Revised | Expenditure | Total | Carry | Adjusted | Carry | Adjusted
| Annual | to date | Variance | Forwards | Variance | Forwards | Variance
| Budget | 2009/10 | 2009/10 | (Committed) |  | (New items)
2009/10
| £ | £ | £ | £ | £ | £ | £
Community Services | 4835600 | 3807037 | -1028563 | 974500 | -54063 | 0 | -54063
Corporate Services | 1607900 | 1475257 | -132643 | 128200 | -4443 | 0 | -4443
Development Services | 4608900 | 4267092 | -341808 | 326700 | -15108 | 0 | -15108
Legal & Democratic Services | 29700 | 0 | -29700 | 29700 | 0 | 0 | 0
| 11082100 | 9549386 | -1532714 | 1459100 | -73614 | 0 | -73614
| 11082100 | 9549385 | -1532715 | 1459100 |  | 0 | -73614
| 0 | -1 | -1 | 0 |  | 0 | 0

## Community
PROVISIONAL GENERAL FUND CAPITAL OUTTURN 2009/10 | [8 empty] | APPENDIX A1
COMMUNITY SERVICES
Position as at 31 March 2010
Directorate
Scheme | Revised | Expenditure | Total | Carry | Adjusted | Carry | Adjusted | Category
| Annual | to date | Variance | Forwards | Variance | Forwards | Variance | of | Details of major variances
| Budget | 2009/10 | 2009/10 | (Committed) |  | (New items) |  | Carry
| 2009/10 | [6 empty] | Forward
| £ | £ | £ | £ | £ | £ | £ | (Note 1)
Sheepmount Development | 45400 | 44603 | -797 | 800 | 3 | 0 | 3 | A | Carry forward covers the planned work still to be completed which was delayed due to equipment unavailability. | CE
Sheepmount Drainage | 0 | 13222 | 13222 | 0 | 13222 | 0 | 13222 | - | Funded from an earmarked reserve. Transfer actioned at year end. Contract awarded and works to commence in Spring 2010. | CE
CCTV | 35000 | 33326 | -1674 | 0 | -1674 | 0 | -1674 | - | Required work in 2009/10 completed. Further budget available in 2010/11. | LE
Kingstown Industrial Estate | 554000 | 54889 | -499111 | 499100 | -11 | 0 | -11 | A | Delays in the proposed work to reconstruct Kingstown Broadway to a standard suitable for adoption. | R
Willowholme Industrial Estate | 4000 | 0 | -4000 | 4000 | 0 | 0 | 0 | A | Work to reconstruct part of Willowholme Road has been delayed due to work by other agencies requiring to be completed prior to commencement of the City Council work. | R
Durranhill Industrial Estate | 3900 | 1850 | -2050 | 0 | -2050 | 0 | -2050 | - | Project complete. | R
Customer Contact Centre | 0 | -2264 | -2264 | 0 | -2264 | 0 | -2264 | - | Project linked to the corporate wide review of Customer Services. | CE
Planned Major Repairs | 252300 | 237588 | -14712 | 14700 | -12 | 0 | -12 | A | Expenditure fully committed and carry forwards required to complete works at the Old Town Hall (part of larger project), Civic Centre and DDA Accessibility Improvements. | R
Vehicles and Plant | 1891600 | 1859137 | -32463 | 35700 | 3237 | 0 | 3237 | A | The replacement of one vehicle has been postponed until 2010/11. | R
MUGA Trinity Church | 137100 | 1534 | -135566 | 135500 | -66 | 0 | -66 | A | Awaiting confirmation from Diosese that ground is not consecrated before we can commence | CE
Talkin Tarn | 28700 | 31758 | 3058 | 0 | 3058 | 0 | 3058 | - | Project complete. | LE
Lowry Hill Park | 14300 | 43783 | 29483 | -29500 | -17 | 0 | -17 | A | Contract placed and equipment stored at Bousteads. Anticipated start late May/early June. | LE
ODPM - Making Space for Water | 25000 | 0 | -25000 | 25000 | 0 | 0 | 0 | A | This budget was allocated from the £1.5million capital grant received in 2005/06 from the Office of the Deputy Prime Minister to be spent on capital works within the flood affected area. | LE
Play Area Developments | 180500 | 21590 | -158910 | 135000 | -23910 | 0 | -23910 | A | Work on some schemes completed and final account awaited. Contracts for other schemes placed and due to start late June. | LE
Synthetic Football Pitch | 0 | 158 | 158 | 0 | 158 | 0 | 158 | - | Project complete. | CE
Renaissance Improvements | 46000 | 21226 | -24774 | 24700 | -74 | 0 | -74 | A | Budget relates to 2 schemes. Renovation and renewal of the murals on Hardwicke Circus has been delayed by weather and requires carried forward to complete the scheme. Additional funding still to be identified. The other part of the budget provides match funding towards the implementation phase of the Urban Design Framework. | ED
Environmental Improvements | 200500 | 175909 | -24591 | 0 | -24591 | 0 | -24591 | - | Budget underspent at year end. Further work to be accommodated within 2010/11 budget. | LE
Waste Minimisation | 38400 | 47221 | 8821 | 0 | 8821 | 0 | 8821 | - | External contributions received for this scheme. | LE
Greystone Community Centre | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | - | Project complete. Funding being managed in conjunction with Community Association. | CE
Chances Park | 793800 | 559709 | -234091 | 234000 | -91 | 0 | -91 | A | Construction phase completed early May and final account awaited. | LE
Small Scale Community Projects | 26000 | 22841 | -3159 | 0 | -3159 | 0 | -3159 | - | Installation of CCTV Camera at Botcherby complete. | SD
Belah Community Centre | 5100 | 5052 | -48 | 0 | -48 | 0 | -48 | - | Project complete. | CE
Castle Street Public Realm | 53300 | 41093 | -12207 | 0 | -12207 | 0 | -12207 | - | Full project has been approved by Cumbria County Council and is expected to be completed by end of 2010/11. Majority of budget reprofiled into 2010/11. | SD
Raffles MUGA | 87200 | 87154 | -46 | 0 | -46 | 0 | -46 | - | Project complete. | CE
Petteril Riverbank Protection Work | 34300 | 32923 | -1377 | 1300 | -77 | 0 | -77 | A | Carry forward required to accommodate final account of contract. | LE
Hammonds CCTV | 21000 | 16953 | -4047 | 4000 | -47 | 0 | -47 | A | Carry forward required to complete the installation of the connection links. | LE
Caldew/City Centre Flood Defence | 20500 | 8311 | -12189 | 12100 | -89 | 0 | -89 | A | Project has been delayed by some minor design changes and is linked to the Connect 2 Cycleway scheme. | LE
Kingmoor Nature Reserve | 20500 | 17115 | -3385 | 0 | -3385 | 0 | -3385 | - | Installation of signage and boardwalks completed. | LE
Connect 2 Cycleway | 60000 | 61731 | 1731 | 0 | 1731 | 0 | 1731 | - | £50,000 external funding received. Overspend incorporated in larger project going fowrward. | ED
Heysham Park Play Area | 49700 | 49055 | -645 | 600 | -45 | 0 | -45 | A | Project completed. Remaining budget required to accommodate project management required for an inspection to allow payment of the retention. | LE
Energy Efficiency - Carbon Trust Initiative | 163500 | 156145 | -7355 | 6000 | -1355 | 0 | -1355 | A | Expenditure fully committed and carry forward is required to complete work already started. | R
Eden Bridge Garden Restoration | 20000 | 10895 | -9105 | 0 | -9105 | 0 | -9105 | - | Project complete within budget. | LE
Roman Gateway | 3000 | 131530 | 128530 | -128500 | 30 | 0 | 30 | A | This project spans a couple of financial years and the overspend relates to profiling between the years. The budget in 2010/11 can accommodate this overspend. | ED
TOTAL | 4835600 | 3807037 | -1028563 | 974500 | -54063 | 0 | -54063
Note 1
A - Committed expenditure (to be used for original purpose/externally funded)
B - New items of Expenditure
A/B - Combination of committed expenditure and new items of expenditure
[7 empty] | Key: |  | SD - Strategic Director
CE - Community Engagement
CE'sO - Chief Executive's Office
ED - Economic Development
LE - Local Environment
R - Resources

## Corporate
PROVISIONAL GENERAL FUND CAPITAL OUTTURN 2009/10 | [8 empty] | APPENDIX A2
CORPORATE SERVICES
Position as at 31 March 2010
Scheme | Revised | Expenditure | Total | Carry | Adjusted | Carry | Adjusted | Category
| Annual | to date | Variance | Forwards | Variance | Forwards | Variance | of | Details of major variances
| Budget | 2009/10 | 2009/10 | (Committed) |  | (New items) |  | Carry
| 2009/10 | [6 empty] | Forward
| £ | £ | £ | £ | £ | £ | £ | (Note 1)
ICT Shared Service | 206200 | 101497 | -104703 | 104700 | -3 | 0 | -3 | A | Underspend is due to a delay in establishing the service.
IT Equipment | 25400 | 36711 | 11311 | 0 | 11311 | 0 | 11311 | - | The overspend relates to the network renewal budget as the refurbishment of the 9th floor had not been previously budgeted for.
Document Image Processing | 45000 | 0 | -45000 | 45000 | 0 | 0 | 0 | A | Project on hold pending creditor/debtor efficiency review. Will now commence in 2010/11.
City Wi Fi | 9400 | 7982 | -1418 | 0 | -1418 | 0 | -1418 | - | Budget used to improve WiFi coverage in Civic Centre. Completed within budget.
Real IT System | 53100 | 38796 | -14304 | 0 | -14304 | 0 | -14304 | - | Asset Management System successfully installed and running. Completed within budget.
RBS Shared Service | 70500 | 92014 | 21514 | -21500 | 14 | 0 | 14 | A | Part of the Shared Service Business Case. Budget available in 2010/11 to fund the overspend in 2009/10.
Capitalisation Redundancy Costs | 1198300 | 1198257 | -43 | 0 | -43 | 0 | -43 | - | Redundancy costs in relation to Transformation transferred from the reserve..
TOTAL | 1607900 | 1475257 | -132643 | 128200 | -4443 | 0 | -4443
Note 1
A - Committed expenditure (to be used for original purpose/externally funded)
B - New items of Expenditure
A/B - Combination of committed expenditure and new items of expenditure

## Development Services
PROVISIONAL GENERAL FUND CAPITAL OUTTURN 2009/10 | [8 empty] | APPENDIX A3
DEVELOPMENT SERVICES
Position as at 31 March 2010
Scheme | Revised | Expenditure | Total | Carry | Adjusted | Carry | Adjusted | Category
| Annual | to date | Variance | Forwards | Variance | Forwards | Variance | of | Details of major variances
| Budget | 2009/10 | 2009/10 | (Committed) |  | (New items) |  | Carry
| 2009/10 | [6 empty] | Forward
| £ | £ | £ | £ | £ | £ | £ | (Note 1)
Private Sector Grants - Minor Works Grants | 20000 | 8626 | -11374 | 11300 | -74 | 0 | -74 | A | £9,000 has been approved and committed to grants for works to be carried out at the year end.
Disabled Facilities Grants | [7 empty] | A | These grants are mandatory. Existing balance of budget committed to approved grants with works due to be carried out and invoiced for.
- Private | 1047000 | 634910 | -412090 | 224500 | -187590 | 0 | -187590
- Housing Strategy | 300000 | 487494 | 187494 | 0 | 187494 | 0 | 187494
| 1347000 | 1122404 | -224596 | 224500 | -96 | 0 | -96
GIS | 14000 | -1790 | -15790 | 0 | -15790 | 0 | -15790 | - | This relates to the charge from the Council's GIS supplier covering 2009-2011 which was under negotiation and not resolved until after 1 April 2010
Housing Strategy - Empty Homes | 60000 | 15500 | -44500 | 44500 | 0 | 0 | 0 | A | Approved commitment of grants is £48,000 with a number of ongoing applications. Carry forward of balance of budget required.
Housing Strategy - Housing Provision | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | - | Commitment to Extra Care scheme and choice based lettings.
Housing Strategy - Renovation Grants | 0 | 1109 | 1109 | 0 | 1109 | 0 | 1109 | - | These are discretionary grants with a couple that were approved prior to us stopping these grants.
Resource Centre | 94600 | 118501 | 23901 | -23900 | 1 | 0 | 1 | A | Consists of design overspend & creditor list. 2010/11 budget will accommodate. Contract to be awarded in June and start in July 2010.
Ghyll Bank Gypsy & Traveller Site | 1473300 | 1424687 | -48613 | 48600 | -13 | 0 | -13 | A | Project completed and handed over. Monies required for final account - due in next 4 weeks.
ODPM Private Sector Renewal | 0 | -173 | -173 | 0 | -173 | 0 | -173 | - | Projects completed under Housing part of this budget.
Sub Regional Employment Sites | 1540000 | 1518228 | -21772 | 21700 | -72 | 0 | -72 | A | This consists of NWDA grant allocation within estimated 2009/10 spend figure. The grant claim and associated expenditure was delayed by ecological constraints on start of substantive demolition works and discovery of unexpected asbestos in two of the buildings.
TOTAL | 4608900 | 4267092 | -341808 | 326700 | -15108 | 0 | -15108
Note 1
A - Committed expenditure (to be used for original purpose/externally funded)
B - New items of Expenditure
A/B - Combination of committed expenditure and new items of expenditure

## LDS
PROVISIONAL GENERAL FUND CAPITAL OUTTURN 2009/10 | [8 empty] | APPENDIX A4
LEGAL & DEMOCRATIC SERVICES
Position as at 31 March 2010
Scheme | Revised | Expenditure | Total | Carry | Adjusted | Carry | Adjusted | Category
| Annual | to date | Variance | Forwards | Variance | Forwards | Variance | of | Details of major variances
| Budget | 2009/10 | 2009/10 | (Committed) |  | (New items) |  | Carry
| 2009/10 | [6 empty] | Forward
| £ | £ | £ | £ | £ | £ | £ | (Note 1)
Gateway - General Expenses | 29700 | 0 | -29700 | 29700 | 0 | 0 | 0 | A | This sum is in respect of a retention currently held back (on the advice of the County archaeologist) from the final stage payment due to Oxford Archaeology under the contract with them for completing the Millennium Scheme archaeological texts.
TOTAL | 29700 | 0 | -29700 | 29700 | 0 | 0 | 0
Note 1
A - Committed expenditure (to be used for original purpose/externally funded)
B - New items of Expenditure
A/B - Combination of committed expenditure and new items of expenditure

## 2010-11 Prog
2010/11 CAPITAL PROGRAMME |  |  |  |  | APPENDIX B1
Scheme | Original | Carry | Brought | Other | Revised
| Capital | Forwards | Forward | Adjustments | Capital
| Programme | from | From |  | Programme
| 2010/11 | 2009/10 | 2011/12 |  | 2010/11
| £ | £ | £ | £ | £
Current non-recurring commitments
Customer Contact Centre | 49600 |  |  |  | 49600
Chances Park |  | 234000 |  |  | 234000
Centre of Excellence | 3081000 | -23900 |  |  | 3057100
Environmental Enhancements | 168000 | 0 |  |  | 168000
Sub Regional Employment Sites | 256000 | 21700 |  |  | 277700
RBS Shared Service | 132900 | -21500 |  |  | 111400
Document Image Processing |  | 45000 |  |  | 45000
| 3687500 | 255300 | 0 | 0 | 3942800
Recurring commitments
Housing Strategy - Affordable Housing | 300000 |  |  |  | 300000
Housing Strategy - Empty Homes | 140000 | 44500 |  |  | 184500
Housing Strategy - Decent Homes | 300000 |  |  |  | 300000
Housing Strategy - Minor Works grants |  | 11300 |  |  | 11300
Housing Strategy - Housing Provision | 200000 |  |  |  | 200000
Planned Enhancements to Council Property | 358700 | 14700 |  |  | 373400
Willowholme Industrial Estate | 135000 | 4000 |  |  | 139000
Kingstown Industrial Estate |  | 499100 |  |  | 499100
Play Area Developments | 50000 | 135000 |  |  | 185000
Vehicles, Plant & Equipment | 381500 | 35700 | 6000 | 4200 | 427400
ICT Shared Service | 380000 | 104700 |  |  | 484700
CCTV | 70000 |  |  |  | 70000
| 2315200 | 849000 | 6000 | 4200 | 3174400
New non-recurring commitments
Womens Hostel Replacement | 200000 |  |  |  | 200000
Old Town Hall | 970000 |  |  |  | 970000
Roman Gateway | 2117000 | -128500 |  |  | 1988500
| 3287000 | -128500 | 0 | 0 | 3158500
Disabled Facilities Grants
Private Sector Grants | 1249000 | 224500 |  |  | 1473500
| 1249000 | 224500 | 0 | 0 | 1473500
Continuing Schemes
Gateway - General Expenses |  | 29700 |  |  | 29700
Ghyll Bank Gypsy and Travellers Site |  | 48600 |  |  | 48600
Lowry Hill Park | 75700 | -29500 |  |  | 46200
Trinity Church MUGA |  | 135500 |  |  | 135500
Heysham Park Play Area |  | 600 |  |  | 600
Petteril Riverbank Protection Work |  | 1300 |  |  | 1300
Hammonds CCTV |  | 4000 |  |  | 4000
Caldew/City Centre Flood Defence |  | 12100 |  |  | 12100
Historic Quarter | 719800 |  |  |  | 719800
Carbon Trust Energy Efficiency |  | 6000 |  |  | 6000
Renaissance Improvements |  | 24700 |  |  | 24700
| 795500 | 233000 | 0 | 0 | 1028500
Flood
ODPM Private Sector Renewal |  | 25000 |  |  | 25000
Sheepmount Development |  | 800 |  |  | 800
| 0 | 25800 | 0 | 0 | 25800
TOTAL | 11334200 | 1459100 | 6000 | 4200 | 12803500

## 5 yr Cap Programme
2011/12 to 2014/15 PROPOSED CAPITAL PROGRAMME | [10 empty] | APPENDIX B2
Scheme | Ledger | Original | Agreed | Potential | Revised | Original | Brought | Revised | Original | Original | Original
| Code | Capital | Carry | c/fwds from | Capital | Capital | Forward | Capital | Capital | Capital | Capital
|  | Programme | Forwards | 2006/07 | Programme | Programme | to | Programme | Programme | Programme | Programme
|  | 2007/08 |  |  | 2007/08 | 2011/12 | 2010/11 | 2011/12 | 2012/13 | 2013/14 | 2014/15
|  | £ | £ | £ | £ | £ | £ | £ | £ | £ | £
Private Sector Grants |  | 849000 | 17000 | 328300 | 1194300 | 1249000 |  | 1249000 | 1249000 | 1249000 | 849000
Planned Enhancements to Council Property |  | 250000 |  | -24400 | 225600 | 300000 |  | 300000 | 300000 | 300000 | 300000
Vehicles, Plant & Equipment |  | 536000 |  | 302600 | 838600 | 1048000 | -6000 | 1042000 | 327000 | 259800 | 0
IT Equipment | [5 empty] | 244800 |  | 244800 | 188800 | 193000 | 108000
Housing Strategy | 90211 | 1250000 |  | -729000 | 521000 | 900000 |  | 900000 | 900000 | 900000 | 0
Play Area Developments | 90253 | 75000 |  | 50000 | 125000 | 0 |  | 0 | 50000 | 0 | 50000
Womens Hostel Replacement |  | 200000 | 0 | 35200 | 235200 | 1560000 |  | 1560000 | 40000 | 0 | 0
CCTV |  | 200000 | 0 | 35200 | 235200 | 20000 |  | 20000 | 50000 | 50000 | 0
Concessionary Fares | 90261 |  | 90000 |  | 90000 | 30000 |  | 30000 | 0 | 0 | 0
TOTAL |  | 3360000 | 107000 | -2100 | 3464900 | 5351800 | -6000 | 5345800 | 3104800 | 2951800 | 1307000