Corporate resources OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 25 May 2004 |
| Title: | BUSINESS PLAN PERFORMANCE MONITORING REPORT |
| Report of: | Head of Revenues & Benefits |
| Report reference: | RB2/04 |

Summary:

This report details the Unit’s progress against the Revenues & Benefits Business Plan during the period 1 April to 31 March 2004 covering key developments and challenges update; progress on Best Value; achievement of performance against Best value indicators; and budget update.  This report has been presented to CMT on 5 May and has been amended, where appropriate, to include their comments.

Recommendations:

That Members note the report.

| Contact Officer: | Peter Mason | Ext: | 7270 |
| --- | --- | --- | --- |

CARLISLE CITY COUNCIL

To:	Corporate Resources Overview & Scrutiny			RB2/04

Committee

Date:	 25 May 2004

BUSINESS PLAN PERFORMANCE MONITORING REPORT

Revenues & Benefits Business Unit

Corporate Management Team (date) 5.5.2004

#### INTRODUCTION

1.1	The purpose of this report is to report to CMT on 5 May 2004 and the Corporate Resources Overview and Scrutiny Committee on 25 May 2004 on the progress of the Business Plan for the Revenues and Benefits Service business Unit.  Included in this report is an update of Performance Indicators and where available, performance monitoring in formation for these indicators.

1.2	The details of the Performance Management report have yet to be discussed with the Portfolio Holder due to his annual leave.

2.	KEY CHALLENGES – REVENUES SECTION (UPDATED TO 31.3.2004)

2.1	Key Challenge 1 – Improve ‘in year’ collection rates that are currently in the lower quartiles

Action taken to improve in-year collection from1.4.03 to date included

- -	Introduction of payment via the internet (24 hours)

- a second direct debit date (16th) and a successful direct debit take up campaign which won the Council an award

- introduction of 24/7 facility in enabling payment over the phone.

ii)	Other initiatives

- All Bailiff and arrest warrant work has been outsourced to Rossendales Limited.

- The Council Tax and NNDR recovery timetable has been reviewed particularly the time period between documents being issued.

- Staffing resources targeted at Recovery work have been increased (via efficiency savings elsewhere).

- A new visiting initiative to inspect empty properties and confirm single person discounts is also picking up changes in circumstances quicker.

iii)	The Audit Team have recently audited Recovery processes including the Council’s anti-poverty strategy and has made recommendations in respect of special payment arrangements that the Revenues Manager is currently progressing.

- Further development of alternative payment options are progressing to timetable with the Post Office Payment Facility being successfully introduced on 01 April 2004.  Approximately 7,000 households now use this facility.

2.2	Key Challenge 2 – Improve staff morale and reduce overtime working

Staff morale has improved recently, due to improved communications, celebrating of success and reducing the requirement for overtime working as follows.

i)	The Head of Revenues and Benefits Services has clarified the Council’s position on externalisation i.e. in-house provision supported by a strategic partner to assist in re-engineering ‘front office’ services. However, staff turnover is a concern with many staff obtaining promotions in the Council’s new Foyer project and with Capita at the County Council and at their processing centre.

- Regrading of a Revenue Assistant to Revenue Officer (funded from overtime budget) which will help reduce overtime working.  However due to unavoidable work peaks some overtime will continue by staff who work extra hours out of choice.

- Communication has been improved with a public folder Calendar set up for leave and other key events.  Also a Revenues bulletin board to keep staff informed of current issues.  In addition monthly staff meetings have been chaired by a different member of staff every month to facilitate better staff involvement in the management of the Unit.

- Overtime has been used on targeted areas of outstanding work.

v)	The improved Collection rates detailed in 4 below have had a positive effect on staff morale.

However office refurbishment particularly in an effort to improve air quality in the office has been put on hold until ground floor office moves have been determined.

2.3	Key Challenge 3 – Improve IT systems

All staff have a new PC which has been a huge improvement, particularly the staff who had very old or problem PCs.

However downtime problems with Images and outlook and occasionally Academy still affect work performances.

The ‘now’ underpowered sun box server significantly affected the length of downtime at annual uprating/main billing and year-end.  However the new corporate server should resolve before 2005/06.

2.4	Key Challenge 4 – Improve forward planning

The Unit has developed an integrated approach to work scheduling and have translated it’s annual work plan in weekly schedules.

The Unit has set up an electronic calendar that staff input their holidays into and management input issues that will affect staff e.g. summons runs, committal courts, CTB1 completion etc.

3.	KEY CHALLENGES BENEFITS

3.1	Key Challenge 5 – Anti poverty strategy

The section introduced a mechanism for claimants to appeal against the maximum rate of recovery on overpayments: dependent on their health and financial circumstances despite affecting the overpayment recovery performance.  It has also introduced a pilot of home visits for new claims (mainly pensioners) and extended the provisions of the existing welfare visiting scheme to the old and infirm.  The section has also introduced an ‘evidence’ collection service in an effort to speed up the benefit determination process.  These initiatives have been incorporated into the service now providing core service requirements are being met i.e. resources allow.

3.2	Key Challenge 6 - Improve training/skills of all benefit staff

Successful bids to the Department of Work and Pensions Standards fund to fund cost of a team leader/trainer for 6 months and a team of 3 trainees for 2 years.  Also organised external training for Rent Officer referrals Tax Credits; Pension Credits and decision-making and Appeals.

3.3	Key Challenge 7 - Improve Staffing levels

Increased staffing levels (temporarily) in preparation for the increased work involved in new Tax Credits (funded by DWP grant).  Staffing levels have returned to original levels as initial impact of Tax Credits has been successfully managed.

3.4	Key Challenge 8 - Improve attendance

Piloted new sickness absence scheme within the Unit in recording absence and reasons for absence on Unit database.  Air conditioning installed and removal of redundant files and filing cabinets to improve space.  Humidifier overhauled and now operational.  Sickness absence trends has been increasing year on year have not increased in 203/04.

3.5	Key Challenge 9 - Improve teamwork

Policy of reallocating work if person absent for more than 5 days introduced. Staff protocol developed for moving staff within office.  Working environment improved by the introduction of air conditioning units.

Monthly staff meetings restarted and TIR teams enlarged to facilitate improved team working. Monthly meetings have improved communications and allowed more opportunity for consultation and sharing of ideas/information. Whilst larger teams have proven more difficult to facilitate team relationships have improved significantly.  Recent round of appraisals have given individual targets linked directly to team targets.  Performance culture being established.

3.6	Key Challenge 10 - Better communication

Staff representation in quarterly workshops considering priorities for next 3 months ahead.  Feedback on team and individual performance weekly to staff.  Feedback on workload levels on a daily basis.

3.7	Key Challenge 11 - Supporting other teams

Providing resource to Customer Services i.e. a liaison role with the customer.  Still providing cover for sickness, periods of high volume etc to the Revenues Reception team.  Permanent Assessment officer resource available for Customer Service assistants.

3.8	Key Challenge 12 - Improving take-up

Joint take-up campaign day for the elderly organised with Age Concern, DACE (Disability Association for Carlisle and Eden), Pension Service, CAB, BAC (4.11.03).  First joint campaign a success in informing pensioners re Pension Credit and changes as part of Pension Credit implementation and affect on Benefits entitlements. Each organisation has recorded its own statistics for the day and their will be a review meeting for late January/early February to compare all statistics, consider the outcomes of the day and decide whether to hold other, similar events.

Benefits staff interviewed 40 pensioners and identified 4 who were entitled to Benefit and not currently claiming.  National Council Tax Benefit Take-Up Campaign being supported through promotional material with non-benefit bills and circulation of publicity material.

3.9	Key Challenge 13 - Forward planning

Quarterly planning workshops for planning workload for 3 months ahead attended by representative of all benefit teams.

3.10	Key Challenges 14 - Preventing and detecting fraud

Pro-active Fraud Prevention and detection initiatives have been progressed i.e.

- targeting particular employment classes e.g. Employment Agencies

- targeting ex claimants who come off benefit without advising of reason

- Investigators PINS training (professionalism in security) now complete including Benefits Manager.

- Additional training in LTAH and W (living together as husband and wife) and prosecution file standards.

- Programme of data cleansing to maximise fraud data matching with other agencies.

Revised SAFE VF scheme implemented w.e.f. 1.4.04.  Improved data matching and high risk analysis intervention.

3.11	Key Challenges 15 - Enhancing technology

In the areas of implementation of

-	DIP.

-	Management Performance Data.

-	Upgrade of PCs.

-	Electronic interface system with Rent Service.

Looking to introduce

- Improvements to DIP (including upgraded server)

- Improvements to computer generated correspondence

- Remote access for lone and home workers

- Payment to landlords by BACs

- Electronic claim form.

A bid to the DWP Standards fund to pilot a home working scheme in 2004/05.

4.	PROGRESS ON BEST VALUE REVIEWS AND OTHER REVIEWS

4.1	Revenues & Benefits

The formal review of Revenues and Benefits commenced in the second half year of 2003/04.  A majority of the evidence in support of the 4C’s has been collected.  This informed the Best Value Review scope considered by O & S Committee in January 2003.  The next business plan update will look at Best Value Issues in more detail.

4.2	Concessionary Fares

The Concessionary Fares Scheme is continuing to improve in accordance with the Action Plan drawn up during a Best Value review of the Scheme during 2002. This year has seen the introduction of smartcard bus passes (NoWcards) with card readers to be fitted on buses during 2003/4. Additional improvements include the extension of the scheme to men aged 60-64 years, a free travel period over Xmas and New Year (funded by efficiency savings made as part of the Best Value review).

5.	PERFORMANCE INDICATORS UPDATE

The Unit is monitored against the following Corporate Plan Performance indicators.

| Reference | Performance Indicator | 2002-2003 Actual | 2002-2003 Target | 2003-2004 Actual | 2003-2004 Target | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| BV9 | in-year’ Council Tax Collections Levels | 96.3% | 96% | 97% | 96.6% | Best performance ever recorded |
| BV10 | in-year’ NNDR (Business Rates (Collection levels) | 98.6% | 98% | 99.2% | 98.5% | Best performance ever recorded will be well into top quartile |
| BV 12 | Sickness Absence | N/A | 11 | 13.29 | 9 |  |
| BV76 | Number of prosecutions & sanctions – reward target | £27,000 | £18,000 | £41,200 | £44,000 | Target too ambitious due to cases taking longer than anticipated to process to court |
| BV78A | Average time to process new claims | 48 | 46 | 50 | 35 | see note i) below |
| BV78B | Average time to process changes in circumstances | 16 | 16 | 21 | 8 | see note i) below |
| BV78C | Percentage of renewals processed on time | 72 | 75 | 50 | 82 | see note i) below |
| BV79A | Accuracy of processing | 97.8% | 97% | 96.8 | 97% | Slight reduction due to significant numbers of new staff in post |
| BV79B | ‘In year’ Overpayment recovery performance | 55.4% | 53% | 54.5 | 55% |  |

Notes on PIs:

i)	BV78A Average time to process new claims

BV78B Average time to process changes in circumstances

BV78C Percentage of renewals processed on time.

As indicated above due to technical problems on the introduction of communal garden charges (which are eligible for benefit) by CHA, the Council’s Housing Benefit system was corrupted.  The impact was that up to two months assessment work backlog built up as staff had to manually recalculate approximately 2,500 housing benefit assessments.  Whilst a robust action plan was put in place to clear the resulting backlog performance against targets for the first 2 quarters deteriorated significantly i.e.

Target		1.4 – 30.9.03		1.10.03 – 31.3.04

(top quartile)

BV78A	  35		          60		       35

BV78B	    8		          33          	         8

BV78C	  82%    	          37% 		       59%

As can be seen 2nd half performance to date has significantly improved.  Indicator BV 78C has been deleted from 1.4.2004.

- COPORATE ISSUES

6.1	Staffing/Human Resource

The Unit has been very proactive in piloting the staff appraisal scheme including training requirements and commenting and making suggestions at each stage of the pilot.

As noted in the body of the report staff turnover has been a problem in 2003/4 as staff have obtained promotions in the Foyer or moved to Capita at the County Council or their processing centre. Staff turnover is currently running at over 10% per annum. The effect of staff turnover has been mitigated to a certain extent by the introduction of  trainee Benefit Officer posts on the structure.

6.2	Delivery of Customer Contact Centre

The Unit has been very influential in progressing the Council’s Customer Contact vision and concept to preferred partner stage in the procurement process.  A majority of the staff in the new Foyer Centre have been recruited from Revenues and Benefits i.e. Manager, Project Officer, Team Leader and Receptionists reflecting the highly developed Customer Contact ethos in Revenues and Benefits.

6.3	CPA

The Unit was at the forefront of the CPA inspection process being subject to an independent CPA inspection by the BFI.  The BFI report which filtered into the overall CPA Inspection report contributed to the Council’s ‘Good’ ranking.

- FORWARD PLAN – KEY DECISIONS UPDATE

No froward plan issues currently outstanding affecting the Unit.

- BUDGET UPDATE

8.1	Summary Resources Statement

Revenues	Benefits 	Concessionary	Total

Fares

Number of employees	26.5	    48	 .5	75

Net Budget requirements	£822,630	£1,256,310	£618,620	£2,627,180

  - Budget & Expenditure to 30 November 2003

| Budget Line | Budget to month end | Actual at month end | Full Year Budget | Anticipated End of Year Variance + / - | Comments |
| --- | --- | --- | --- | --- | --- |
| Revenues | 822,630 | 709,846 | 822,630 | -112,000 | See note 1 |
| Benefits | 1,256,310 | 1,209,379 | 1,256,310 | -58,330 | See note 2 |
| Concessionary Fares | 618,620 | 586,990 | 618,620 | 31,630 | See note 3 |

Note 1:	Anticipated year end underspend of £112,000 due to significant staff turnover in 2003/4 (£68,000) as staff gain senior positions in the Council’s new Foyer project. Also positions with Capita at both the County Council and their new Benefits processing centre at Kingmoor Park. This £68,000 underspend will go towards meeting the corporate staff turnover budget savings requirement of £230,000.  The other £44,000 is mainly down to increased income due to increasing Court costs from £45 to £50.  This additional income has been taken into account in the 2004/05 income budgets.

Note 2: 	Anticipated year-end underspend of £58,330 is due to new staff taken on to resource the implications of LSVT on Benefits (funded by Government administration subsidy).  Due to difficulty in recruiting Benefit Assessment officers (and staff turnover) new staff where not in post until August 2003.

Note 3: 	Current underspend on Concessionary Fares of £31,630 due to income from Railcards not budgeted for (£6,500).  Also Concessionary Fares Project officer transferred to project officering the Customer Contact Centre initiative.

9.	RECOMMENDATION

Members are asked to note progress against Revenues & Benefits Business Plan in the period 1April to 31 March 2004 covering key developments and challenges update; progress on Best Value; achievement of performance against Best value indicators; and budget update.

Peter B Mason

HEAD OF REVENUES & BENEFIT SERVICES

Contact Name:	Peter B Mason		Ext:  7270

Revenues & Benefits

Carlisle

7 May 2004

PM/EL/RB2/04