CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 29 June 2006 |
| Title: | PROVISIONAL CAPITAL OUTTURN 2005/06 AND REVISED CAPITAL PROGRAMME 2006/07 |
| Report of: | The Director of Corporate Services |
| Report reference: | FS15/06 |

Summary:

The attached report:

- summarises the 2005/06 provisional out-turn for the Council’s Capital Programme;

- provides details of the revised Capital programme for 2006/07

and was considered by the Executive on 16 June 2006.

Recommendations:

Members are asked to consider the report.

| Contact Officer: | Jackie Grierson | Ext: | 7289 |
| --- | --- | --- | --- |

| REPORT TO EXECUTIVE |
| --- |
| PORTFOLIO AREA: FINANCE AND PERFORMANCE MANAGEMENT |
| Date of Meeting: | 16 June 2006 |
| Public |  |
| Key Decision: | Yes | Recorded in Forward Plan: | Yes |
| Inside Policy Framework |
| Title: | PROVISIONAL CAPITAL OUTTURN 2005/06 AND REVISED CAPITAL PROGRAMME 2006/07 |
| Report of: | DIRECTOR OF CORPORATE SERVICES |
| Report reference: | FS15/06 |

Summary:

The attached report:

- summarises the 2005/06 provisional out-turn for the Council’s Capital Programme;

- provides details of the revised Capital programme for 2006/07.

Recommendations:

The Executive is asked:

i	to note the 2005/06 out-turn, as detailed in Appendix 1;

ii	to agree the revised programme for 2006/07, as detailed in Appendix 2, for recommendation to Council on 18 July;

iii	to note that the information contained in this report is provisional and subject to the formal audit process.

iv	to approve the virement of £40,000 from the Civic Centre flood recovery budget previously approved at £235,000 to fund works at Bousteads Grassing in 2005/06 and also to approve the virement of £10,000 from the same budget in 2006/07 referred to in paras 2.4 and 2.5.

| Contact Officer: | Jackie Grierson | Ext: | 7289 |
| --- | --- | --- | --- |

CARLISLE CITY COUNCIL

To:	The Executive								FS15/06

16 June 2006

PROVISIONAL CAPITAL OUTTURN 2005/06

AND REVISED CAPITAL PROGRAMME 2006/07

- BACKGROUND INFORMATION AND OPTIONS

1.1	This report sets out the summarised financial out-turn for the Council’s Capital Programme as follows:

- the out-turn for individual schemes for 2005/06, summarised in Appendix 1

- the revised programme for 2006/07, summarised in Appendix 2

1.2	The report sets out the financial implications arising from the out-turn including the impact on capital resources for 2006/07.  Members should note that the information contained in this report is provisional and subject to the formal audit process. Any necessary changes required following the approval of the 2004/05 accounts will, if required, be reported verbally at the Executive meeting.

1.3	Please note that throughout this report the use of brackets represents a favourable variance i.e. either an underspend or additional income received.

- SUMMARY CAPITAL OUTTURN 2005/06

  - Appendix 1 details the out-turn for schemes included within the Council’s Capital Programme compared to the revised budget approved by Council in February 2006 and other necessary budget adjustments.   The list is analysed according to the level of progress on schemes and is summarised in the following table:

|  | 2005/06 Revised Budget £ | 2005/06 Actual £ | 2005/06 Variance as at 31/03/06 £ | Committed Expenditure Carried forward to 2006/07 £ | 2005/06 Revised Variance £ |
| --- | --- | --- | --- | --- | --- |
| Capital Programme | 10,810,600 | 7,005,957 | (3,804,643) | 3,821,600 | 16,957 |

  - The capital programme as per FS44/05 Budget Monitoring Report: April to December 2005 totalled £10,530,500. Further amendments to the programme are as follows:

£

Total Programme Per FS44/05					10,530,500

Gross up budgets for external funding received:

Recycling scheme							       33,100

IEG 										     150,000

Longtown MTI							       47,000

Back Lanes								       50,000

10,810,600

  - As at 31st  March 2006 actual expenditure was £7.0m against a revised budget for the year of £10.8m. The explanations for the variance of £3.8m (36%) at the financial year end can be found within Appendix 1; the majority of these schemes will be completed during 2006/07.

  - Included within the provisional out-turn figures is £40,000 relating to expenditure incurred at Bousteads Grassing for improvement work. Members are requested to approve the virement of this scheme from the Civic Centre Flood Recovery budget approved at £235,000. This will leave £195,000 being carried forward to 2006/07 to carry out other flood recovery work (refer to paragraph 2.5 below).

  - The Director of Corporate Services has delegated powers to approve carry forwards where the expenditure is committed and the use of the resource is restricted to the purpose the budget was originally provided for. Carry forwards of £2.4m have already been approved by the Executive in November 2005. Appendix 1 details brief reasons for the carry forward requests on each individual scheme, and the Director of Corporate Services is satisfied that budgets of £3.8m should be carried forward to 2006/07 to enable the schemes to be completed, subject to formal approval by Council.  Members are requested to approve the virement of the  £195,000 carry forward request for the Civic Centre which includes £10,800 for Botcherby Community Centre to fund other betterment work not covered by either Bellwin or Insurance.

2.6      While this report does indicate a significant degree of slippage into 2006/07, even     allowing for the carry forward of £2.4m referred to above, it should be noted that the regular capital budget monitoring summaries have consistently indicated a considerable level of underspend that would entail a carry forward request.

2.7      As a means of tackling this issue, the Capital Projects Board  will be strengthened and will be charged with monitoring issues of accurate budget profiling and spend, designating a responsible officer for each project and generally attempting to tackle the issue of capital underspending/slippage that has been a consistent feature of capital outturn in the authority for a number of years.

- EXPLANATION OF VARIANCES

  - The net overspend for 2005/06 of £16,957 after allowing for the committed expenditure carry forward as detailed in Appendix 1 can be summarised as follows:

| Scheme | £ | Note |
| --- | --- | --- |
| Street Lighting | 7,168 | 1 |
| Recycling | 10,826 | 1 |
| Miscellaneous items | (969) | 2 |
| Total | 16,957 |  |

Notes:

- These overspends are due to expected capital grants/contributions for these schemes which will now not be received.

- As detailed in Appendix 1

- FINANCING OF CAPITAL PROGRAMME 2005/06

4.1	Utilisation of resources to fund the Capital Programme in the light of the out-turn is	provisionally estimated as follows:

|  | Revised Budget £ | Provisional Out-turn £ |
| --- | --- | --- |
| Capital Programme expenditure in year | 10,810,600 | 7,005,957 |
| Financed By: |  |  |
| Capital Receipts (note 1) | 4,699,600 | 4,025,371 |
| Renewals Reserve | 1,963,000 | 855,343 |
| Capital Grants (note 2) | 2,580,800 | 1,677,465 |
| Borrowing (supported by RSG) (note 3) | 1,109,700 | 0 |
| Specified Capital Grant (DFG) | 252,400 | 261,219 |
| Contributions from other bodies | 205,100 | 186,559 |
| Total Financing | 10,810,600 | 7,005,597 |

Notes:

- Usable capital receipts carried forward from 2004/05 and those generated during the year amount to £15,921,638 compared to the revised estimate figure of £6,558,000, an increase of £9,363,638. This increase is mainly due to a change in accounting treatment whereby the PRTB receipts are now usable when receivable rather than when physically received so include the receipt received on 28th April 2006 and also due to a reduced call on capital receipts in previous years due to slippage. Of the total sum available, £4,025,371 has been used to fund the General Fund Capital Programme in 2005/06, with the balance (£11,896,267) being carried forward to 2006/07.

- The shortfall on capital grants applied relates to the fact that on certain schemes, principally the Housing Strategy (funded from the special £1.5m ODPM grant), there are still some grants to claim and/or utilise.

3.	Given the current level of capital receipts, it is not proposed to utilise the supported borrowing allocation in 2005/06 of £1.109,700 to finance any capital expenditure incurred in the year. This will result in a revenue saving (in respect of MRP) in 2006/07 of approximately £44,400 with further (though gradually reducing) savings in future years. The only disadvantage would be that £1.11m of capital receipts will have been utilised for capital financing purposes in 2005/06 and therefore cannot be called upon as part of any future capital programme. Given the Council’s current level of unapplied capital receipts, it is felt that for the time being this is not a significant disadvantage.  The Council always has the option of borrowing this sum in a future years if circumstances so warrant albeit it would then be classed as unsupported borrowing.

- CAPITAL PROGRAMME 2006/07

5.1	The revised Capital Programme for 2006/07 totalling £13,153,400 is detailed in Appendix 2. This is based upon the programme as agreed by Council in February 2006 of £7,657,600, the carry forwards already approved by the Executive in November 2005 of £2,464,200 and the commitments brought forward from 2005/06 as identified above of £3,821,600. The programme has been adjusted for the transfer of £1,000,000 to the Asset Investment Reserve, the delay of the Desktop Replacement scheme by one year of £120,000 and the earlier use of the Cremator budget from 2008/09 amounting to £330,000. Members should be aware that the Longtown Market Town Initiative commenced during 2005/06 and will continue into 2007/08. This scheme is a combination of revenue and capital funding, however the precise split is not yet known and will be reported to a future meeting of the Executive.

5.2	It is suggested that the revised programme be financed as follows:

|  | Original Budget 2006/07 £ | Revised Budget 2006/07 £ |
| --- | --- | --- |
| Original Programme | 7,657,600 | 7,657,600 |
| Add: Carried forward from 2005/06 | 2,464,200 | 6,285,800 |
| Add: Cremator budget brought forward from 2008/09 | 0 | 330,000 |
| Less: transfers to earmarked reserve | (1,000,000) | (1,000,000) |
| Less: Desktop Replacement scheme | 0 | (120,000) |
| Total Expenditure to be financed | 9,121,800 | 13,153,400 |
| Financed by: |  |  |
| Capital grant (Regional Housing Pot) (note 1) | 1,503,000 | 1,503,000 |
| Specified Capital Grants (DFG) | 205,000 | 205,000 |
| Capital Receipts (note 2) | 6,791,200 | 9,301,300 |
| Capital Grants | 330,000 | 724,800 |
| Renewals Reserve | 292,600 | 1,397,800 |
| Revenue Contributions | 0 | 21,500 |
| Total Financing | 9,121,800 | 13,153,400 |

Notes:

1.	In previous years borrowing has been assumed at the level at which the ongoing cost was estimated to be supported by the Revenue Support Grant settlement. However this has been removed from the RSG and has been replaced by a separate funding stream in the form of a Housing Capital Allocation. This capital allocation funded from the Regional Housing Pot (RHP) is paid as a capital grant and totals £1.503m for 2006/07.

2.	The PRTB (Preserved Right to Buy) sharing agreement with Carlisle Housing Association generated a receipt of £3,972,104 relating to PRTB sales in 2005/06. This sum was received on 28 April 2006. The agreement will continue for the first 15 years of the contract and substantial receipts are expected over this period. These receipts will be used to fund initiatives that will benefit the delivery of the sustainable community.

- CONSULTATION

6.1  	Consultation to Date.

The Strategic Financial Planning Group and the Senior Management Team have considered the report and their comments have been incorporated into the report.

  - Consultation proposed.

Corporate Resources Overview and Scrutiny Committee will consider the report on 29 June 2006.

- RECOMMENDATIONS

7.1	The Executive is asked:

i	to agree the 2005/06 out-turn, as detailed in Appendix 1;

ii	to agree the revised programme for 2006/07, as detailed in Appendix 2, subject to approval by full Council;

iii	to note that the information contained in this report is provisional and subject to the formal audit process.

iv	to approve the virement of £40,000 from the Civic Centre flood recovery budget previously approved at £235,000 to fund works at Bousteads Grassing and also to approve the carry forward request of the balance of £195,000 referred to in paras 2.4 and 2.5.

8.	REASONS FOR RECOMMENDATIONS

As stated above.

9.	IMPLICATIONS

- Staffing/Resources – Not applicable

- Financial – contained within the main body of the report.

- Legal – Not applicable

- Corporate – The Strategic Financial Planning Group and the Senior Management Team have considered this report and their comments have been incorporated.

- Risk Management – Individual capital schemes have different risks attached.

- Equality Issues – Not applicable

- Environmental – Not applicable

- Crime and Disorder – Not applicable

ANGELA BROWN

Director of Corporate Services

Contact Officer:	Jackie Grierson				Ext:	7289