COMMUNITY OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |  |
| --- | --- |
| Date of Meeting: | 31st August 2006 |
| Title: | LATE NIGHT SHOPPING : PROGRESS REPORT |
| Report of: | DIRECTOR OF DEVELOPMENT SERVICES |
| Report reference: | DS.68/06 |

Summary:

The report provides an update on the progress achieved with the City’s Late Night Shopping Initiative.

Recommendations:

The report be noted.

| Contact Officer: | John Bell | Ext: | 7160 |
| --- | --- | --- | --- |

DS.68/06

LATE NIGHT SHOPPING : PROGRESS REPORT

1.0	BACKGROUND

1.1	Late night shopping (Thursday evening – 7.00 pm opening) was successfully launched on 1st June.  It was advertised and promoted as set out in the proposals within the report to O&S Committee on 20th April 2006.

2.0	PROGRESS

2.1	Footfall:	The exercise has now been running for two months and it is pleasing to report that 1,131 (+47%) extra customers have been attracted to the Lanes (for Lanes read city centre) between 5.00 pm and 7.00 pm during the period 1st June – 27th July.

The detailed breakdown of the week on week growth is shown in Appendix 1.

2.2	Participants:  57 retailers (list of names shown in Appendix 2) within the city centre are participating in the Late Night Shopping promotion along with numerous cafes and restaurants.  The indications are that support for the exercise remains strong with certain retailers already considering an even later finish (8.00 pm).

2.3	The Council’s Tourist Information Centre has remained open until 7.00 pm from the commencement of the exercise and has had an additional 30-40 customers each Thursday evening between 5.30 – 7.00 pm.

2.4	Tullie House too is now open until 8.00 pm (commenced 13th July) on Thursday evenings and will continue to do so until 31st August.  Very few people however have been attracted so far.

2.5	Entertainment:  The City Council has also organised entertainment in the city centre to enhance the establishment of late night shopping.  A list of entertainers used is reproduced as Appendix 3.

2.6	Budget:  A budget of £15,000 was provided for the establishment and promotion of Late Night Shopping.  A breakdown of the expenditure incurred is shown as Appendix 4.  The activity undertaken is still within budget with a small balance remaining which will be used for further joint promotional activity with the city centre marketing group to boost awareness of the late night shopping initiative when required.

2.7	Ongoing Promotion:  The banners and car park signs within the city centre provide an ongoing awareness of late night shopping.  A major boost has also been given to the exercise with the implementation of the City’s ’Summer in the City’ promotion which involved the distribution of 400,000 flyers to generate day and staying visitors for the City.  Late night shopping features in this initiative as another incentive to visit Carlisle.  This joint initiative is supported by the Lanes, Debenhams, Virgin Trains and Settle-Carlisle Railway Development Company.

3.0	SUMMARY

3.1	The late night shopping promotion has been successfully established.  It has substantial support from city centre businesses and the promotional activity has succeeded in creating significant awareness, which is resulting in week on week growth being achieved.  Monitoring will continue, but at this point in time, there is every confidence that the late night shopping initiative will be sustained, and run successfully, up and into the Christmas late night Thursdays which was the main objective for 2006.  The whole exercise can then follow on through 2007 with additional publicity and promotional activity in early January to ensure the awareness and support is maintained.

APPENDIX 1

FOOTFALL

1.0	OVERALL

1st June	27th July	Increase

Increase 5.00 – 7.00 pm		1,638		2,258		+ 620 (+38%)

6.00 pm to 7.00 pm			   762		1,273		+ 511 (+67%)

_____		_____		_____

2,400		3,531		+ 1131 (+47%)

2.0	WEEK ON WEEK GROWTH

5.00 pm to 7.00pm

8th June					+ 220

15th June					-  449 (England World Cup Match)

22nd June					+ 246

29th June					+ 133

6th July					+ 156

13th July					+ 816

20th July					-    67

27th July					+   76

_____

+1,131

APPENDIX 4

PARTICIPATING STORES

| THE LANES |  |  | CITY CENTRE STORES |
| --- | --- | --- | --- |
| Activmobile | JD Sports | Additions |  |
| Ann Summers | JJB Sports | Body Shop |  |
| Barratts | KFC | House of Fraser |  |
| Bay Trading | Carlisle Library | La Senza |  |
| Birthdays | Millies Cookies | Mark 1 |  |
| Bodycare | Miss Selfridge | Marks & Spencer |  |
| Bon Appetit | Monsoon | New Look |  |
| Car Phone Warehouse | Officers’ Club | Tesco |  |
| Claire’s Accessories | Original Shoe | TK Maxx |  |
| Clarks | Peter Jackson | Top Shop |  |
| Crème | Phones 4 U | Wilkinsons |  |
| Debenhams | Qube | Woolworths |  |
| Dorothy Perkins | Quiz |  |  |
| Edge Lifewear | Republic/Schuh |  |  |
| Ernest Jones | Scotts |  |  |
| Faith Shoes | Superdrug |  |  |
| Fat Face | T Mobile |  |  |
| FQ | The Shoe Den |  |  |
| Game | The Watch Hospital |  |  |
| Gap | Toni & Guy |  |  |
| Greggs | Virgin |  |  |
| H&M | Watch International |  |  |
| HMV |  |  |  |

APPENDIX 3

ENTERTAINMENT

1st June	Esk Valley Jazz Band

8th June	William Howard School Band/Stiltwalker

15th June	William Howard School Band/Stiltwalker

22nd June	Esk Valley Jazz Band

29th June	Gentlemen of Jazz

6th July	Esk Valley Jazz Band

13th July	Gentlemen of Jazz

APPENDIX 4

EXPENDITURE BREAKDOWN

£

Entertainment			2,500

Advertising Promotion

Advertising			3,500

Flyers				   800

Banners/Car Park Sign	1,300

Production/Artwork		1,500

Summer Campaign		3,000

_____

12,600

 The Lanes footfall is monitored by ‘electronic eyes’ and used as a reasonable indicative measure for the city centre as a whole.