Audit COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 26th September 2008 |
| Title: | Corporate Risk Management |
| Report of: | Deputy Chief Executive |
| Report reference: | CE 24/08 |

Summary: The purpose of this report is to give members of the Audit Committee an update on the Council’s Risk Register.

Recommendations:

The Committee is asked to note the Corporate Risk Register as an indication of the continuing commitment to sound governance arrangements for corporate risk management.

| Contact Officer: | Carolyn Mitchell | Ext: | 7306 |
| --- | --- | --- | --- |

CITY OF CARLISLE

To:	Audit Committee

Date:	26th September 2008

1. Background

In accordance with the Council’s Risk Management Policy, the draft Corporate Risk Register is submitted to Corporate Resources Overview and Scrutiny Committee (CROS) for consideration on a quarterly basis.

This Report contains the Risk Register (see appendix 1) that was presented to CROS on 24th July 2008 and is the one to which the CROS minutes from July 2008 refer. Subsequent amendments and scores, discussed and agreed by the Senior Management Team and Corporate Risk Management Group, will be presented to CROS in October 2008.

2. Comments on the Corporate Risk Register

Members will note that any change in the scored status of a risk is shown by a symbol in the movement column.

Current Action Status / Control Strategy sections are addressed and the scoring of risks amended accordingly and revisions consolidated on a quarterly basis.

- Recommendations

The Committee is asked to note the Corporate Risk Register as an indication of the continuing commitment to sound governance arrangements for corporate risk management.

# Appendix 1 – Corporate Risk Register Updated 15th July 2008

# Note: amendments in last quarter marked in red italics (or italics only on the printed version).

| Ref | Risk Description | Impact | Likeli-hood | Risk Score | Move-ment | Current Action Status/Control Strategy | Responsible Officer & date last updated |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Pay and Workforce Strategy Failure in the implementation of PWS financial impact impact on staff including Low morale/demotivation Retention difficulties Increased call on resources Impact on business/productivity Failure to implement succession planning | 4 | 3 | 12 | = | Implementation Plan and Programme determined and published Prince 2 methodology applied Regular Staff updates via Management Briefing and newsletters Continual monitoring of progress by Project Manager overseen by Project Board Project developed and delivered in partnership with Unions. Job Evaluation Appeal panels are taking place and should be complete by early August. | Deputy Chief Executive 15/07/08 |
| 2 | Medium Term financial planning and maintaining asset values; failure leading to:- - risk of systems and procedures failing to address MTFP objectives - risk that expenditure not linked to key objectives and priorities - fails to be forward looking and programmed - failure to deliver savings assumptions approved as part of the budget could result in significant overspends - lack of corporate ownership - failure to achieve balanced budget through the budgetary process - failure to match future commitments and aspirations compared to funding available - maintaining asset values | 4 | 3 | 12 |  | The MTFP and Capital Strategy were approved by Council on 17th July 2007, and an update for the next three year period is currently underway. The MTFP and Capital Strategy are reviewed regularly in the light of current pressures arising and this has been carried out throughout the 2008/09 to 2010/11 budget process. As predicted the RSG settlement, whilst not being zero in cash terms for this Council, was well below inflation. The increase was 1% in 2008/09, 0.5% 2009/10 and 0.5%2010/11, against general inflation of 2.8% being included in the 2008/09 estimates. The PWS implications, shortfalls in income projections and budget pressures in a number of areas are set out in the 2008/09 three year Budget. There is a specific risk in failing to achieve the identified savings to offset the spending pressure identified and SMT are monitoring this aspect prior to reporting back to members. Clear strategy for linking resources to corporate priorities is to be developed. The work of the Capital Projects Group and Corporate Programme Boards will support the improvements to financial and performance improvements regarding the capital programme. | Director of Corporate Services 11/06/08 |
| 3 | Failure to develop Shared Services and /or deliver the Council’s internal efficiency agenda, specifically: Promised savings of 3% (shared services) 5% (internal efficiency reviews) not realised; Partners not engaging to an equal extent; Programme of service improvements and efficiency reviews not completed within financial timescales; Governance arrangements not responsive enough to allow changes to evolve / amendments to be made. | 3 | 3 | 9 | = | A Shared Services Strategy was agreed by the Council in March 2007. This clearly articulates that no shared services arrangement will be entered into by the City Council unless there are clear benefits for the Council that can be demonstrated in a full business case (including meeting the efficiency requirements). An internal Shared Services and Efficiencies Working group has been formulated to oversee shared services and improvement/efficiencies reviews within the Council. This officer / member Group operates with clear terms of reference when assessing progress of shared services and efficiency reviews initiatives taking place. Corporate Services has set up a dedicated team to oversee the Council’s shared services and efficiencies agenda and provide progress reports to SMT, SPG and Members. Also, to work closely with Aperia (consultants originally appointed by CLASB to oversee the Business Architecture Project for Cumbria i.e. analysing the Council’s work processes and comparing these with other internal processes and with other Cumbrian authorities). Aperia have identified 8 areas where service improvements may be delivered and these are currently being investigated / incorporated into reviews which are already in progress (key area being Customer Services). The draft Cumbria-wide Shared Service Strategy Is out for consultation. The Council has had and will continue to have through the consultation process, significant input into the production of this document, ensuring its shared services disciplines are set out in the Strategy. Whilst the initiatives detailed above are designed to deliver the Council’s Shared Services / Efficiencies Agenda, the timescale (3 years) and the number and complexity of the reviews and the level of savings required suggest that the current risk score is still valid. | Director of Corporate Services 10/06/08 |
| 4 | Carlisle Renaissance There is a strategic risk associated with withdrawal of the support of key partners at a sub-regional, regional and national level, loss of momentum and resultant loss of confidence within the local resident and business community. Capacity and the availability of resources are critical to this as well as effective engagement and communication mechanisms. Failure will be expressed in Reputational – failure to achieve stated objectives Financial – failure to secure and utilise funds appropriately Delivery – failure to manage a programme of growing scale and diversity. | 4 | 2 | 8 | = | Consultants have been engaged to progress options for a Delivery Mechanism for Carlisle Renaissance to manage the delivery of development and infrastructure projects. A Detailed Application has been submitted for approval by the NWDA. This application will secure funding for additional development and project management capacity. Following discussions between Carlisle City Council and NWDA Chief Executive and Chairman, agreement has been reached on the establishment of a private sector led leadership group to drive forward Carlisle Renaissance. A Chair of the Board has been appointed, along with twelve members of the Board, including five private-sector representatives. Public sector representation includes elected members from City and County Councils, the Northwest development Agency and Cumbria Vision. A Programme Director has also been appointed and additional team members will be recruited during 2008. The target date for the formal establishment of this new mechanism and Board is July 2008. Progress will be monitored through the Corporate Resources Overview and Scrutiny Committee. | Director Carlisle Re- naissance 17/06/08 |
| 5 | Carlisle Northern Development Route | 4 | 2 | 8 | = | The County Council selected a preferred bidder, Connect CNDR (a brand name for Balfour Beatty), on the 22 November. Final negotiations are expected to be completed by end March 2008 with a view to awarding the contract in early June 2008. Construction, which is expected to take 2 years would commence in September 2008. In addition to the construction of the CNDR the 30 year concession includes the management and maintenance of:- A7 (Junction 44 to Scottish Border) A689 (Junction 44 to Brampton Bypass) A595 from Newby West, south A6071 (Brampton Bypass to Scottish Border. The completion of the CNDR would reduce pollution on Scotland Road to below the threshold level. | Director of Community Services 18/06/08 No change |
| 6 | Financial Management Information provided must be accurate, robust & timely to enable Budget Holders to manage, failure leading to:- - poor management decisions - loss of credibility in information provided -Service Heads fail to focus on key objectives - Not linked to performance management - failure to adopt best practice and achieve value for money - specific risks identified associated with Contractor Plus system | 3 | 2 | 6 | = | The Council’s Financial Management arrangements have been assessed as adequate in the Audit Commission’s Use of Resources judgement, and also by the independent review of financial management conducted by IPF. Action has been taken on all areas of improvements required. The updated Use of Resources judgement in 2007 maintained the assessment at adequate. An action plan is being developed to tackle the areas which need improving to raise the score. Work is ongoing with the Policy and Performance and Finance Teams to further improve linkages between use of resources and performance, and this is set out in the Direction of Travel Action Plan. All of the posts in the new financial services structure approved by the Executive at the end of September last year have now been appointed to. This will increase capacity in the service and deliver further improvements. A specific risk remains to the Council from the existing system utilised by the Community Services Directorate for ex DSO work and the ability to easily reconcile the system to the Councils core financial management system. A budget has been allocated and work is progressing to replace the Community Services system. A significant financial training programme has now been launched to improve the financial management standards throughout the authority. | Director of Corporate Services 11/06/08 No change |
| 7 | Failure to focus clear Corporate Priorities leading to:- - resources wasted on lesser priorities - key objectives not achieved | 3 | 2 | 6 | = | New Corporate Priorities now determined :- Greener , Cleaner and Safer The Learning City Carlisle Renaissance Further work is in place to ensure that these are the drivers for focussing activity and expenditure. Refresh of Corporate Plan scheduled for April 2008. | Town Clerk & Chief Executive 17/06/08 No change |
| 8 | Protection of IT E-records and data and hard copy information:- - failure will have business/financial impact - inability to meet legal/other obligation - impact on resources / cost of re-establishment | 3 | 2 | 6 | = | New work as part of the shared service with Allerdale will, when implemented, result in a more robust and resilient service. | Director of Corporate Services 17/06/08 |
| 9 | Failure to implement an effective IT Strategy:- - failure to maximise benefits of e-business and e-procurement - increased security risks | 3 | 2 | 6 | = | The Information Systems Group (ISG) is currently working upon revised strategy for 2008/2011 which will be considered by Corporate Resources Overview and Scrutiny Committee in due course. A new security policy is in development to deal with increased security risks. | Director of Corporate Services 17/06/08 No change |
| 10 | Performance Management challenges Failure to embed performance management in the culture of the Council at all levels - inefficient and ineffective management - misdirected/wasted resources - failure to meet target/continuous improvement | 3 | 2 | 6 | = | Quarterly Performance conferences now commenced to monitor and address performance corporately. Performance Management included in Directorate’s Service Plans. Performance Management Framework was published March 2007. New Performance Management system (Covalent) is now live and training is being delivered to officers and members . | Deputy Chief Executive 15/07/08 |
| 11 | Health & Safety management and systems failure could lead to:- - exposure to legal action - financial impact of failing to ensure recovery of all - reputational impact on Council - increased exposure of staff to H&S risks - creation of image of non-proactive employer - lack of understanding of Health and Safety Manager’s role | 3 | 2 | 6 | = | Council’ Health and Safety Policy fully adopted Qualified H&S Manager employed in a corporate role Clear H&S management systems installed across the Council Health and Safety action plan regularly updated and ongoing auditing of current practices Developing local Performance Indicators which will be reported on in the Council’s performance management reports to Corporate Resources Overview & Scrutiny Committee Continuing training of staff as appropriate including mandatory training for newly appointed employees Role of Health and safety to be included in Service plans H&S strategy under development. | Deputy Chief Executive 17/06/08 No change |
| 12 | Financial Reporting following comments of audit Commission on standard of financial reporting- Failure will lead -reputational damage -have an impact on overall CPA assessment -poor relationship with District Audit | 3 | 2 | 6 | = | The Audit Commission judged the Council’s financial reporting standard for 2006/07 as part of the Use of Resources judgement to be inadequate, albeit improvements were recognised. The 2007/08 Accounts will be submitted to Council on 26th June following consideration by the Audit Committee and Executive on 23rd June. The area of greatest risk for improving the financial reporting standards is in the increasing complexity of the accounts under the move to International Financial Reporting Standards, which increases the risk of error in the accounts. | Director of Corporate Services 11/06/08 No change |
| 13 | Partnerships (including framework agreement & collaborative working arrangements) Existing partnerships and New and proposed partnerships , failure to ensure compliance with existing arrangements leading to:- - failure to meet stated objectives - reputational and financial impact - onerous terms and conditions, and inadequate exit strategy - increased exposure to risk - major review of compliance with partnership agreements or evidence of agreements not undertaken on a regular or structured basis | 3 | 2 | 6 | = | The revised draft Partnership policy has been considered by the Executive and Corporate Resources Overview and Scrutiny Committee and will be submitted for approval to the next Council meeting. The Use of Resources judgement has highlighted that the Council needs to improve its financial performance of partnerships including a link to outputs and ensure the results are shared with partners and acted upon. It has also highlighted that appropriate governance arrangements should be in place for all significant partnerships. The new policy sets out responsibilities in this respect. Corporate Services Efficiency and Procurement team is responsible for the monitoring arrangements, this includes the update of the central register, completion of annual reviews of all significant partnerships, annual reports to members and quarterly progress reports to SMT. One to one assistance is given to officers when setting up new partnerships. Senior Management Team will ensure that their individual risks from partnership working arrangements should be included in Operational Risk Registers. | Director of Corporate Services 11/06/08 No change |
| 14 | Flooding | 3 | 2 | 6 | = | The flood defence project on the Eden is now substantially completed and will provide increased protection for properties in the Warwick Road area from river flooding. The flood defence project for the river Caldew has achieved all the approvals and has commenced. United Utilities start work in April 2008 on major sewerage improvements in the Willowholme area. The "Making Space for Water Group" meet on a regular basis and flood response arrangements are reviewed regularly to provide an integrated response to incidents. | Director of Community Services 18/06/08 |
| 15 | Failure to implement Code of Corporate Governance failure to meet legal duty failure to adopt sound, consistent, transparent and auditable processes | 4 | 1 | 4 | = | The Code of Corporate Governance Action Plan is updated and reported to the Audit Committee quarterly. The Code itself has recently been updated following guidance received from CIPFA / SOLACE. This required a fundamental review of our current arrangements and will be implemented in time for the 2007/8 accounts. The Code of Corporate Governance and the annual Governance statement will be submitted for consideration by the Audit Committee on 23rd June. | Director Corporate Services 17/06/08 |
|  | Vacancy Management |  |  |  |  | Risks associated with this activity will be considered and included in next update of this Risk Register |  |
|  | Efficiency Savings |  |  |  |  | Risks associated with this activity will be considered and included in next update of this Risk Register |  |

Appendix 2 - Corporate Risk Register 15th July 2008

# Quality Control Document (changes since March 2008)

For consideration by Corporate Overview and Resources Committee 24th July 2008

| REF NO | BRIEF DESCRIPTION | SCORE | COMMENTS |
| --- | --- | --- | --- |
| 1 | Pay and Workforce Strategy | 12 | Control strategy/action status updated |
| 2 | Medium term financial planning | 12 | Risk increased. Control strategy/action status updated |
| 3 | Shared Services | 9 | Control strategy/action status updated |
| 4 | Carlisle Renaissance | 8 | Control strategy/action status updated |
| 5 | Carlisle Northern Development Route | 8 | No change |
| 6 | Financial Management Information | 6 | Control strategy/action status updated |
| 7 | Corporate Priorities | 6 | No change |
| 8 | Protecting IT records | 6 | Control strategy/action status updated |
| 9 | Implement Effective IT Strategy | 6 | No change |
| 10 | Performance Management | 6 | Control strategy/action status updated |
| 11 | Health and Safety | 6 | No change |
| 12 | Financial Reporting | 6 | No change |
| 13 | Partnerships | 6 | No change |
| 14 | Corporate Governance | 4 | Control strategy/action status updated |
| 15 | Flooding | 6 | Control strategy/action status updated |
|  | Vacancy management |  | New – for further consideration |
|  | Efficiency savings |  | New – for further consideration |