CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 19 February 2004 |
| Title: | BEST VALUE PERFORMANCE INDICATORS - SICKNESS ABSENCE AND ILL HEALTH RETIREMENTS |
| Report of: | Head of Member Support & Employee Services |
| Report reference: | ME 1/04 |

Summary:

This report summarises progress against the Sickness Absence Action Plan, as requested by this Committee at their meeting on 4 September 2003.

Recommendations:	 Members to note the report

| Contact Officer: | David Williams | Ext: | 7082 |
| --- | --- | --- | --- |

- Introduction

The Best Value performance indicator for sickness absence is one where the Council is in the lowest quartile, and one where we have drawn up an action plan to address this.  The plan was drawn up in the latter part of 2002, and Members received a progress report at their meetings of the Corporate Resources Overview and Scrutiny Committee on 10 April 2003 and 4 September 2003. Members asked for a further update for their meeting on 19 February 2004.

- Sickness Absence performance

The table below shows Carlisle City Council’s performance over the last three years, which, as can be seen, has been getting worse.

| 2000/1 | An average of 12.2 days per employee |
| --- | --- |
| 2001/2 | An average of 12.9 days per employee |
| 2002/3 | An average of 13.1 days per employee |

Our target is 8.2 days per year by 2004/5, and the target for 2003/4 is 9 days.

We now have statistics available for three of the quarters of 2003/4. They show a cumulative average of 9.62 days per employee.

Care has to be taken when extrapolating this figure to that for a full year, as absence is unpredictable, but it suggests that by the end of the year we will have at least managed to arrest the deterioration in performance. Our current year-end estimate is 12.83.

This would mean however, that we shall fall a long way short of our target.

This is disappointing and hardly reflects the attention that has been devoted to this area and the priority accorded to it. Nor does it reflect the excellent progress that has been made with the Action Plan (see 3 below). Clearly there is going to be a delay before the effect of our actions ‘kicks-in’.

It suggests also with the benefit of hindsight, that we may have been overly ambitious with our targets, prompted it must be said by the national Performance Indicator. Examination of other authorities that are struggling with similar levels of absence as ourselves, reveals that more realistic and less-demanding targets may be more useful and certainly less demoralising, and that even small steps in the right direction should be viewed as progress.

We may wish to lower our milestone targets in recognition of this.

There will be no let up in our efforts to address this problem and bids have been submitted to Members to invest further resources in support of this important work.

During the last quarter we have focussed a good deal of attention upon addressing on-going long term cases of sickness absence. Our analysis indicates that although these are relatively few in number, such cases account in aggregate for around 60% of our overall absence figure.

Dealing with long term sickness problems is time consuming and complex, particularly as we would want to continue to take the position of a caring and compassionate employer. However, we are confident that our efforts will begin to impact positively upon our statistics in the near future.

- Progress against the Action Plan

A copy of the original action plan is shown as Appendix 1 with the final column  outlining the progress achieved.

As can be seen, there has been substantial progress since we last reported and most of our targets in the plan have now been met, albeit later than originally anticipated (for reasons discussed and accepted at earlier meetings of this committee).

I believe that the groundwork is now in place for these actions to begin to impact noticeably upon the statistics so that we should be able to record further improvement over the next year and thereafter.

- Ill health retirements performance.

The table below shows Carlisle City Council performance against this indicator.

| Year | % ill health retirements | Actual Number | Target |
| --- | --- | --- | --- |
| 2000/1 | 0.6% | 6 | - |
| 2001/2 | 1.17% | 13 | 0.65% |
| 2002/3 | 0.52% | 5 | 1% |
| 2003/4 | 0.71% | 5 | 1% |
| 2004/5 | - | - | 0.35% |

There were 5 health early retirements during the year to date. We estimate that a further two are possible before the end of the reporting period.

The small numbers, and the lengthy process involved mean that ill health retirement statistics can fluctuate greatly when looked at over a short space of time.

A previous report (ME 02/03 – April 2003) identified the limited measures available to influence performance in this area, and we continue with this approach.

- Recommendation

Members to note the report and consider any adaptations to the Action Plan.

Appendix 1:	 Sickness Action Plan update at 10 February 2004

| Action | Timescale | Target | Progress at 10 February 2004 |
| --- | --- | --- | --- |
| Review Absence Management policy & procedures in the light of outcomes from management training. | Review by 31/5/03 Consult unions by 30/6/03 Single policy by 31/7/03 | Revised and updated single absence policy & procedure fully implemented and operational. | We have consulted extensively on a single revised policy and procedure document. Subject to final endorsement by trade unions at the CJC on 11 February a new Attendance Management Policy will become operational. Presentations at Management Briefing will facilitate communication of this to all staff. |
| As part of the above review to formalise the use, reporting and monitoring of Return to Work Interviews. | Audit usage by 31/5/03. Embedded as normal practice by 30/6/03 | Consistent applications by managers of return to work interviews as part of overall policy. | Managers are holding such interviews as a matter of routine. Personnel staff are monitoring similarly. |
| Continue to provide training for managers in the implementation of the Absence Policy & Procedures (84 trained to date) and to make the training a compulsory element of management training. | 95% managers trained by 31/12/02 Remainder by 31/5/03. New MDP in place by 12/9/03 | Fully trained and competent managers, both existing and newly appointed. | All managers are now trained in the ‘old’ policy and procedures. A new Management Development Programme (MDP) was launched across the authority in October 2003. Refresher workshops will be held within the MDP to update all managers in the new policy during 2004. Engagement with the MDP is compulsory for all supervisors and managers, and training in Attendance Management is also a compulsory component within it. |
| To identify named managers in each Business Unit who will be directly responsible for monitoring absence management within the Unit. | By 16/5/03 | To have a clear list of managers responsible for monitoring and managing absence within each Business Unit | Business Unit Heads have taken full responsibility for addressing the problem, overseen by Executive Directors. |
| To continue to improve the quality and quantity of management information and to review data collection procedures and timescales. | New data-collection system in place by 31/12/03 | Regular detailed management information provided to managers. | Each Business Unit now routinely receives extensive and tailored information quarterly from Personnel. See Appendix 2. The links between accidents and sickness are also monitored and reported. See Appendix 3. |
| To require feedback from managers on what action has been taken in cases highlighted by monitoring carried out by the Personnel Team. | By 31/7/03 | To ensure timely and consistent actions by managers on absence problems | A Case Study of one such Business Unit was presented to Management Briefing in January in order to share the approach, experiences and learning. |
| To provide Personnel support to managers in dealing with absence issues. | Full service available from 31/7/03 | To have managers who are able and confident to manage absence and to support those managers whenever necessary without allowing them to abrogate their responsibility. | This support has always and still is, available from MSES Additional resources were successfully sought in order for MSES to provide support specific to CTS. |
| To establish management of absence as a standard item on departmental/Business Unit Management Team meetings. | By 31/5/03 | To ensure that absence is given proper consideration on a regular basis. | This subject has been extensively covered at recent monthly Management Briefings. In CTS absence is routinely monitored and reported to both management and unions. Regular discussion with trade unions is held on this matter quarterly at CJC. |
| To ensure that all long-term absences are considered for referral to the Council’s Doctor after 2 months’ absence or earlier. | Review situation by 31/5/03. Apply immediately wherever found not to be. Review Occupational Health support arrangements by 31/10/03 | To ensure that all appropriate cases of long term absence are subject to an assessment by the Council’s Occupational Health Adviser after 2 months. | We have reviewed the current arrangements for support from Occupational Health. In order to ensure that the advice received best meets our needs, we have made a bid to members to adopt a new approach for 2004. In order to help progress certain long term sickness cases, additional Occ Health advice was purchased. Long term cases have been specifically targeted during the last quarter. |
| To select the worst performing department/sections for an in-depth analysis for the reasons for poor performance to ensure action can be targeted. | Review by 31/5/03. Act by 31/7/03 | To concentrate effort in the areas where it is likely to have the greatest impact on a reduction in the overall level of absence. | Under regular discussion at CMT. |

#### Carlisle City Council					Appendix 2

Member Support & Employee Services

# INTERNAL MEMORANDUM

| From: | Senior Personnel Officer | Please ask for: | Carolyn Hamilton |
| --- | --- | --- | --- |
| To: | Heads of Business Units, Chief Executive | Extension: | 7083 |
| FAO: |  | E-mail: | Carolyn Hamilton |
|  |  | Your ref: |  |
|  |  | Our ref: | CAH/KDB |
|  |  |  | 21 January 2004 |

SICKNESS ABSENCE STATISTICS (APRIL – DECEMBER 2003)

The performance indicator relating to BV12 (average working days lost to sickness absence) for the third quarter (Oct – Dec 2004) is 3.4 days. The 2nd and 1st quarters were 3.7 days and 2.6 days respectively.  You should note that these are estimated figures : the actual figure will be calculated for the whole year in April 04.

I now attach a number of documents which provide performance data both council-wide and specific to your Business Unit.

- Sickness Absence Rates, displayed by Business Unit and broken down into long and short term absence.

- Further breakdown of sickness absence rates for your business unit (CTS excepted).

- Causes of Absence across the whole Council.

- Causes of absence specific to your Business Unit.

I have already circulated records of sickness absence for the 12 month period to

31 December 2003 to assist you with individual monitoring (CTS excepted). Members of CROS please note that this is not included in Appendix 2, in view of confidentiality.

I hope you find this combination of information of interest and value in monitoring and managing sickness absence.  This is the second quarter when information has been provided in this manner, the first being at the end of October. Any comments you may have would be appreciated.

C A HamiltonSenior Personnel Officer

| Business Unit | Staff nos 1/4/03 | No days absence short term | short term absence rate | No days absence long term | long term absence rate | No days absence overall | overall absence rate | long term absence as % of total | Avg days overall absence per emp'ee |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CLS | 57.2 | 191.0 | 1.9 | 137.5 | 1.4 | 328.5 | 3.3 | 41.9 | 5.7 |
| CTS | 393.1 | 1326.0 | 1.9 | 3044.5 | 4.5 | 4370.5 | 6.4 | 69.7 | 11.1 |
| CIS | 29.0 | 99.5 | 2.0 | 212.5 | 4.2 | 312.0 | 6.2 | 68.1 | 10.8 |
| ECD | 54.9 | 163.5 | 1.7 | 408.5 | 4.3 | 572.0 | 6.0 | 71.4 | 10.4 |
| EPS | 68.8 | 228.0 | 1.9 | 160.5 | 1.3 | 388.5 | 3.3 | 41.3 | 5.6 |
| Executive Group | 4.0 |  |  |  |  | 0.0 |  |  |  |
| FS | 21.2 | 56.0 | 1.5 | 10.5 | 0.3 | 66.5 | 1.8 | 15.8 | 3.1 |
| LDS | 20.4 | 62.0 | 1.8 | 140.0 | 4.0 | 202.0 | 5.7 | 69.3 | 9.9 |
| MSES | 13.1 | 33.0 | 1.5 | 0.0 | 0.0 | 33.0 | 1.5 | 0.0 | 2.5 |
| Planning | 38.3 | 139.5 | 2.1 | 74.0 | 1.1 | 213.5 | 3.2 | 34.7 | 5.6 |
| Property | 9.1 | 33.0 | 2.1 | 0.0 | 0.0 | 33.0 | 2.1 | 0.0 | 3.6 |
| RBS | 72.7 | 424.0 | 3.4 | 385.0 | 3.1 | 809.0 | 6.4 | 47.6 | 11.1 |
| SPS | 13.5 | 33.5 | 1.4 | 113.5 | 4.8 | 147.0 | 6.3 | 77.2 | 10.9 |
| TOTAL | 795.4 | 2789.0 | 2.0 | 4686.5 | 3.4 | 7475.5 | 5.42 | 62.7 | 9.4 |
|  | Best value performance indicator is estimated at 3.36 days for the October - December quarter. |  |  |  |  |  |  |  |  |
|  | The cumulative figure for April - December is estimated at 9.62 days. |  |  |  |  |  |  |  |  |
|  | The target for 2003/04 is 9 days |  |  |  |  |  |  |  |  |
| BU | Division | Staff nos 1/4/03 | No days absence short term 1/4/03 - 31/12/03 | short term absence rate | avg days short term absence per emp'e 1/4/03 - 31/12/03 | No days absence long term 1/4/03 - 31/12/03 | long term absence rate | avg days long term absence per emp'e 1/4/03 - 31/12/03 | No days absence overall 1/4/03 - 31/12/03 | overall absence rate | Avg days absence per employee 1/4/03 - 31/12/03 |
| MSES |  |  | 5 |  |  |  |  |  | 5 |  |  |
|  |  |  | 5 |  |  |  |  |  | 5 |  |  |
|  |  |  | 19.5 |  |  |  |  |  | 19.5 |  |  |
|  |  |  | 3.5 |  |  |  |  |  | 3.5 |  |  |
|  | Total MSES | 13.1 | 33.0 | 1.5 | 2.5 | 0.0 | 0.0 | 0.0 | 33.0 | 1.5 | 2.5 |

Appendix 3  - reporting effects of accidents upon sickness levels - illustrative