5th Floor, Civic Centre, Carlisle, CA3 8QG, Tel 01228 817011

| Title: | Audit & Strategy Deliver Plan |
| --- | --- |
| Author: | Steven K O’Keeffe |
| Date Created: | 24/2/04 |
| Version: | 0.1 |
| CC: | Leadership group Overview & Scrutiny Committee |

| Stage | Stage Name | Product | Product Name | Duration | Date | Milestone |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | Project Initiation | 0.1 | Business Case and Risks | 3d | Feb-04 |  |
| 0 | Project Initiation | 0.2 | Project Initiation Document | 3d | Feb-04 | 1 |
| 0 | Project Initiation | 0.3 | Project Files | 2d | Feb-04 |  |
| 1 | Review | 1.1 | Strategy Review | 7d | Jan-04 | 2 |
| 1 | Review | 1.2 | Data & Information exchange review | 1d | Feb-04 |  |
| 1 | Review | 1.3 | Review of priorities | 1d | Feb-04 |  |
| 1 | Review | 1.4 | Review other relevant strategic plans | 3d | May-04 |  |
| 2 | Data Capture | 2.1 | Data & Information capture and storage plan | 1d | Jan-04 | 3 |
| 2 | Data Capture | 2.1.1 | Identify D&I Sources | 2d | Jun-04 |  |
| 2 | Data Capture | 2.2 | Collect D&I | 10d | Jul-04 |  |
| 2 | Data Capture | 2.2.1 | Primary D&I | 6d | Jul-04 |  |
| 2 | Data Capture | 2.2.2 | Secondary D&I | 4d | Jul-04 |  |
| 3 | Data Analysis | 3.1 | Analysis D&I | 20d | Jul-04 |  |
| 3 | Data Analysis | 3.1.1 | Primary D&I Analysis | 10d | Aug-04 |  |
| 3 | Data Analysis | 3.1.1 | Secondary D&I Analysis | 10d | Aug-04 |  |
| 3 | Data Analysis | 3.2 | Audit Report | 5d | Sep-04 |  |
| 3 | Data Analysis | 3.3 | Audit Acceptance | 1d | Sep-04 | 4 |
| 4 | Indentify Priorities | 4.1 | Priorities Framework | 2d | Oct-04 | 5 |
| 4 | Indentify Priorities | 4.1.1 | Priorities Report | 5d | Nov-04 |  |
| 5 | Refine Priorities | 5.1 | Report Consultation | 10d | Nov-04 |  |
| 6 | Draft Strategy | 6.1 | Draft Strategy | 5d | Nov-04 |  |
| 7 | Draft Strategy | 6.2 | Statuory Public Consultation | 10d | Dec-04 | 6 |
| 7 | Final Strategy | 7.1 | Final Strategy | 3d | Mar-05 | 7 |
| 7 | Final Strategy | 7.2 | Final Consultation | 5d | Mar-05 | 8 |
| 7 | Final Strategy | 7.3 | Strategy Acceptance | 1d | Mar-05 | 9 |
| 7 | Final Strategy | 7.4 | Strategy Distribution | 5d | Mar-05 | 10 |
| 8 | Implementation | 0 | Action plans within partnership sub-groups |  | Apr-05 |  |