OVERVIEW AND SCRUTINY MANAGEMENT COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 22 April 2004 |
| Title: | MONITORING OF AND CHANGES TO THE FORWARD PLAN |
| Report of: | Head of Legal and Democratic Services |
| Report reference: | LDS. 21 /04 |

Summary:	To inform Members of changes to the Executive’s Forward Plan for 1 March 2004 to 30 June 2004 since its publication on 16 February 2004.

Recommendations:	To note the modifications, deferrals and departures from the Forward Plan for 1 March 2004 to 30 June 2004.

| Contact Officer: | Elspeth MacKay | Ext: | 7034 |
| --- | --- | --- | --- |

- Background

1.1	The Overview and Scrutiny Management Committee on 22 November 2001 requested “That a standing item be included on future Agendas for this Committee identifying any deletions, modifications, deferrals and departures from the Forward Plan, together with the reasons”.

- Deletions, Modifications, Deferrals and Departures from the last Forward Plan

  - The Forward Plan for April to July 2004 was published in mid March 2004.  In addition to new items, it also contained some changes to the previous Plan.  Details of departures from, modifications to and deferrals in respect of the Forward Plan covering the period 1 March to 30 June 2004 are outlined in Appendix A of the report.

3.0	Recommendation

3.1	That the modifications, deferrals and departures from the Forward Plan for 1 March to 30 June 2004 be noted.

Contact Officer:		Elspeth MacKay						Ext:: 7034

1st March 2004 to 30 June 2004

| Reference Number: | Subject: Relevant Overview and Scrutiny Committee | Change: | Changed by: |
| --- | --- | --- | --- |
| KD.073/03 | Best Value Review of Risk Management and Health and Safety and Corporate Risk Register Corporate Resources O&S Committee | Deferred from 24 November 2003 to 01 March 2004, then deferred to April 2004 and then deferred to June 2004 | Head of Commercial and Technical Services |
|  | Reason: Delay due to priority being given to the Recycling Initiative |
|  | Homelessness Hostels Review Community O&S Committee | Item was not included in the Forward Plan – considered by Executive on 29 March 2004 under General Exception Rules | Head of Environmental Protection Services |
|  | Reason: Decision needs to be made in order to enable the required changes to be put in place for the Supporting People funding regime |
|  | Request for Licence to hold a Market Infrastructure O&S Committee | Item was not included in the Forward Plan – considered by Executive on 1 March and 29 March 2004 under General Exception Rules | Leader |
|  | Reason: An early response to the request is required |
|  | Civic Centre Fire Alarms Corporate Resources O&S Committee | Item was not included in the Forward Plan – considered by Executive on 29 March 2004 under General Exception Rules |  |
|  | Reason: Need to ensure a replacement system is put in place as the alarm system is dated and difficult to maintain |
| KD.114/03 | Review of Carlisle District Local Plan Infrastructure O&S Committee | Deferred from 29 March to a Special meeting some time during April 2004 | Corporate Management Team |
|  | Reason: To allow time for consultation on the Plan |
| KD.113/03 | Sheepmount Project Tender Community Overview and Scrutiny Committee | Was scheduled for a Special meeting to be arranged some time during March, but went to the scheduled meeting on 29 March 2004 under General Exception Rules | Corporate Management Team |
|  | Reason: Special meeting did not need to be arranged as it fitted in with the timetable for 29 March Executive meeting |