| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Achieve DWP Performance Standards |
| Does the LA have clear systems that it can demonstrate are working, to act on information received from Jobcentre Plus to make extended payments and to prioritise the reassessment of claims for customers moving into work? E2 | Develop procedures to identify cases for indexers/ scanners | DWP Performance Standards met | Self assessment and evidenced for DWP | Team Leader Neil Dewar | B | 4 (2 : 2) | Medium Term | 1 |
| Does the LA identify the need for information from the customer and third parties such as landlords within 7 days of receipt of the claim or notification of change of circumstances and take action to obtain it. E3 | When up to date not a problem but backlog situation will affect our ability to reach this target | DWP Performance Standards met | Self assessment and evidenced for DWP | Staff time | D | 6 (2 : 3) | Longer Term | 2 |
| Does the LA have routine, rapid arrangements for providing a certificate of earnings form for the employer to complete, allowing the change of circumstances or new claim to be processed rapidly, with safeguards to prevent fraud? E3 | When up to date not a problem but backlog situation will affect our ability to reach this target | DWP Performance Standards met | Self assessment and evidenced for DWP | Staff time | D | 6 (2 : 3) | Longer term | 3 |
| Does the LA have systems in place to prioritise changes of circumstances that lead to a reduction in, or a cessation of, benefit to minimise the occurrence of overpayments? E5 | Develop procedures to identify cases which will result in a deduction | DWP Performance Standards met | Self assessment and evidenced for DWP | Anite already set to prioritise cancellations. Overpaymentstaff to identify reasons for o/p’s as start of strategy. | B | 6 (2 : 3) | Medium term | 4 |
| In tandem with its targeted review activity, does the LA analyse the results of all management and accuracy checks across the full range of benefit activities including counter-fraud and deliver continuous improvement in its performance and service delivery by using its findings to identify the overall level of error in its caseload, inform training plans and the appraisal process? E10 | Performance Monitoring officer and Training/ technical officer posts filled | DWP Performance Standards met Improvements in accuracy | Self assessment for DWP Stats 124 | Management time partially actioned Waiting for QA module from Academy | C | 6 (2 : 3) | Longer term | 5 |
| Does the LA have in place a collection and monitoring policy and systems in place to monitor the recovery of administration penalties? E16 |  | DWP Performance Standards met | Policy in place but Academy consultant help required | Overpayment staff and consultants time | C | 6 (2 : 3) | Quick win | 6 |
| Does the LA publicise guidance on making a referral to all employees working for the LA? E20 |  | DWP Performance Standards met |  | Corporate policy On line form to be designed and put on the Council's web site. Advertised in Staff Focus | D | 4 (2 : 2) | Quick win | 7 |
| Does the LA provide fraud awareness sessions at induction and support this with an ongoing programme of fraud awareness to employees who are involved in HB/CTB benefit administration, housing and council tax collection, and any employees working for an RSL who are involved in the verification of HB/CTB claims? E20 | To be introduced as part of the new internal business unit induction | DWP Performance Standards met | Training records | Benefits Manager & Income Management Team Leader To be discussed at the next R&B management meeting | C | 2 (1 : 2) | Quick win | 8 |
| Does the LA risk assess all referrals giving priority to medium to high risk cases? E22 | Temporary Fraud officer to look at all referrals and provide intelligence analysis to inform risk scoring analysis | DWP Performance Standards met |  | Temporary fraud officer | B | 4 (2 : 2) | Medium term | 9 |
| Does the LA sift referrals within an average of 10 working days of receipt and use a management information system to track all fraud referrals, which are allocated to a named investigator and the progress made on them? E24 | CP enabler 24 & 25 software from Intec | DWP Performance Standards met |  | £500 one off fee to Intec software suppliers | A | 6 (2 : 3) | Quick win | 10 |
| Does the LA commence investigations within an average of 10 working days of referrals being sifted? E25 | CP enabler 24 & 25 software from Intec | DWP Performance Standards met |  | £500 one off fee to Intec software suppliers | A | 6 (2 : 3) | Quick win | 11 |
| Does the LA make all appointments of authorised officers in accordance with the law and monitor the use of these powers or use a centralised intelligence resource such as NAFN or a DWP OIU or in conjunction with neighbouring LAs? E31 | Software doesn’t allow monitoring at present but all appointments are made in accordance with the law. | DWP Performance Standards met | Centralised intelligence use authorised by Benefits Manager. Spreadsheet records kept. | Benefits Manager | D | 4 (2 : 2) | Long term | 12 |
| Does the LA have a written strategy or plan, covering issues of customer service, availability of help and advice and access, to encourage take up of HB/CTB that goes beyond the first step of raising awareness, and works in partnership with other stakeholders, such as the Pension Service, LA Welfare Rights Services, CAB and other voluntary advice groups, to ensure that eligible customers are enabled to make successful claims? E38 | Involved in DWP pilot to encourage take up of HB / CTB for customers in receipt of Pension Credit | DWP Performance Standards met | Increase in Pension Credit cases of HB/CTB | DWP Pilot Staff time | A | 8 (2 : 4) | Quick win | 13 |
| Does the LA regularly review the service it provides taking account of its obligations under the Race Relations Acts (1976 & 2000), the Disability Discrimination Act (1995) and to ensure it best meets customer needs? E40 | Equality pilot group set up within the Authority | DWP Performance Standards met | Corporate Policy and consultants Trinity Developments | Benefits Project officer on equality team | D | 6 (3 : 3) | Longer term | 14 |
| Does the LA maintain regular contact, supported by formalised and documented working arrangements, if considered appropriate, with other organisations, for example RSL’s, CAB, Police, CPS or Procurator Fiscal in Scotland? E46 |  | DWP Performance Standards met | Regular liaison meetings with majority landlord Carlisle Housing Association | Too resource intensive to make a satisfactory business case |  | 2 (1 : 2) | Will not be actioned under current business case. Bid for DWP Performance funding rejected. | 15 |
| Does the LA manage and monitor the contract arrangements with its IT providers to ensure compliance with agreed and documented performance standards in the provision of the service? E60 | SLA required with IT | DWP Performance Standards met Down time minimised and therefore performance improved | Self assessment | Management time IT Applications and Information Manager | D | 6 (3 : 2) | Longer Term | 16 |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Staff Security (Lone Workers) |
| All external visiting officers to be issued with personal hard copies of appropriate documentation. | To ensure as far as possible staff safety. | Reduce risk to staff of incidents |  | Team Leaders | B | 8 (2 : 4) | Medium term | 17 |
| Reporting procedures need reviewed, formalised and standardised across the Business unit and the Authority, that meets the Data Protection regulations. Procedure needs to include out of office working. | Under Best Value unit’s policy has been completely reviewed but a Corporate review is required | Improvements in staff safety and prevention of further incidents where possible. Reduced risk to staff of incidents |  | To be agreed by Head of MS&ES and Health & Safety officer Benefits Manager in conjunction with external visiting officers. | B |  |  | 18 |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk assessments require updating for: | Head of Revenues & Benefits to take to CMT |  |  | Head of Revenues & Benefit and Benefits Manager to liase with DWP on their risk analysis to learn from good practice | B | 8 (4 : 2) | Medium term | 19 |
| 1. 2. 3. 4. 5. 6. | General observations and doorstep enquiries Joint operations Interviews under caution Attendance at Magistrates or Crown Court Home Visits Use of surveillance vehicles |  |  |  |  |  |  |  |  |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Telephone Service To The Public |
| Ascertain satisfaction with the improved telephone service. | Originally actioned, see paper 3rd August 2004, however to be reintroduced to monitoring equipment being lost in the flood. | Survey in progress November 2005 | Customers to be surveyed using the BV80 questionnaire format. | Staff time | B | 6 (2 : 3) | Quick win | 20 |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initiatives To Maintain / Continually Improve Revenue Collection Rates |
| Pilot again telephone recovery practices. Pilots tried under Community Charge and in the early 1990’s proved resource intensive and ineffective. | To be progressed by new Customer Contact Centre | Some success with HB overpayments | BV9 & BV10 BV79I, ii & iii | Revenues Manager Recovery staff | D | 2 (1 : 2) | Longer Term | 21 |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improve Forms, Publicity, And Written Correspondence |
| Arrange for DWP and Pension Service leaflets to be available in the Customer Contact Centre. This will include a selection written in different languages. | To be ordered when refurbished Customer Contact centre reopened | BV80 |  | Team leader Benefits Customer Services | C | 4 (2 : 2) | Quick win | 22 |
| Redesign the benefit determinations and notification letters based on good practice examples, and using ProPrint functionality, for consultation with welfare agencies before final production. | Updating 117 + templates on an individual basis. 4 templates completed so far. | BV80 |  | Jill Chamberlin / Emma Younger | C | 6 (2:3) | Medium term | 23 |
| Roll out ProPrint into Revenues when Benefit implementation is complete. | Updating templates (high risk due to licence requirements on existing software ) | Customer satisfaction surveys |  | Technical Team Leader & Technical Officer | C | 9 (3 : 3) | Medium term | 24 |
| Timetable improvements to Benefits and Revenues templates to provide additional information based on personal circumstances. | To be determined once ProPrint fully functional | BV80 |  | Jill Chamberlin / Emma Younger | D | 4 (2 : 2) | Longer term | 25 |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IT enhancements within Revenues & Benefits |
| Payment of Housing Benefit by BACS and AUDDIS software installation | Housing Benefit payments to be made direct to claimants bank accounts to save raising cheques and claimants having to bank them. AUDDIS software to verify bank sort codes | Direct Debit take up |  | Deputy Benefits Manager & Team Leader Technical | C | 6 (2 : 3) | Medium term | 26 |
| Electronic Benefit Claim form |  | BV80 |  | Academy e-form | B | 4 (2 : 2) | Quick win | 27 |
| Introduction of other electronic forms | 10 most used forms (mando forms) | BV80 |  | Academy IT and Revenues Technical Officer | B | 4 (2 : 2) | Medium term | 28 |
| Introduction of bar codes on customer documentation | Proprint can be used to bar code documents produced from Academy. To investigate the possibility of introducing bar codes on Images via the bar code font. |  |  | JC / EY | D | 2 (1 : 2) | Quick win | 29 |
| Skills transfer required from Applications and Information Manager to ensure lack of down time with Computer Services. | See Head of Revenues & Benefits report | Down time to be measured against SLA |  | Head of Revenues & Benefits & Head of Customer & Information Services | C | 9 (3 : 3) |  | 30 |

| Area for Improvement | Specific Improvement Action (if required) | Measurable | Attributable (Source) | Resourced | Priority for Improvement A - Imminent B - 6 months C - 1 year D - Long term | Risk Assessment If no action Impact/ Likelihood | Impact Quick Win Medium Term Longer Term | R E F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Other Initiatives |
| To review Overpayment targets in line with DWP guidelines. | Business case required to risk assess | BV78 I,ii & iii |  | Head of Revenues & Benefits | D | 4 (2 : 2) | Quick win | 31 |
| Preparation for Local Housing Allowance being introduced in Benefits | Likely to be April 2008 |  |  | Benefits Manager | D | 9 (3 : 3) | Longer term | 32 |
| Resource implications of Council Tax Banding revaluation | Delayed until after 2009 |  |  | Revenues Manager | D | N/A | N/A | 33 |
| Links required to other business units/corporate policies | Housing strategy etc. |  | Satisfy external challengers observations | Head of Revenues & Benefits | D | 6 (2 : 3) | Longer term | 34 |
| Post flood opportunities re Renaissance | Actions required in supporting Corporate priorities |  | Satisfy external challengers observations | Head of Revenues & Benefits | D | 4 (2 : 2) | Longer term | 35 |
| Rural proofing | All policies are corporate decisions | Rural proofed as much as possible but corporately needs rural proofed | Satisfy external challengers observations | Head of Revenues & Benefits | D | 4 (2 : 2) | Longer term | 36 |
| External Threats |
| Gershon efficiency savings on 2006/7 and 2007/8 | Find required savings within new Corporate Services directorate | Targets set corporately |  | Head of Revenues & Benefits | B | 6 (2 : 3) | Medium term | 37 |
| Outsourcing shared provision of services | A new business case required every 5 years and if the Council decides to leave the Civic Centre under the Renaissance initiative. | Cost or efficiency savings accrued if any |  | Head of Revenues & Benefits | D | 4 (2 : 2) | Longer term | 38 |
| Excellent CPA rating concentrate resources on maintaining an excellent rating in respect of the customer | Further efficiency savings due to reduced DWP grant allocation | Bench marking | DWP | Benefits Manager | C | 9 (3 : 3) | Medium term | 39 |
| Reduced government grant has implications for downsizing of Revenues & Benefits resources. | Further efficiency savings due to reduced DWP grant allocation | Bench marking |  | Head of Revenues & Benefits | C | 9 (3 : 3) | Medium term | 40 |

Risk Assessment

| Impact | 1. Negligible | 2. Marginal | 3. Critical | 4. Catastrophic |
| --- | --- | --- | --- | --- |
| Likelihood | 1. Extremely Remote | 2. Remote | 3. Reasonably probable | 4. Probable |