# Carlisle City Council

# Overview and Scrutiny Improvement Plan

2005-2007

Progress Report January 2007

Report OS02/07

## Introduction

Carlisle City Council aspires to have a high performing Overview and Scrutiny (O&S) function. Since its introduction O&S has tried to seek out and adopt best practise. As part of this approach and to assist continued development of O&S Management Committee agreed to an independent evaluation of progress by Dr Stephanie Snape, one of the leading experts in this field nationally.

## Dr Snape’s Evaluation

The overall aim of the evaluation was:

‘To review the overview and scrutiny arrangements at Carlisle City Council in order to identify key achievements, remaining challenges and to provide recommendations for further improvement’.

The fieldwork took place between October 2004 and March 2005 and included analysis of key documents, observations at O&S Committee meetings, interviews and focus groups with members and officers.

Achievements

Dr Snape identified good progress including:-

## O&S bedded down & developed, members understanding deepened

## Good approach to in-depth reviews

## Good system for Best Value Reviews

## O&S structure essentially sound

## Impressive start on Task & Finish Groups

## Good Member commitment & cross party working

## Quality outside contributions especially by partners

## Good reports with comprehensive recommendations

## O&S Support Unit’s valuable contribution

## Key Areas for Improvement

The evaluation highlighted the following areas for improvement:-

## Improve chairing and leadership

## Review conduct of meetings

## Shorter agendas and consequent prioritisation

## Pursue innovative ways of working

## More Task & Finish Groups

## Enhance O&S Status and resources

## Develop performance management, especially measurement of Outputs and Outcomes

## Improve relations with Executive

## Enhance Community Engagement

## Achieve greater media exposure

## Redefine role of Management Committee

## Improvement Plan

Dr Snape’s Report made recommendations for improvement and these were the subject of a full-day’s workshop by O&S Management Committee which developed the following Improvement Plan designed to deliver those recommendations. As proposed by Dr Snape the plan covers a three year period (2005-07) during which all identified changes are to be achieved.

## Plan Format

The plan is in tabular form and for each recommendation there is a Comment (based on the Management Committee’s views), Actions (as agreed at the worksho p), a person or group to Lead that action, Risk to successful O&S development (High, Medium or Low), Priority (1,2 or 3; 1 being high) and the original implementation timescale. Progress to date is then outlined.

|  | Recommendation/Issue | Comment/Action | Lead | Risk, Priority and original timescale agreed | Progress |
| --- | --- | --- | --- | --- | --- |
|  | Chairing of Overview & Scrutiny Committees |  |  |  |  |
| 1 | The chairing weaknesses with both Corporate Resources & Infrastructure to be urgently addressed. It is the firm recommendation of this evaluator that each Committee needs new, strong chairmen for the council year 2005/06 | Comment – Appointment of chairmen a matter for Council and Political Groups. Support and training important. Action – Review of Member Induction Programme and Training and Development (including chairing skills). | Maggie Mooney, John Egan, David Williams | High 1 By end December 2005 | There were 3 new O&S chairmen this Civc year. ACE programme included an IDeA event for O&S Chairmen but only one was able to attend. A countywide seminar by Prof Steve Leach was attended by two chairmen and one vice-chairman. One chairman attended the INLOGOV training event for O&S Chairmen, one having previously attended that event. Members Learning and Development Programme includes relevant opportunities including chairing skills. |
| 2 | New leadership roles to be produced by more use of task & finish groups | Comment - Task & Finish Groups an important way forward. Action – Chairmen to promote use, O&S Support to produce brief guidance document. Each committee to initiate at least one T&F group before end of year. Form pool of officers to support T&F groups | All chairmen, O&S Support CMT | Medium 2 By end of Civic year | T&F Groups in operation in all committees now. Guidance Agreed and being applied. |
| 3 | Experiments to be conducted in developing a small number of individual member champions for O&S | Comment – Not viewed as a priority Action – Review again in 2006/07 |  |  | No actions agreed |
|  | Moving out of Traditional Committee Mode |  |  |  |  |
| 4 | Officers from business units providing reports to O&S to consider the specific role and nature of O&S, in particular to provide one side of A4 which summarises the main issues in the report & explicitly states what is expected from the O&S committee; | Comment - More reports should be prepared specifically for O&S. Reasons for consideration by O&S and expectations of the committee must be included. Action – Report formats be reviewed to provide for this approach. CMT to undertake quality assurance role on reports to O&S. | John Egan CMT | Medium 1 End November 2005 | Progress continues but more to be done. O&S Support will promote during 2007. |
| 5 | Direct officer support unit to work with O&S members, Legal & Democratic Services and officers from business units to ensure that agenda, minutes & reports are in an appropriate, useful format for O&S committees. This may involve the development of new proformas or ‘model’ reports; | Comment – Current format of agenda’s and minutes strongly supported. Action – See 4 above regarding reports. |  |  | See 4 above. It is also intended to review report formats during 2007, capacity in both O&S Support and Committee Administration has not yet permitted this. |
| 6 | O&S committees should at times experiment with holding meetings in different venues (this links to public & partner engagement); | Comment – Previous lack of success with this relevant, not viewed as a priority. Action – When suitable topics arise committees should hold meetings elsewhere, target of 2 before end of Civic Year. | O&S Support,Committee Administration | Low 3 When suitable opportunity arises | Sheepmount and Talkin Tarn used last year. Chairmen and O&S Support will actively seek opportunities. Also covered in agreed O&S Communications Plan. |
| 7 | The layout of the tables and chairs for O&S Committees should be given greater consideration and should be varied according to the purpose of the meeting. For example brainstorming workshops could be held with a round or square table format (and away from the formality of the committee rooms). Select committee style formal hearings should have a horseshoe or U-shaped table layout, with the members and direct support officers of a committee clearly labeled and separate from officers providing evidence and other witnesses. There should also be a separate but distinct public seating area (with spare copies of the agenda and papers on these seats); | Comment – Proposal supported. Action – Workshop sessions in Slupsk Room , new layout for meetings and evidence sessions in Flensburg Room. | Committee Administration | High 1 Immediately | Completed |
| 8 | The physical environment of the committee room used for O&S also requires attention in a number of aspects, including audibility. | Comment – Improvements required. Action – Review of heating, air-conditioning and provision of a sound system. | Committee Administration and Commercial and Technical Services | Medium 1 By start of new Civic Year | Completed |
|  | Re-considering the Role Profile |  |  |  |  |
| 9 | The O&S function needs to consider developing a more balanced role profile, ensuring that external scrutiny, holding the executive to account and pre-decision scrutiny are not neglected; | Comments – Portfolio Holders should be more clearly accountable for policy. Involvement in policy development should be at early stage. Requires improved relationship with Executive. Executive must give reasoned responses to O&S recommendations and referrals. External scrutiny not viewed as high priority. Action – Include Portfolio Holders accountabilities and reasoned Executive responses in protocol under 15 below. Officers to plan for early O&S involvement in policy development. Executive to give fuller and reasoned responses to O&S. | O&S Support. CMT. Executive. | High 1 By start of new Civic year | To be included in work of Protocol T&F Group. This years budget proposal scrutiny by CROS was more focussed on portgolio-holders. |
| 10 | Such a wider role balance would take into account emergent new roles, in particular, the role of O&S in the improvement planning process; | Comment – O&S involvement in Improvement Planning needs to be built in to process. Action – Develop process which specifically includes O&S and allows for informal interactive input. | Jason Gooding | Medium 2 By start of new Civic year | Deputy Chief Executive has agreed to include O&S in Improvement Planning as outlined. Community O&S will be closely involved in Community Development Improvement Review. |
| 11 | A more balanced role profile has to be linked to realistic, achievable work programmes and shorter agendas for committees; | Comment - Supported. Action – Chairmen to take strong line, consider guidance on maximum number of substantive agenda items. | Chairmen, O&S Support | High 1 End November 2005 | Guidance Document agreed, success so far patchy, chairmen to be asked to be more proactive when agreeing draft agendas |
| 12 | This will involve greater prioritisation of work items; | Comment – Accepted role of chairmen, Action – Chairmen to take forward. Prepare guidance on criteria for such prioritisation. Aim to be 2 hour focussed and productive meetings. | Chairmen, O&S Support | High 1 December 2005 | Guidance Document agreed, see 11 above. |
| 13 | In undertaking prioritisation consideration must be given – at least in part – to the council’s priorities and those of the communities it serves. | Comment – Priorities important criteria but not sole one. Action – Include priorities in criteria under 12 above | Chairmen | High 1 December 2005 | Guidance Document agreed, criteria are being considered by chairmen. |
|  | Relating to the Executive |  |  |  |  |
| 14 | As discussed later, O&S Management Committee to take strategic responsibility for developing a more effective relationship with the executive. | Comment – The changed role and meeting arrangements for Management Committee supported. Action – Executive to be invited to joint discussion with Management Committee twice yearly. | Jason Gooding | Commencing with discussionon taking Improvement Plan forward. | Completed |
| 15 | A Protocol to be developed to guide the relationship between the Executive and O&S. (The process of development of a Protocol is as valuable, if not more valuable than, the written document itself). | Comment – Supported see 9 above. Action – Protocol to be developed in joint workshop session between O&S Management Committee and Executive. | O&S Support | Medium 1 During current Civic year | Protocol T&F Group has met once and meets again shortly. |
| 16 | As discussed later, O&S to ensure SMART recommendations to their work. | Comment – Need for clarity and sharpness in resolutions accepted. Action – Chairmen to sum up as carefully and clearly as possible. Training to be provided. Use of SMART recommendations to be included in protocol under 15 above. | Chairmen. David Williams | Low 3 During next Civic year | Guidance Document agreed. |
| 17 | Legal & Democratic Services to develop in partnership with the O&S support unit a robust system for tracking the response to O&S recommendations. | Comment – Supported but not a priority Action – System to be developed | Committee Administration, O&S Support | Low 3 During next Civic year | Database established, further work will be ongoing to develop and refine appropriate reporting and analysis as resources in both O&S Support and Committee Administration permit. |
|  | Engaging Public, Partners & Media |  |  |  |  |
| 18 | O&S to develop specific measures to: publicise the work of O&S more widely amongst partners and the public; ensure that they contribute more effectively to the O&S agenda; and participate more fully in O&S processes; | Comment – Supported but on selective, cost effective basis. Action – Limited range of initiatives to be developed. | O&S Support, Strategic & Performance Services | Medium 3 During next Civic Year | O&S Communications Plan agreed. |
| 19 | O&S may wish to consider some of the following initiatives undertaken in other authorities in addressing the above: the development of a number of attractive scrutiny web pages on the Council website (to include an electronic form for raising issues for O&S to consider in their work programmes); the production of a range of information leaflets on O&S, tailored to different audiences; the inclusion of a regular O&S column in the Council newspaper and staff newsletter; the production of an O&S newsletter to be distributed to partners and at libraries, council offices (and other locations); O&S road shows at supermarkets and shopping centres; Co-option of partner, user & community representatives on task and finish groups; Stakeholder analysis to determine which partners/public to invite to provide oral evidence and/or written evidence; Expansion in the use of expert witnesses, drawn from universities, consultancies and national user/lobbying groups | Comment – Newsletter and Road shows not considered appropriate or cost effective. Co-operation with Universities supported. Neighbourhood forums could be useful vehicle especially for consultation. Action – See 18 above. | As 18 | As 18 | O&S Communications Plan agreed. Website established. Use of external witnesses continues where appropriate. |
| 20 | Strategic & Performance Services to develop, in discussion with O&S members and the direct officer support unit, a PR & Communications strategy for O&S (and then to deliver this strategy). | Comment – Regarded as essential. Action – Communications Strategy to be developed. | Strategic & Performance Services | Medium 1 By start of new Civic year | O&S Communications Plan agreed. |
|  | Officer Support to O&S |  |  |  |  |
| 21 | The Council to strengthen officer support to O&S, principally through an enlarged officer support unit, an enhanced role for Legal & Democratic Services, a more substantive role for Strategic & Performance Services and the creation of a pool of managers to work on in-depth task and finish subject reviews. | Comment – Supported Action – O&S Support and role of Strategic and Peformance Services to be addressed as part of reorganisation (stage 2) | Town Clerk & Chief Executive | By start of new Civic year | Additional officer for O&S Support not agreed, a part-time post funded from Civil Contingencies Budget to backfill additional time spent on Emergency Planning by Head of Scrutiny and Emergency Planning. That post now vacant. Some progress on other aspects following formation of PPP Directorate. O&S part-time vacancy to be filled by joint post with Policy Team. |
| 22 | The Council to consider the appropriate level in the officer structure for the head of the direct support unit. | Comment – Supported Action- To be addressed as part of reorganisation (stage 1). | Town Clerk & Chief Executive | High 1 By start of new Civic year | Completed |
| 23 | The Council to consider a more appropriate ‘location’ for the O&S direct support unit, if a reorganisation of the Council is undertaken. | Comment – Supported Action- To be addressed as part of reorganisation (stage 1). | Town Clerk & Chief Executive | High 1 By start of new Civic year | Completed |
|  | Capturing Outputs & Outcomes of O&S |  |  |  |  |
| 24 | O&S direct support unit, with support and advice from the performance management section of Strategic & Performance Services, to develop a robust system for measuring outputs and outcomes. | Comment – Support for a limited number of PI’s. Action – Proposals for PI’s and collection system be developed. | O&S Support, Strategic & Performances Services | Medium 2 During next Civic year | Resources have not yet permitted progress. Will revisit during 2007. |
| 25 | In undertaking this work, the Council may wish to review the work in this area by: the Centre for Public Scrutiny, Birmingham City Council, Tameside Borough Council and South Ribble Borough Council. The Council may also wish to consider pooling resources with a neighbouring Council to develop such a system. | Comment – Some of these authorities measures considered of marginal value, selective approach needed. Acton – See 24 above. |  |  |  |
| 26 | O&S Committees to work to ensure that recommendations from its reports or meetings are SMART (specific, measurable, accurate, realistic and timely). | Comment – Smarter where possible, clarity main issue. Action – See 16 above. |  |  | Guidance Document agreed. |
| 27 | Information on impact and performance (i.e. performance indicators) to be included in scrutiny pages on the Council website and in the Annual Report for O&S. | Comment – Supported Action – Scrutiny web pages to be developed. | Strategic & Performance Services | Low 3 During next Civic Year | See 24 above. |
|  | Lack of Substantive Role for O&S Management Committee |  |  |  |  |
| 28 | O&S Management Committee to take strategic responsibility for developing a more effective relationship with the executive. | Comment – Supported. Action – See 14 above. |  |  | Completed |
| 29 | O&S Management Committee to have a joint meeting with the Executive Committee on a twice yearly basis to discuss respective work programmes, barriers to an effective relationship, and so on; | Comment – Supported. Action – See 14 above. |  |  | Completed |
| 30 | O&S Management Committee to discuss, determine, drive and monitor an Improvement Plan for the O&S function on the basis of this report and its recommendations. | Comment – Improvement Plan and relationship with Executive to be sole focus of Management Committee. Action – Future agendas structured accordingly. | Committee Administration | High 1 By end November 2005 | Process complete, monitoring and driving Improvement Plan ongoing |
| 31 | O&S Management Committee to consider meeting on a quarterly basis. | Comment – Management Committee (with business as in 30 above) to meet only as required. Action – Council is recommended to amend constitution accordingly. | John Egan | High 1 By end 2005 | Completed |