CORPORATE RESOURCES OVERVIEW AND SCRUTINY COMMITTEE

Committee Report

| Public |
| --- |
| Date of Meeting: | 7 December 2006 |
| Title: | PROGRESS REPORT ON EMPLOYEE OPINION SURVEY IMPROVEMENT PLAN |
| Report of: | Head of Personnel and Development Services |
| Report reference: | PPP59/06 |

Summary:

Members on Corporate Resources Overview and Scrutiny Committee received a report in July this year detailing actions to be taken in response to issues raised by employees in their Opinion Survey some months earlier. Members agreed that they would monitor progress with this Improvement Plan. This is the first such progress report to come before you.

Recommendations:

Members to:

- comment upon progress achieved thus far

- note that a second Opinion Survey is currently underway

- note that the Improvement Plan will be amended in the light of further feedback received from employees

- note that subsequent progress reports to this committee will reflect these changes.

| Contact Officer: | Jennifer Williams | Ext: | 7163 |
| --- | --- | --- | --- |

# Employee Opinion Survey Improvement Plan  - Progress at November 2006

###### Glossary

TIR	Team Improvement Plan

CMT 	Corporate Management Team

SMT 	Senior Management Team

IiP 	Investors in People

MDP	Management Development Programme

#### EEP 	Employee Enhancement Programme

#### CIS 	Customer Information Services

CTS 	Commercial and Technical Services

RBS 	Revenues and Benefits Services

PDP 	Personal Development Plan

WDP 	Workforce Development Plan

Note that areas of concern/issues in particular former business units are shown in Italics

| Areas of concern/issue | Actions | Lead | Targets (including time-scales) | Outcomes | Measures (of outcomes) | Progress at November 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| General Actions which will influence many of below actions | Internal communications review – particularly the role and performance of the management communication chain including TIR, Management Briefing, future CMT and team meetings. This review should lead to the development of internal communications strategy SMT IiP workshop to identify which levels the council will aim to achieve within the profile and time-scales for achievement MDP further developed to address specific management skills e.g. appraisal, return to work interviews, team meetings, TIRs Management training (above) to be incorporated into revised probation policy | Jason Gooding David Williams David Williams David Williams | July – Dec 06 June 2006 workshop 2007 next IiP assessment Launch of new programme 2007/08 (financial year) Review probation policy 2006 | Improved communications Clarity on IiP levels for actions within plan Specific training delivered to address areas of concern identified by survey | Employee survey IiP Achievement of agreed IiP profile IiP Employee Survey results Framework of evaluation for training and development | Draft Internal Communications Strategy considered by SMT on 21 November Draft IiP Profile now under consideration by SMT. New MDP contains skills development in all these areas Revised Probation Policy is now under consultation with unions. Is linked with training and assessment of competence in role. |
| General Actions which will influence many of below actions | Raise manager awareness of framework of evaluation for training and development Review of management competencies to cover areas of concern e.g. leadership Decision to be made on how the next survey will reflect the new directorates and be comparable with results from the last survey | David Williams David Williams Jennifer Williams David Williams | Nov 06 2007/08 financial year Sept 06 | Managers effectively evaluating training Increase management capacity Comparable information year on year | Achievement of IiP profile indicator level 4 – capabilities managers need to lead, manage and develop people effectively are clearly defined and understood Future survey results/analysis | Delayed until early 2007 – see Action 36 n/a Corporate information will be compared year-on-year but we will have to start from scratch with Directorate data |
| Response rate varied across council | Resolve distortion of electronic version of questionnaire Investigate possibility of ‘save’ facility when completing questionnaire Send questionnaire in addressed envelopes to individuals without PC access and provide pre paid envelopes Make anonymous issue more explicit in introduction to the survey Develop local PI to measure the response rate | Jennifer Williams | Nov 06 when survey repeated | Increased response rate | Increase in response rate | Investigated - we were using the wrong type of question in software Depends on if user has cookies on PC. Will send instructions on how to install to enable save facility. This is to happen Survey introduction has been amended PPP will use this as an internal PI in their Service Plan |
|  | Benchmarking with other Cumbrian authorities Include additional questions to enable us to measure new PIs | Jennifer Williams Jennifer Williams David Williams | Nov 06 when survey repeated | Identified small number of common questions To enable us to measure our performance | Cumbria wide statistics Measures in place and published in BVPP June 06 | We will benchmark several questions with Allerdale and Copeland New questions included in survey |
| Additional investigation | Chief Executive’s Sounding Board lunches with staff | Maggie Mooney | Weekly sessions | Greater understanding of staff’s key concerns, possibly with progression of some common themes through task and finish groups/Action Learning Sets | See outcomes | Continue to be held regularly with over 120 employees attended thus far. 2 subjects for Task and Finish Groups have been identified (Flexi-time, and Childcare) with Flexi group about to start |
|  | Appropriate outcomes of Chief Executive’s Sounding Board lunches with staff incorporated into this plan | Jennifer Williams David Williams | July 06 | Issues incorporated into one improvement plan | Employee Opinion Survey Improvement plan | See above |
| Line managers providing employees with feedback on their performance Over 1/5 of say rarely or never CIS - 42% CTS – 42% RBS – 39% | Internal communication review Appraisal refresher training Special appraisal briefings for former CTS MDP – specific training on the importance of and how to run effective team meetings | Jason Gooding David Williams | July – Dec 06 Nov 06 April 06 Nov 06 | Improved communications Line managers provide employees with feedback on their performance | Future survey results IiP Indicator 5 – managers are effective in leading, managing and developing people Team meeting training evaluation feedback Full management attendance at appraisal refresher training | Review is underway Training scheduled Many Briefings were held at Bousteads Grassing in 2006 with more planned for early 2007 In new MDP |
| Line Manager supporting employee to achieve their objectives 16% say rarely or never CIS – 36% CTS – 25% RBS – 25% | Appraisal refresher training | David Williams | Nov 06 | Line Managers support employees to achieve their objectives | Future survey results IiP Indicator 5 – managers are effective in leading, managing and developing people Full management attendance at appraisal refresher training | Training scheduled |
| Employees having the opportunity to comment on issues affecting them Just over 1/5 only ‘sometimes’ have opportunity to comment CIS – 39% | Internal communication review Appraisal refresher training MDP – specific training on importance and how to run effective team meetings | Jason Gooding David Williams David Williams | July – Dec 06 Nov 06 Nov 06 | Improved communications Employees feel that they have the opportunity to comment on issues affecting them | Future survey results Full management attendance at appraisal refresher training Team meeting training evaluation feedback IiP Indicator 5 – managers are effective in leading, managing and developing people | Review underway Training scheduled In new MDP |
| Employees attending TIR 50% not had a TIR in last 6 months (31% not had one) CTS – 82% CIS – 69% EPS – 62% | Internal communication review MDP – specific training on the importance of and how to run effective TIRs | Jason Gooding David Williams | July – Dec 06 Nov 06 | Employees attend TIR or equivalent | Future survey results TIR training evaluation feedback IiP Indicator 5 – managers are effective in leading, managing and developing people | Review is underway In new MDP |
| Frequency of team meetings (2nd preferred method of communication) CTS and CIS would like to have more | Internal communication review MDP – specific training on the importance of and how to run effective team meetings | Jason Gooding David Williams | July – Dec 06 Nov 06 | Improved communications Team meetings held when necessary | Future survey results Team meeting training evaluation feedback IiP Indicator 5 – managers are effective in leading, managing and developing people | Review is underway In new MDP |
| Employees who feel their skills and experience are valued 17% of employees do not feel valued CIS – 42% | Commitment in new Training and Development Policy to 5 days learning per employee (pro-rata) e.g. management briefing attendance Targets for employees achievement of qualifications | David Williams David Williams | June 06 Published in BVPP June 06 | Employees feel their skills and experience are valued | Future survey results IiP Indicator 6 – people’s contribution to the organisation is recognised and valued Learning City PIs | Commitment expressed in new Policy which was approved in August Several new Learning City PIs relating to employees, including qualification achievement, were in the BVPP published in June |
| Employees who have an appraisal 31% have not had an appraisal in last 12 months CIS – 77% RBS – 71% | Appraisal refresher training Make appraisal briefing mandatory (new employees are booked onto course) Enforce appraisals Prompt and guide managers during appraisal round Develop new PI in relation to appraisals | David Williams Linda Mattinson Jason Gooding David Williams David Williams | Nov 06 Nov 06 Jan each year Jan each year Nov 06 | All employees had an appraisal | Future survey results Record of appraisals in personnel PI on appraisal IiP Indicator 5 – managers are effective in leading, managing and developing people Full management attendance at appraisal refresher training | Training scheduled System now in place to automatically book new employees onto a briefing n/a A working group is currently looking at ways of improving take-up of appraisal and we will use their recommendations in new guidance to go out early 2007 LP74 now in place |
| Line manager encouraging employees to develop new skills and enhance career prospects 20% feel that their line manager does not encourage them Problem most noticeable in RBS, CTS, CIS and MSES | Training – improve maximising training module (MDP D11) Introduce directorate training plans (integrated into service planning process) Pilot career development strategy | David Williams | Nov 06 June 06 Jan 07 | Line managers encourage employees to develop new skills and enhance career prospects | Maximising training evaluation feedback Future survey results IiP Indicator 2 – learning and development is planned to achieve the organisations objectives | Instead we are to remove D11 and replace it with a completely new module that will be piloted early in 2007. The module will address this and several other related areas of concern A model Directorate Training Plan template has been designed and is currently being piloted n/a |
| Training and development opportunities that will benefit employees are brought to their attention 19% say that training and development opportunities are not brought to their attention CIS – 42% | Introduce directorate Training Plans (integrated into service planning process) Formalise role of union learning representative (ULR) | David Williams David Williams | June 06 Dec 06 | Training and development opportunities that will benefit employees are brought to their attention | Future survey results IiP Indicator 5 –managers are effective in leading, managing and developing people | A model Directorate Training Plan template has been designed and is currently being piloted The Skills for Life Strategy approved by Executive in September 2006 places the ULR in a pivotal position. The ULR role is to be formally articulated within a new Facility Time Agreement which is currently being consulted upon with the trade unions |
| Discussions take place with line manager before a training/development activity 34% do not discuss CIS – 65% | Training – improve maximising training module (MDP D11) | David Williams | Nov 06 | Discussions take place with line managers before a training/development activity | Maximising training evaluation feedback Future survey results IiP Indicator 5 – managers are effective in leading, managing and developing people | Instead we are to remove D11 and replace it with a completely new module that will be piloted early in 2007. The module will address this and several other related areas of concern |
| Discussion take place with line manager after a training/development activity 32% do not discuss CIS – 50% CTS – 48% CLS – 42% | Training – improve maximising training module (MDP D11) | David Williams | Nov 06 | Discussion take place with line managers after a training/development activity | Maximising training evaluation feedback Future survey results IiP Indicator 5 – managers are effective in leading, managing and developing people | Instead we are to remove D11 and replace it with a completely new module that will be piloted early in 2007. The module will address this and several other related areas of concern |
| Employees feel that overall training and development has helped them to do their job more effectively 18% do not feel training has helped CIS – 43% | SSDG to identify and distribute case studies of good practice to appropriate employees | David Williams | June 07 | Help employees to link training and development to helping them to do their job more effectively | Future survey results IiP Indicator 8 – people learn and develop effectively IiP Indicator 9 – Investment in people improves the performance of the organisation IiP Indicator 8 – people learn and develop effectively | n/a |
| Employees have a Personal Development Plan which is reviewed at each appraisal 26% do not have a PDP CIS – 66% CTS – 57% | Enforce appraisal Issue guidance on PDPs and funding of training | Jason Gooding David Williams | Jan each year Jan each year | Employees have a Personal Development Plan which is reviewed at each appraisal | Future survey results Future recording of personal development plans in new ERBs system (Employment and rewards business system) | n/a n/a |
| Employees feel they have opportunities to develop their career in the council 34% do not feel they have opportunities EPS – 68% LDS – 60% | Training – improve maximising training module (D11) Implement career development strategy | David Williams David Williams | Nov 06 Jan 08 | Employees feel they have opportunities to develop their career in the council | Maximising training evaluation feedback Future survey results | Instead we are to remove D11 and replace it with a completely new module that will be piloted early in 2007. The module will address this and several other related areas of concern n/a |
| Previous business units with particular areas of concern/issues on above (highlighted in italics) | Directors of the previous business units will decide on actions Report to SMT on directorates with areas of most concern when improvement plan reported Directors will communicate what action they plan to take to their employees | SMT SMT SMT | July 06 Oct 06 July 06 | Focussed attention on areas of council with most concern | Future survey results | Directors have identified and undertaken various actions These actions were shared and discussed within SMT Service Heads have communicated actions to employees within their respective service. Confirmed at joint SMT/Heads of Service meeting on 21 November |
| Employees (29%) disagree that the council has established a culture where they can contribute their ideas on how things are done | To be addressed within further development of MDP to address specific management skills | David Williams | Launch of new programme 07/08 (financial year) | Employees agree that the council has established a culture where they can contribute their ideas on how things are done | Future survey results Training evaluation feedback | n/a |
| Employees (17%) say their line manager gives them recognition for work well done rarely or never | Internal communication review To be addressed within further development of MDP to address specific management skills | Jason Gooding David Williams | July – Dec 06 Nov 06 | Improved communications Employees feel that their line manager gives them recognition for work well done | Future survey results IiP profile indicator 5 – managers are effective in leading, managing and developing people | Review is underway New provision of skills development included within MDP |
| A quarter of employees think they are ‘sometimes’ motivated by their line manager and a quarter think they are ‘rarely’ or ‘never’ motivated | To be addressed within further development of MDP to address specific management skills | David Williams | Launch of new programme 07/08 (financial year) | Employees feel motivated by their line manager | Future survey results Training evaluation feedback IiP Indicator 5 – managers are effective in leading, managing and developing people | n/a |
| Employees (36%) feel that the council 'sometimes’ deals effectively with staff absence | 55) Raise awareness of what is being done to try and reduce e.g. management briefing, Member-Officer Forum display June/July 2006 | David Williams | Dedicated sickness management briefing June 06 and cascaded by managers Other methods will be used following outcomes of internal communications review | Employees feel that the council deals effectively with staff absence | Future survey results | Management Briefing held in June. Also a subject of the Member-Officer Forum held 7 November 2006 |
| Employees (52%) are ‘not sure’ if the council deals effectively with stress | Raise awareness of training and policy e.g. management briefing, Member-Officer Forum display June/July 2006 Roll-out the stress audit and associated support | David Williams | Highlighted at June management briefing and cascaded by managers Other methods will be used following outcomes of internal communications review Ongoing and Complete 2008 | Employees feel that the council deals effectively with stress | Future survey results Comparison with results of 2008 audit to see if actions have made a difference | No progress yet. Internal communications review is still underway One third of council have completed audit with rest scheduled over next 12 months |
| Employees (45%) are unsure that the council deals effectively with violence and aggression from the public | Need to raise awareness of few incidents and that are treated seriously e.g. management briefing, Member-Officer Forum display Aug 2006 | David Williams | Highlighted at June management briefing and cascaded by managers Aug 06 Other methods will be used following outcomes of internal communications review | Employees feel that the council deals effectively with violence and aggression from the public | Future survey results | No progress yet. Internal communications review is still underway |
| Employees (35%) are unsure if the council deals effectively with accidents at work | Need to raise awareness of few incidents and that will be treated seriously e.g. management briefing, Member-Officer Forum display Aug 2006 Communicate Workforce Profile within WDP | David Williams | Highlighted at June management briefing Aug 06 | Employees feel that the council deals effectively with accidents at work | Future survey results | Statistics presented at June Management Briefing |
| A quarter of employees disagree that they feel their job is secure | Review of existing framework for recruitment and retention | Jean Cross | June 07 | Reviewed policies | Future survey results PWS | n/a |
| Communications | Report on LP142 - % staff with internal communications | Jo Osborne | Published in BVPP June 06 | LP142 reported | Improvement in performance | Reported in BVPP 2006/07 |
| Flexible working | Part of proposed Employee-Wellbeing strategy – review policies and reflect current review of flexible working | David Williams | Feb 07 | Flexible working policy | Future survey results | n/a |
| Equal access | Incorporate feedback into Corporate Equality Action plan Report on BV2b | Jennifer Williams Lesley Dixon | June 07 Published in BVPP June 06 | Incorporated into ongoing equality work BV2b reported | Future survey results BVPP 2006/07 | Incorporated into Corporate Equality Action Plan Reported in BVPP 2006/07 |
| Customer contact centre | Equal access issues in literal report | Michael Battersby |  |  | Future survey results | Issue under review |
| Staff communication of employee survey | Present results to management briefing Put report on public folders Send headline actions to employees Put improvement plan on public folders Directorates with particular areas of concern to communicate planned actions to employees in directorate Communication of simple messages e.g. what the council is doing and how this links into employee perceptions – include in internal communications strategy | David Williams Jennifer Williams SMT Jason Gooding | 7th Feb 06 8th Feb 06 June 06 June 06 July 06 Oct 06 | Survey results and action plan fed back to employees Planned action communicated to appropriate employees Improved communications | Future survey results | Briefing held in February 2006 Survey Report went on Public Folders in February Headline actions presented to all employees in letter from the Chief Executive in June Improvement Plan on Public Folders in June Service Heads have communicated actions to employees within their respective service. Confirmed at joint SMT/Heads of Service meeting on 21 November Draft Internal Communications Strategy considered by SMT on 21 November |
| Member communication | Report improvement plan to JMT Report improvement plan to CROS | David Williams | July 06 July 27th | Survey action plan reported to Members | Members informed of planned improvements | Reported to JMT in July Reported to CROS in July, who will be scrutinising progress on 7 December |
| Union communication | Report improvement plan to CJC | David Williams | 14th June 06 | Survey results and action plan reported to Unions | CJC informed of planned improvements | Reported to CJC in June, who will be discussing progress on 13 December |
| Monitoring of Improvement Plan | Report to SMT, CJC and Corporate Resources Overview and Scrutiny Directors to report progress on addressing areas of concern in previous business units | David Williams/ Jennifer Williams SMT | Oct 06 Oct 06 | Progress of actions | Employee Survey | CJC updated on progress in October, SMT in November and CROS scheduled for December Service Heads have communicated actions to employees within their respective service. Confirmed at joint SMT/Heads of Service meeting on 21 November |